Conformed copy subject to

IFAD management approval

PROJECT SUPERVISION MISSION – AIDE MEMOIRE

Rewarding the Upland Poor for Environmental Services (RUPES) (TAG 534)

(12 to 21 November 2006)

###### I. Introduction

An IFAD Mission undertook a supervision of the Rewarding the Upland Poor for Environmental Services (RUPES) project from 12 to 21 November 2006.  The project is financed by an IFAD grant (TAG-534) and is being implemented by the World Agroforestry Centre (ICRAF).

The mission visited one of the RUPES pilot sites in the Philippines (Bakun), met with the teams responsible for implementing RUPES in that country.   The mission then spent some time at the project headquarters at Bogor where it had discussions with RUPES and ICRAF staff.   The mission would like to particularly thank Dr Meine van Noordwijk ICRAF Regional Coordinator and RUPES Coordinator, Ms Beria Leimona, RUPES Manager, and Ms Grace Villamor, Coordinator of RUPES Philippines.

This Aide Memoire presents the findings of the mission, and includes recommendations as discussed in a meeting with RUPES management on 19 November.

II. Overall Implementation Status

Grant Performance Evaluation

| Implementation Progress (Grant Manager assessment of specific implementation progress indicators) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Progress Indicators | Last | Current | Progress Indicators | Last | Current |
| Timely availability of counterpart resources | 1 | 1 | Coherence between AWP/B & implementation | 1 | 1 |
| Timely availability of cofinancing | 1 | 1 | Timeliness of audit | - | - |
| Grant disbursement rate | 1 | 1 | Quality of accounts | 1 | 1 |
| Achievement of targets and outputs | 2 | 2 | Project management performance | 2 | 2 |
| Performance of M&E system | 3 | 2 | Stakeholder participation | 1 | 1 |
| Timeliness of reporting | 1 | 1 | Institution building and linkages | 2 | 2 |

Rating scale:   (1) Above or on target    (2) Mostly on target    (3) Substantially below target    (4) Little or no progress

(a) Action research sites

Work at five of the six pilot sites has now almost be completed and is scheduled to end in December 2006.  The exception is the Bakun site in the Philippines which is only now entering its third and final year, and where work will continue in the first half of 2007.  Exit strategies (prepared for all except Sinkarak?) show that, at most sites, many activities relating to development and environmental services will continue with support from other partners.  However there seems less potential for future support for Kulekhani in Nepal, possibly because donor and NGO activities have been, until recently, severely constrained by the security situation.

(b) Reports and communications

The project has continued to produce a significant number of publications and reports.  Materials produced in 2006 include:

Books:

- Rapid Hydrological Appraisal in the Context of Environmental Service Rewards, Kevin Jeanes, Meine van Noordwijk, Laxman Joshi, Atiek Widayati, Farida, and Beria Leimona

- Rapid Agrobiodiversity Appraisal (RABA) in the Context of Environmental Service Rewards Susilo Ady Kuncoro, Meine van Noordwijk, Endri Martini, Pornwilai Saipothong, Veronika Areskoug, Andree Ekadinata Putra, and Trudy O’Connor

Papers:

- Conceptual Framework for Economic Valuation of Environmental Services in Southeast Asia for the RUPES Program, M Kallesoe and U Iftikhar

- Rapid Hydrological Appraisal of Singkarak Lake in the Context of Rewarding Upland Poor for Environmental Services, Farida, K Jeanes, D Kurniasari, A Widayati, A Ekadinata, D Presetyo Hadi, L Joshi, D Suyamto, M van Noordwijk

- Criteria and Indicators of Compensation and Rewards for Environmental Services, draft paper developed under the IDRC Global Scoping Study

- PES – Means for Watershed Protection and Poverty Alleviation: Case Studies in the Philippine’ Uplands. Villamor, G. and R. Lasco. (in prep)

- ‘Rewarding Upland Poor for the Environmental Services –RUPES’ – an ‘environmental instrument’ for the empowerment of the poorest in Vietnam - lessons learnt, Minh Ha Fagerstrom

- Rewards for environmental services for poverty alleviation (in Indonesian), S Suyanto, N Khususiyah, submitted to Jurnal Ago Ekonomi

- Poverty and Environmental Services: Case Study in Way Besai Watershed, Lampung, S Suyanto, N Khususiyah, B Leimona, submitted to Journal of Ecology and Society

- Looking through the Eyes of the future: Rewarding Upland Poor for Environmental Services in the Philippines, Victoria Espaldon

Book chapters:

In Community Forest Management as a Carbon Mitigation Option, ed D Murdiyarso and M Skutsch, CIFOR:

- The Ikalahan Ancestral Domain, the Philippines, Grace B. Villamor and Rodel D. Lasco

- Singkarak: Combining Environmental Service Markets for Carbon and Watershed Functions? Beria Leimona, Rizaldi Boer, Bustanul Arifin, Daniel Murdiyarso and Meine van Noordwijk

Booklets:

- Sumberjaya brief 1: Pathway to healthy landscape and enhance livelihood

- Sumberjaya brief 2: Clean River, Lights On

- Seeking Rewards for Conserving Biodiversity in Traditional Rubber Agroforests in Bungo (with KKI-WARSI, YGB and IUCN

- Erosion and land care, and river care leaflets re Sumberjaya in Indonesian.

Video:

- Exploring and developing reward mechanisms for upland farmers for watershed functions in Sumberjaya.

Internet

- Website updated with new information and access to all RUPES publications. Policy is to keep the site current and active with brief information for easy access.

- Regular posting on “highlights” and “information on fundings” items.

- Links to ENRAP website and IFAD website added as recommended by IFAD Mission 2005.

- New links added to relevant websites, upcoming conferences and meetings in the region.

- Webpage for the 2007 RUPES Global Event developed

(c) Workshops, seminars and training

In total, RUPES project staff and representatives participated in 29 seminars and workshops within the events delivering 20 presentations, 2 poster displays and 5 papers, and joining 2 exhibitions.   Participation in workshops and other events included:

- Participation of RUPES Action Research Site Leaders at Carbon Expo, Germany May 2006

- Presentation on the potential of RUPES sites involving carbon markets by Dr. Daniel Murdiyarso, an ISC member in the IISD side-event, UNFCC SBSTA 24 in Bonn, May 2006.

- Presentation of “Transaction Cost Analysis of Upstream-Downstream Relations in Watershed Services: Lessons from Community-Based Forestry Management in Sumatra, Indonesia”, Dr. Bustanul Arifin, at the 26th Conference of the International Association of Agricultural Economists (IAAE), Gold Coast, Queensland, Australia, August 2006

- Agro-biodiversity and CGIAR tree and forest science: approaches and examples from Sumatra, Meine van Noordwijk, Jean-Laurent Pfund, Mohammed Bakarr, Louise Jackson, Goetz Schroth, Kurniatun Hairiah and Laxman Joshi, at Biodiversity Conservation in Agriculture May 2006 Dominican Republic

- Criteria amd Mechanism for Rewarding Upland Poor for the Environmental Services they Provide, Meine van Noordwijk, Bustanul Arifin, and Beria Leimona, at seminar on Multifunctionality of Agriculture ,  Bogor June 2006

- What criteria and indicators can or should be used to evaluate the actual/potential effectiveness of ‘pro-poor mechanisms of compensation for ecosystem services’? Beria Leimona, Meine van Noordwijk, South Asia Regional Workshop on Compensating for Ecosystems Services, Institute for Social and Economic Change, Bangalore, India

- Participation in IDRC Scoping Study Global Workshop and Annual Meeting, Beria Leimona, Nairobi, Kenya

- Rewarding Communities for Keeping Rivers Clean, R H Widodo, S Suyanto, B Verbist, B Lusiana, Susanto, P Purnomosdhi, at 4th Internatioal Symposium on South-east Asian Water & Environment, Bangkok, December 2006.

- Environmental Systems and Livelihoods, S Suyanto, Gajahmada University, Jojjakarta, Indonesia, April 2006.

- Impacts of conditional land tenure agreements in contested watersheds in Lampung, Indonesia: poverty alleviation and commitments to protect the remaining forest, S Suyanto, Kennedy School of Government, Harvard University, USA, April 2006

- Conservation paradigm: payment and market schemes for biodiversity protection. Villamor, G. and R. Lasco. 2006. Paper presented in the BBEC 4th International Conference, 14-16 February 2006, UMS, Kota Kinabalu, Malaysia.

- A bright future for the Philippines’ upland poor. Villamor, G. and R. Lasco. 2006. Paper submitted to the International Symposium Towards Sustainable Livelihoods and Ecosystems in Mountainous Regions, 7-9 March 2006, Chiang Mai.

- RUPES: Payments for Watershed Functions - Application of Rapid Hydrological Appraisal (RHA) in Bakun Watershed, Philippines. Villamor, G. B., Cruz, R.V., Lasco, R. D., and Sanchez, P.A. 2006. Paper submitted to the International Seminar-Workshop on Integrated Water Resources Management, 4-8 September 2006, Quezon City. (Submitted to Journal for Forest Research)

Training provided included the methodology for poverty baseline surveys, and skills enhancement for stakeholders engaging in ES transfer agreements

The national level technical committees held meetings in Indonesia and Philippines, and meetings were also held with government agencies in Indonesia, Vietnam and Philippines.

(d) Project expenditure

Compared with 2005, the pace of expenditure of IFAD funds has accelerated in 2006, and by the end of the year, it is estimated that US$244,000 will have been spent, almost 25% of the total allocation for the 5.5 year period.  This includes payments for a number of activities that were carried out in 2004   A balance of just over US$50,000 will remain for the final six months of the project in 2007 (see Table 1).  RUPES proposes to reallocate about UD$22,000 from operational costs to action research to fund completion of site activities.

Table 1: Expenditure of IFAD funds

| US $ | Project Allocation 2002-2007 | Actual expenditure |  |  |  |  | Forecast | Balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2002 Jan-Dec | 2003 Jan-Dec | 2004 Jan-Dec | 2005 Jan-Dec | 2006 Jan-Sep | 2006 Oct-Dec* | 2007 Jan-Jun |
| Staff (Institutional Specialist and Project Leader | 400,000 | 57,210 | 152,091 | 97,309 | 32,099 | 30,827 | 9,164 | 21,300 |
| Operational Cost | 420,000 | 38,321 | 75,965 | 80,039 | 51,123 | 28,650 | 12,356 | 133,547 |
| Consultation & Workshop | 80,000 | 40,793 | 7,078 | 77,953 | 48,974 | 6,371 | 5,324 | (106,493) |
| Action Research / TA Support | 500,000 | 3,429 | 73,026 | 141,139 | 28,596 | 182,158 | 69,405 | 2,248 |
| Total | 1,400,000 | 139,753 | 308,160 | 396,440 | 160,791 | 248,006 | 96,249 | 50,601 |

Total expenditure of IFAD funds at pilot sites amounts to over US$425,000, or 30% of total project expenditure (Table 2).  RUPES continues to be successful in mobilising funds for sub-projects in support of core RUPES activities.   Out of 53 proposals submitted, 17 have so far been funded, with the total funds raised being US$3.47 million, almost 2.5 times more than the IFAD funding for RUPES (Table 3).

Table 2: Expenditure of IFAD funds at pilot sites

US dollars

| Site | Actual 2003 | Actual 2004 | Actual 2005 | Budget 2005 | Budget 2006-7 | Total 2003-2007 |
| --- | --- | --- | --- | --- | --- | --- |
| Bungo |  | 6,436.00 | 23,839.21 | 45,733.00 | 44,724.79 | 75,000.00 |
| Bakun |  | 22,740.00 | 19,195.91 | 13,644.00 | 3,545.09 | 45,481.00 |
| Sumberjaya |  | 23,060.00 | 34,319.94 | 30,000.00 | 37,620.06 | 95,000.00 |
| Singkarak |  | 21,250.00 | 6,471.17 | 23,750.00 | 24,818.83 | 52,540.00 |
| Kalahan | 14,948.00 | 21,411.00 | 22,614.08 | 29,823.00 | 7,208.92 | 66,182.00 |
| Kulekhani | 18,401.00 | 20,682.00 | 22,336.55 | 52,217.00 | 29,880.45 | 91,300.00 |
| Total | 33,349.00 | 115,579.00 | 128,776.86 | 195,167.00 | 147,798.14 | 425,503.00 |

The project grant agreement between IFAD and ICRAF states that ICRAF would mobilise an additional US$3.53 million in funding alongside the US$1.4 million grant from IFAD.  These additional funds would come from ICRAF itself and from other donors.   The actual amount of additional funding mobilised will amount to about US$3.94 million (including an estimated US$0.81 million to be contributed by donors in 2007 – see Table 4).   This excludes the cost of ICRAF headquarters staff, staff time for partners on ISC and TEC meetings, and other in-find contributions.  Much of this money is for specific sub-projects, and most of the US$3.47 million shown in Table 3 is included in the Table 4 amounts (funding for some sub-projects is likely to continue into 2007, and this may not be in Table 4).

Table 3: Sub-project proposals and awards

|  | Proposals submitted |  | Successful to date* |  |
| --- | --- | --- | --- | --- |
|  | Number | Value (US$) | Number | Value (US$) |
| 2003 | 16 | 7,692,103 | 3 | 15,000 |
| 2004 | 9 | 3,347,579 | 4 | 555,000 |
| 2005 | 10 | 7,905,020 | 5 | 1,402,986 |
| 2006 | 18 | 5,527,642 | 5 | 1,497,728 |
| Total | 53 | 24,472,344 | 17 | 3,470,714 |

* some proposals are still under consideration

Table 4: RUPES funding from other donors

US dollars

| Donor | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ACAR | 80,961 | 283,971 | 166,124 | 119,462 | 138,438 | 77,378 | 866,334 |
| BMZ | - | - | - | - | - | 31,500 | 31,500 |
| CIF | - | - | - | - | 115,227 | 110,938 | 226,165 |
| DFID | - | 30,000 | 23,250 |  | 183,024 | 66,717 | 302,991 |
| EEPSEA | - | - | - | - | 16,556 | 18,996 | 35,552 |
| EU | 111,680 | 143,795 | 106,500 | 59,669 | 328,000 | 265,549 | 1,015,193 |
| FAO | - | - | 15,000 | - | - | - | 15,000 |
| FORD | 67,430 | 975 | - | - | 116,357 | 75,212 | 259,974 |
| GPW | 2,966 | - | - | - | - | - | 2,966 |
| IBRD | - | 62,892 | - | - | - | - | 62,892 |
| ICRAF CORE | - | 53,522 | 7,496 | - | - | 18,400 | 79,418 |
| IDRC | - | - | - | - | 348,944 | - | 348,944 |
| IFPR/MSU-USAID | 39,000 | - | 51,000 | 95,184 | 63,119 | 141,204 | 389,507 |
| IIED | - | - | 7,371 | 5,518 | - | - | 12,889 |
| IIEF | - | - | 15,000 | 15,800 | - | - | 30,800 |
| IRD | - | 3,821 | - | - | - | - | 3,821 |
| SIDA | - | 10,000 | - | - | - | - | 10,000 |
| SII | - | 50,946 | 5,466 | 12,809 | - | - | 69,221 |
| USAID | 76,336 | - | 94,207 | - | - | - | 170,543 |
| WWF | - | - | - | - | - | 5,935 | 5,935 |
| Total | 378,373 | 639,922 | 491,414 | 308,442 | 1,309,665 | 811,829 | 3,939,645 |

(e) Tasks for 2007

RUPES management has identified the following tasks for the remainder of the project period (up to June 2007):

- Conduct the RUPES Global Event and ISC meeting in January 2007

- Support remaining site activities (primarily Bakun)

- Complete all publications in pipeline (including editing, layout/formatting, distributing)

- Complete studies at cross-site level: land-management vs ES provision, poverty, buyer, policy impact.

- Complete RUPES Self-Evaluation

- Complete RUPES TANs

- Finalize RUPES Phase II Proposal

- Deliver RUPES Final Report to IFAD (Technical and Financial)

(e) Status of the recommendations of the last supervision mission

| Recommendations | Actions taken |
| --- | --- |
| RUPES logframe |  |
| - Revise RUPES programme logframe with a view of merging overlapping sets of tasks and activities | This has been done and approved by ISC |
| Payments for Environmental Services |  |
| - Hold discussions with buyers and potential buyers with a view to establishing system of payment related to specific ES | Study of potential buyers about to be undertaken in Philippines and Indonesia. Participation in IRDC scoping study on global market for ES. |
| Impact on poverty |  |
| - Evaluate impact of ES rewards on poverty | Participatory poverty assessments planned and training completed |
| Exit strategy |  |
| - Prepare exit strategies for pilot sites and TECs | Strategies prepared for 5 of 6 sites. The two TECs are now self-sustaining. |
| Reporting |  |
| - Base reports on project logframe, with tables to summarise site activities | Annual report 2006 under preparation. Initial draft is based on logframe outputs |
| Project completion reporting |  |
| - Prepare final completion report | Planned for 2007 |
| Project period extension |  |
| - IFAD to process extension of contract agreement | Done |
| Linkage with other IFAD projects |  |
| - Better linkages required | Attended IFAD regional workshop. Influencing design of CHARM II (Philippines) and new project in Vietnam. TANs are being prepared. |

III. Results and Impact Management

A. Achievement of project outputs

|  | Output | Highlights of Achievements in 2006 |
| --- | --- | --- |
| 1 | Identify environmental service functions in various settings, and assess where and how their benefits are distributed | - Reports and studies produced prior to 2006 have identified these services. Work is continuing for each site to develop criteria and indicators for watershed functions, and trade-off scenarios between land use changes and ES criteria. - Training in participatory analysis of multi-dimensional poverty levels has been undertaken, and focus group discussions will gather information on constraints on communities effectively benefiting from ES - Survey of ES buyers is being carried out in Indonesia and Philippines - Report on ES lessons learned in Vietnam has been produced in 2006. |
| 2 | Develop and test mechanisms to reward the poor for the environmental services they provide in three to four sites across a range of settings. | - Collaboration with RUPES action research sites and leaning sites includes assistance for Kalahan in developing a PIN for carbon sales - Trial of reverse auction at Sumbarjaya for willingness to accept payments to adopt soil conservation practices. - “River care” programme at Sumberjaya with payments for community based on sediment loads. - Research site leaders participated in Carbon Expo 2006 in Germany - Exit strategies for five of six sites developed |
| 3 | Support a transparent enabling institutional environment at local, sub-national, and national levels to deliver rewards that are effective, equitable, and sensitive to marginalised groups. | - Training sessions (10) for site teams to support local institutions involved in negotiating ES sales. - Policy advocacy work in 2006 included presentations of Indonesia and Philippines TECs at national workshops. A national workshop with DENR will be held in Philippines on 6 December 2006 - Agreement with Ministry of Forests (Indonesia) to conduct study of policy impacts. Drafting national guidelines for ES financing mechanisms |
| 4 | Raise awareness among government officials, and ES producers and consumers of the potential for rewards to enhance environmental services. | - Website is being maintained and up-dated, and new links added. - Communication materials produced - Participation in seminars and other events. - Material translated into Indonesian and Vietnamese - RUPES Global Event planned for January 2007 - Research on communication efforts with Wageningen Agricultural University - Communications with IFAD: presentation in Rome February & March 2006, attend regional workshop in Bangkok in June 2006, preparing series of TANs. |
| 5 | Develop and manage effective partnerships among consortium member institutions and regional, national and local organisations. | - Four new proposals for sub-projects submitted to partners/donors in 2006 - Meetings of national networks (5 in Philippines and 2 in Indonesia) - RHA toolkit – training in Lombok in September 2006, field work in October 2006. - Annual RUPES ISC meeting deferred to Global Event in January 2007 – where many partners will participate. |

B. Progress towards project objectives

The goal of the project (in the revised logframe) is to “Develop new mechanisms for enhanced livelihood and resource security of poor upland communities in Asia”.  This is to be achieved via the project purpose which is to “Create the basis for systems to reward the poor for the environmental services they provide for the global and national communities”.

The indicators in the logframe at goal level are:

- Increased income and food security, ensured security of access to land, and better welfare of households and communities managing environmental services in upland watersheds; and

- Improved and safeguarded environmental values including hydrological/watershed functions, biodiversity/landscape, and carbon sequestration.

It appears unlikely that actual payments for environmental services such as reduced carbon emissions, clean water or bio-diversity will be sufficient to make such a significant contribution to local incomes as to directly reduce poverty.  The potential value of trees in terms of certificates for reduced carbon emissions is only one sixth of the value of timber (even before transaction costs are taken into account).  Payments for watershed values (water for hydropower schemes) only amount to a dollar or so per head of population per year, and are not yet related to actual provision of environmental services (such as reducing silt loads through better land management.  Given the limited value of potential rewards, RUPES has developed Rapid Hydrological Assessment, Rapid Carbon Assessment and Rapid Agrobiodiversity Assessment as tools to enable initial quantification of ES without the high cost of detailed evaluation studies.  This enables buyers to be identified and ES sale negotiations to start with lower transaction costs.

The process of identifying and valuing environmental services has increased awareness of watershed conservation and better land management, and has also built social capital.   Adoption of improved practices can have a direct impact on agricultural production – such as improved and more sustainable yields of coffee at Sumberjaya.   The project has also helped local communities get a share of water royalty payments channelled to local government rather than remain in the hands of national or provincial authorities.

At the purpose level, logframe indicators are:

- Agreements have been activated in at least 6 project sites that recognise local communities' land use rights in recognition for their efforts to improve the environmental services provided by their local watersheds.

- Increased adoption of agroforestry and community forestry practices by large numbers of small holder households across at least 6 project sites

- More effective locally-led natural resource management institutions are in place that actively manage environmental services in upland watersheds in partnership with local and national government bodies in at least 6 project sites.

At all six action research sites, communities have rights to utilise and manage land.   At Sumberjaya farmers, who were illegally occupying forest land and converting it to coffee, are now getting leases on this land in return for maintaining some forest trees as shade for coffee. During the mission the Ministry of Forests announced new national guidelines for granting such leases based on the model in Sumberjaya and acknowledging the role of ICRAF in developing this arrangement.

At the other two sites in Indonesia, the original communities have land rights, although much land has now been taken by in-coming settlers and, in Bungo, by oil palm and rubber plantations.   At the two sites in the Philippines tribal communities also have land rights.   At Kulekhani in Nepal much of the watershed is government forest land, but this is now under community management through the Community Forest Scheme.   This has provided incentives, via forest user rights, for communities to allow forests to regenerate, resulting in broader watershed benefits.

Of the six sites, only in Sumberjaya and Kulekhani can improved access to land be said to be in return for an environmental service (better forest land management).  At the other locations, communities access rights have come about in order to provide equitable access to original inhabitants of the area.   At Sumberjaya, land rights in return for better management was bought about by concern for the watershed and its environmental values, but at Kalekhani community forestry was driven by the need to improve forest management rather than broader environmental values.

RUPES and other initiatives have encouraged adoption of improved land and forest management practices.  This is especially apparent at Sumberjaya (where it has now gone beyond coffee agro-forestry to “river care”) and at Kalahan where a sustainable and ecological approach to land use has been promoted by an effective organisation of tribal people (but where RUPES interventions may have played a relatively minor role).   At Bakan and Bungo there are pressures to convert land to more commercial use (vegetables at Bakun and plantations at Bungo) leading a deterioration in the Bakun watershed and loss of biodiversity at Bungo.

The project has worked effectively with local organisations at all six sites, and has helped build their awareness and capacity on environmental issues.  These organisations interact effectively local government.

.

IV. Mission Recommendations

- Progress in Nepal

Understandably activities in Nepal have lagged behind Indonesia and Philippines.  Now that peace is hopefully breaking out, there are opportunities to focus more on this country, especially beyond the Kalekhani site, to make an impact on other development agencies and NGOs, and to be part of the process to generate policy ideas for a future government.  In particular only one RUPES document has, as yet, focused on this country.

- Focus on buyers of environmental services

If real payments for environmental services are to materialise, in terms of payments linked to actual delivery of specific services (such as water with a defined level of silt), then it would be helpful if the project were to focus more on buyers of ES – such as hydro-power companies, irrigation authorise, carbon trading organisations and owners of eco-friendly labels.  The project is only now carrying out a survey of ES buyers, and this needs to be at a national rather than local level as these tend to be national level organisations.  The best opportunities for the introduction of watershed PES could be where new sources of water are being tapped, and where the user of this water wants to ensure that the watershed is protected.

- Innovations on agro-forestry

Support for innovations in agro-forestry could make sustainable land use systems financially more attractive, so reducing pressure in places such as Bungo and Bakun to convert land to monoculture, while also helping to reduce poverty.   If the introduction of these innovations were to be funded by users of ES (such as hydro-power companies), then they could be considered as rewards for ES.

- Links with IFAD

RUPES has done well this year in strengthening its links with IFAD.  In particular it attended the annual Asia region workshop in Bangkok, which seems to have led on to further meetings with the CPM for Vietnam and the incorporation of an ES approach into the design of a new IFAD project in that country.  IFAD has requested that RUPES produce some TANs with the main objective of providing inputs for the design of future projects.  These TANs should follow the standard IFAD format, and should be on the basis of a “why and how to do” for a particular ES.   Other material produced by RUPES is also useful for IFAD in spreading the overall message about RES.

- Project completion

All project activities will need to be completed by the end of June 2007.  This will include exit strategies for all sites (the strategy for Singkarak needs to be completed), the self-evaluation and final project report.  The final report needs to document all activities, outputs and results of the project, including comprehensive lists of all publications, workshops etc. (the publication lists given to the mission omitted much of what has been produced).  The draft of the 2006 Annual Report also lacks information on RUPES learning/associate sites, which are a key for dissemination of RUPES learning through effective partnerships.  Information on these sites should be included in the final report.

- Planning of RUPES II

ICRAF would like to build on the achievement of RUPES through a follow-up project.  IFAD has indicated that it may be interested in financing such a RUPES II, but this will need to be in partnership with at least one other donor.   The timeline for submission of a RUPES II grant proposal to IFAD is as follows:

  - A concept note, in IFAD standard format, must be ready by the end of March 2007 at the latest so that it can be submitted to the Grant Screening Committee (GSC) in April 2007.

  - If accepted by the GSC, a revised concept note, incorporating comments from the GSC must be submitted by end of April as the OSC (Operational Strategy and Policy Guidance Committee) is in May 2007.

  - The full design document, in standard IFAD format, must be ready by end of May as the TRC (Technical Review Committee) is in June 2007.

The concept note for RUPES II will need to be submitted as part of the competitive grants programme, hence the GSC meeting in April will score RUPES II against other proposals from other regions. Only the top proposals, with the highest scores, get approved for the OSC in May.   As this is a Phase II project, co-financing is critical. If there is no firm agreement on significant co-financing, the proposal will not get through the GSC.

The basic strategy for the use of IFAD grant resources is to test ideas that can be up-scaled by future IFAD projects.   It would therefore be useful to focus on IFAD target groups and strategic priorities and include provision for linkages with the IFAD project design process.

- Edward Mallorie (mission leader), Dr Dev Nathan (economist).