IFAD

SUPERVISION MISSION REPORT

ICRAF TAG-534:

REWARD THE ASIAN UPLAND POOR

FOR THE ENVIRONMENTAL SERVICES

THEY PROVIDE

(RUPES)

Asia and the Pacific Division

Programme Management Department

March 2004

Table of Contents

Page

Weights and Measures	ii

Abbreviations and Acronyms	ii

Fiscal Year		ii

SECTION 1: Supervision Summary

A. Project Basic Data, Objectives and Components

B. Project Performance Evaluation

SECTION 2: Project Status Implementation

A. Introduction

B. Project Progress and Achievements

C. Status of the recommendations of the last supervision mission

D. Project cost and funding

E. Project Management

SECTION 3: Mission Recommendations

APPENDIX 1:

APPENDIX 2:

APPENDIX 3:

APPENDIX 4:

APPENDIX 5:

- Weights and measures

1 kilogram (kg)	=	2.204 pounds (lb)

1,000 kg	=	1 metric ton (mt)

1 kilometre (km)	=	0.62 mile (mi)

1 metre (m)	=	1.09 yards (yd)

1 square metre (m2)	=	10.76 square feet (ft2)

1 acre (ac)	=	0.405 hectare (ha)

1 hectare (ha)	=	2.47 acres

- Abbreviations and acronyms

ASB	Alternative to Slash and Burn

AWPB	Annual Workplan and Budget

BITO 	Bakun Indigenous Tribal Organization

CBD	Convention on Biological Diversity

CFI	Community Forestry International

CGIAR	Consultative Group on International Agriculture Research

CHARM	Cordillera Highland Agricultural Resource Management (Project)

CI	Conservation International

CIFOR	Centre for International Forestry Research

CPM	Country Portfolio Management

DENR	Department of Environment and Natural Resources

EEPSEA	Economy and Environmental Programme for Southeast Asia

ENRAP	Electronic Networking for Rural Asia/Pacific Projects

ES	Environmental Services

FPE	Foundation for Philippine Envuironment

FY	Fiscal Year

ICRAF	World Agroforestry Centre

ICRAFSEA	ICRAF Southeast Asia Programme

IDRC	International Development Research Centre

IIED	International Institute for Environment and Development

IFAD	International Fund for Agricultural Development

IPRA	Indigenous Peoples Rights Act

ISC	International Steering Committee

IUCN	World Conservation Union

LGU	Local Government Unit

NGO	Non Governmental Organisation

NRM	Natural Resources Management

PAFID 	Philippine Association for Intercultural Development

PDR	Peoples Democratic Republic

RUPES	Reward the Upland Poor for the Environmental Services They Provide

SHG	Self Help Groups

TAG	Technical Assistance Grant

TEC 	(National) Technical Committee

TOR	Terms of Reference

UPLB	University of the Philippines at Los Banos

WWF	Worldwide Fund for Nature

WRI	World Resources Institute

WSSD	World Summit on Sustainable Development

- ICRAF (World Agroforestry Centre)

- Fiscal Year: 1 January – 31 December

- SECTION 1

- Project supervision summary

- Project Basic Data, Objectives and Components

| Asia |  |  |  |  |  | Programme ID |  | ICRAF TAG 534 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Reward the Asian Upland Poor for the Environmental Services they provide |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date of Update: | 10/01/06 |  | Date Last Update |  |  | 13/01/04 |  |  |  |  |  |  |  |
| Coop. Inst. | IFAD supervision |  | Contact Person |  |  | N. Brett (IFAD, CPM) Meine van Noordwijk, ICRAF Regional Coordintor |  |  |  |  |  |  |  |
| Approval | 01/04/2001 |  | Original Closing |  |  | 31/12/06 |  |  | Last Amendment |  |  |  |  |
| Agreement | 01/04/2002 |  | Extended Closing |  |  | 30/06/07 |  |  | Last Audit |  |  |  |  |
| Effectiveness | 18/01/2002 |  | No. of extensions |  |  | 1 |  |  | Last Supervision |  |  |  |  |
|  |  |  |  |  |  |  |  |  | No. of Supervisions |  | 3 |  |  |
|  | USD m |  |  |  |  |  |  |  | Disbursement |  |  | Percentage |  |
| Programme cost | 4.23 |  |  |  |  |  |  |  | IFAD grant |  |  | 26% |  |
| IFAD grant | 1.40 |  |  |  |  |  |  |  |  |  |  |  |  |
| Cofinanciers |  | USD m |  |  |  |  |  |  |  |  |  |  |  |
| ICRAF/Int Partners |  | 0.77 | DFID 0.25 |  |  |  |  |  |  |  |  |  |  |
| ACAR |  | 0.79 | IFPR 0.25 |  |  |  |  |  |  |  |  |  |  |
| IDRC |  | 0.35 | EURU 0.42 |  |  |  |  |  |  |  |  |  |  |
| Programme Development Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The main programme objective is to create the basis for proven institutional mechanisms for recognising and rewarding IFAD target groups for the environmental services they provide. To achieve this the programme will develop an international consortium to create the knowledge to deploy rewards to upland communities Beneficiaries: Nearly 250mn people inhabiting the mountainous and hill regions of Asia could potentially benefit from receiving rewards for providing environmental services. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme components |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identification of environmental service functions Developing typology depending on land-use practices Identification characteristics of environmental services Identification beneficiaries Quantification of benefits Developing and testing an array of institutional mechanisms Identification and selection of representative action-research pilot sites Review of existing practices of benefit sharing Identification of key partners Testing environmental service transfer payments in action-research mode Development of replicable methods for benefit sharing |  |  |  | Support of enabling environment Identification of enabling environment Identification of existing supportive institutional environments and frameworks Capacity building of stakeholders Establishment of conducive policy framework Awareness-building Establishing communication platform Development and deployment of channels for dissemination Partnerships Partnerships of accomplishment of outputs Identification and development of partnerships Monitoring of partnerships Identification of institutional approach (now dropped) SWOT analysis of existing institutional mechanisms Preparation of business plan Identification of players in overseeing evolution of institutional options |  |  |  |  |  |  |  |  |  |

B.  Programme Performance Evaluation

| Implementation Progress: CPM’s assessment of specific implementation progress indicators (Indicators: 1 = Problem Free; 2 = Minor Problems; 3 = Major Problems, Improving; 4 = Major Problems, not Improving) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Progress Indicators |  | Last |  | Current | Impact Indicators |  | Last | Current |
| Compliance with Grant Covenants |  | 2 |  | 2 | Development Impact |  | NA | 3 |
| Availability of counterpart funds |  | 2 |  | 1 | Expected Benefits |  | NA | 3 |
| Quality of audits |  | -- |  | -- | Beneficiary Participation |  | NA | 1 |
| Quality of accounts |  | 2 |  | 1 | Institution Building |  | NA | 2 |
| Achievement of physical targets |  | 2 |  | 3 |  |  |  |  |
| Technical assistance progress |  | 1 |  | 1 | Yes/No |  |  |  |
| Performance of M&E system |  | 3 |  | 3 | Time overrun |  |  | Yes |
| Timeliness of reporting |  | 2 |  | 1 | Regular submission of AWP/B |  |  | Yes |
| Coherence between AWP/B & implementation |  | 2 |  | 1 | Acceptable disbursement rate |  |  | Yes |
| Programme management performance |  | 2 |  | 2 |  |  |  |  |
| CPM overall assessment of programme performance |  |  |  | 3 |  |  |  |  |
| (1) Problem-free | (2) Minor problems |  | (3) Major problems but improving |  |  | (4) Major problems and not improving |  |  |
| Comments on implementation progress (mandatory for criteria rated 3 or 4) |  |  |  |  |  |  |  |  |
| Progress towards objectives is limited as the potential for concrete rewards has not materialised as anticipated in the project design (in particular the Kyoto protocol has not resulted in flows of funds for carbon sequestration. Significant payments available for bio-diversity conservation and other environmental values have also not materialised. However there has been a growing willingness to pay for more localised ES such as conservation of watersheds and tourism resources. Although such payments (or other types of rewards) may not be large in themselves, they do acknowledge the interdependence of upland and lowland communities. Such rewards now exist in a number of RUPES pilot and associate watersheds, and RUPES has also been involved in promoting the concept at policy level. There is now a need to evaluate how such rewards can contribute to the livelihoods of the upland poor, including the planned participatory poverty assessments at the pilot sites. |  |  |  |  |  |  |  |  |

- SECTION 2

Project status implementation

A. Introduction

A supervision mission (Edward Mallorie, IFAD consultant) of the project Rewarding the Upland Poor for the Environmental Services They Provide (RUPES) took place from 28 November to 3 December 2005.  The project is financed by an IFAD grant (TAG-534) and is being implemented by the World Agroforestry Centre (ICRAF).

The mission visited one of the RUPES pilot sites in Indonesia (Sumberjaya), met with members of COMMITTEES (the project’s technical committee for Indonesia).   The mission also had extensive discussions with RUPES and ICRAF staff at the project headquarters at Bogor.   The mission would like to particularly thank Dr Meine van Noordwijk ICRAF Regional Coordinator and RUPES Coordinator, Ms Beria Leimona, RUPES Manager, Mr. S. Suyanto, RUPES Sumberjaya Site Leader, and Ms Grace Villamor, Coordinator of RUPES Philippines.    A list of people met is in Appendix 1.

B. Project progress and achievements

Progress towards project objectives

The project aims to develop mechanisms to provide the upland poor with rewards for the environmental services that they provide to local, national and international communities.  Progress towards this objective has been limited as the potential for concrete rewards has not materialised as anticipated at the time of project design.  When RUPES was planned there were high hopes that the Kyoto protocol would result in flows of funds for carbon sequestration, and that a proportion of these flows could be directed to smallholder upland agro-forestry systems.   It was also hoped that there would also be significant payments available for bio-diversity conservation and other environmental values.

By and large these hopes have not been realised (or at least not yet realised).   The failure of the USA and Australia to ratify the Kyoto protocol and complex procedures for the Clean Development Mechanisms has meant that carbon sequestration payments have not been as easily accessible and valuable as had been hoped.  More important, mechanisms so far have tended to emphasise the planting of new trees, and poor farmers may lack land for significant new planting.  Processes are also complicated and transaction costs are high.

Biodiversity payments have also yet to produce significant payments for poor communities.  Payments for biodiversity, often from international NGOs, tend to go for pristine ecosystems where there is little human activity, and hence little potential to benefit for many poor people.  Areas where poor people tend to live tend to be a mosaic of forest, field and agro-forestry, and not as highly valued for biodiversity unless as a buffer zone or connecting corridor for areas of undisturbed ecosystem.

However RUPES has been demonstrating some new ideas to improve the livelihoods of the upland poor.  Although significant payments in terms of “commoditised” environmental services (ES) have not materialised, there have been a growing willingness to pay for more localised ES such as conservation of watersheds and tourism resources.  Although such payments (or other types of rewards) may not be large in themselves, they do acknowledge the interdependence of upland and lowland communities.  Such rewards now exist in a number of RUPES pilot and associate watersheds, and RUPES has also been involved in promoting the concept at policy level.  Such rewards mean that:

- The upland poor are providing ES of economic importance to themselves and to other communities

- Environmental services are worth providing.

- Payment and support to the upland poor can be made conditional on achievement of ES goals.

This is a departure from the approach of providing the upland poor with external (government or donor) support in order to reduce poverty or protect the environment.  The rewards for environmental services (RES) approach links payment or support to these communities with their actions to provide ES.  It also seeks to mobilise, at least some funds from consumers of ES, thus creating more pressure for the provision of ES.

Review of outputs and activities

Output 1 - Studies and research - “Identification of environmental service functions in a range of settings, and assess where and how the benefits of these services currently are distributed”

In the two years (2004 and 2005) since the last supervision mission the project has produced 11 research papers with two more at a final draft stage.  These papers cover the identification and valuation of ES, the assessment of markets for ES and the potential for the poor to be rewarded.  The papers covered issues on provision of environmental services in Indonesia, Philippines, Sri Lanka and Vietnam.   Details of RUPES research papers are in Appendix 2.

To facilitate the identification of environmental values and functions, RUPES has developed and tested a number of tools including rapid hydrological assessment (RHA), rapid agro- biodiversity assessment (RABA) and the FALLOW landscape mosaic model.

Output 2 - Testing and pilots = “An array of mechanisms is developed and tested with communities in at least 6 sites, across a range of settings, that will reward the poor for the environmental services they provide”

RUPES is now working on six pilot sites in Indonesia (3), Philippines (2) and Nepal (1).  The project also has another six associate or learning sites, where activities are primarily implemented and funded by RUPES partner institutions.   Information on activities is the six pilot sites is summarised in the matrix in Appendix 3.   A description on the progress towards getting rewards for environmental services at RUPES sites, and a discussion of some of the issues involved, is in Appendix 4.

Although the security situation has, in general, affected development work in Nepal, the local implementing agency for the Kulekhani pilot site, Winrock International, says they are able to visit the field and work is continuing, although they are unable to hold large meetings at the community level. The registration of an organisation for suppliers of ES has been delayed.

At the Sumberjaya pilot site in Indonesia, detailed baseline data at plot and household level was collected for the Sumberjaya site (funded by the Belowground Biodiversity GEF project) and is currently being analyzed and synthesized for global comparison.    Proposals for carbon trading have been developed for the Kalahan site in the Philippines and local site organisations are preparing to enter negotiations with a broker.

RUPES plans to carry out participatory poverty assessments at all its pilot sites.  Although tools have been developed, and training given, this work has not yet started, and should be given a priority in 2006.

In addition, a RUPES training course in Chiang Mai and funded by SII Netherlands, has resulted in further interest in developing the RUPES approach in other countries, including China (where seven case studies have been funded by SII and RUPES) and India (where awareness raising activities have taken place at the national, state and local levels).

The mechanisms that are tested vary in scale (contracts with groups of farming households of different size), nature of the ‘reward’, timeframe of evaluation and level of conditionality. Some of the experience relates to efforts to channel existing ‘reward’ (including payments made for watershed protection or biodiversity conservation) flows more effectively to the actual providers of these services. Another part relates to efforts to enhance the level of rewards.

Output 3 - Policy and institutional environment – “A transparent enabling institutional environment at local, subnational, and national levels has been supported, so as to deliver rewards that are effective, equitable, and sensitive to marginalised groups (including ethnic groups and women)”

At site level in Indonesia, supporting institutional arrangements exist, and there is also an enabling legal framework.  Local level institutions have been established to facilitate RES at sites such as Lake Singkarak and Sumberjaya.  RUPES has been advising the government on ratification of the Kyoto protocol and on the implementation of reward mechanisms for CDM carbon projects.  RUPES has also been in dialogue with the government concerning the use of the national reforestation fund – which now has considerable unutilised resources.

In China there is considerable momentum at a high level to promote systems for PES.  However a policy review and case studies commissioned by RUPES show that such initiatives may lack support for implementation at a local level. Existing programmes often do not work well due to lack of participation and support from local stakeholders.

For the Philippines, a RUPES study “Rewards for Environmental Services in the Philippine Uplands: Constraints and Opportunities for Institutional Reform” has identified policy gaps and institutional constraints.  The findings were presented at the national RUPES workshop in the Philippines in March 2005.

In Nepal, the Ministry of Local Development is taking the initiative to prepare guidelines on the distribution of royalty payments from hydropower.   Upland communities are beginning to use ES arguments in asking for support from District Development Committees.

Carbon sequestration remains the most clearly defined “payment for an environmental service”, however it is problematic in terms of allowing smallholders to participate effectively.  RUPES is continuing to monitor developments in the CDM, including recent bi-lateral agreements between Indonesia and the Netherlands and Denmark (with agreements involving Canada and Austria expected soon).  A report on Promoting Smallholder Projects through the Clean Development Mechanism by Afforestation and Reforestation by Mogens Buch-Hansen (ICRAF) was presented and discussed at a RUPES meeting and circulated within the RUPES network.  A list of carbon trading brokers has been put on the RUPES website.

Output 4 – Communications – “Awareness of the potential for rewards to enhance environmental services has been raised among government officials, and the producers and consumers of these services”

RUPES has a well developed communications strategy.  A total of four newsletters have been produced (two in 2003 and two on 2004).  The RUPES website was expanded in 2004 and continues to be regularly updated.  There has been a significant increase in the number of RUPES website visitors, from around 1,000 per month in 2004 to over 2,000 per month in 2005. In October 2005 the number of visitors reached the highest ever - 2,400 visitors.   This increase can at least be partly attributed to the introduction of a system for emailing website users with notification of new material.  The top five countries of origin of visitors are: United States, Japan, Indonesia, Philippines, and the Netherlands. Most downloads are recorded for the page containing the working papers indicating considerable interest in the findings of RUPES.

RUPES project staff and representatives attended and participated in 22 meetings in 2004 and 19 in 2005 up to early December (excluding internal RUPES project meetings and including the Katoomba Group Meeting).  They also gave 35 presentations at various conferences (international and nationally) in 2004, and 29 in 2005.

To improve communications in Indonesia, a number of RUPES reports have been produced in Bahasa Indonesia, and other materials have been translated, including the IIED book “Silver Bullet or Fools Gold”, by Natasha Landell-Mills and Ina T. Porras.  The RUPES brochure has also been translated into Vietnamese and other reports produced in that language.

Output 5 – Partnerships – “Effective partnerships among consortium member institutions and regional, national and local organisations have been developed and managed”

The RUPES International Steering Committee (ISC) reflects the broad partnerships that RUPES has created.  In 2004 the World Bank joined the ISC, with Forest Trends (an NGO) admitted with observer status.  The ISC includes representatives of the following organisations: ICRAF, IFAD, World Bank, CIFOR, WWF, IIED, Conservation International, Winrock, IUCN , Ford Foundation, The Nature Conservancy, plus the chairs of the national technical committees.

RUPES has been able to further develop partnerships and mobilise additional resources via the implementation of a number of sub-projects funded by ISC partners and other agencies.  To date, a total of 35 proposals have been submitted, of which 12 have been successful, generating funding of almost US$ 2 million (see Table 1).

Table 1: Sub-project proposals and awards

|  | Proposals submitted |  | Successful to date* |  |
| --- | --- | --- | --- | --- |
|  | Number | Value (US$) | number | Value (US$) |
| 2003 | 16 | 7,692,103 | 3 | 15,000 |
| 2004 | 9 | 3,347,579 | 4 | 555,000 |
| 2005 | 10 | 7,905,020 | 5 | 1,402,986 |
| Total | 35 | 18,944,702 | 12 | 1,972,986 |

* some proposals are still under consideration

RUPES has established local TECs (Technical Committees) in Indonesia, Philippines and Sri Lanka.  These include a range of local stakeholders, and are set up to initiate and guide RUPES activities in these countries.  The Indonesia TEC held eight meetings in 2004 and 2005, and has now evolved into a new and more independent organisation – COMMITTEES - with a broader membership (including private sector representatives) and a wider mandate, including a policy advocacy and networking for environmental services.  The Philippines TEC has also been active, with four meetings in 2004 and 2005.

C. Status of the recommendations of the last supervision mission

| Recommendations | Actions taken |
| --- | --- |
| Programme administration and budgets |  |
| - Recruit part-time NR senior economist, preferably amongst ISC members | Recruited from IUCN, an ISC member |
| - Engage assistance of social scientist for reviewing site proposals & yearly workplans; follow-up possibility of CIFOR undertaking such task | Done by national TECs |
| - Recruit on 6-week retainer basis an expert to site groups in developing mechanisms for sharing ES payments at site level | Not done |
| - Hire IP/NGO expert, on retainer basis, for Indonesia and Philippines | Victora Espaldon was hired for the Philippines |
| - Reduce international staff travel to bare minimum necessary, to effect programme savings | Done |
| - Bio-physical research and economic valuation studies for all sites should be undertaken only at programme level | Programme level report at draft stage |
| - Keep expenditures for bio-physical research and economic valuation studies below 8% of total budget | Expenditures will amount to 14% of 2005 budget |
| Site planning and activities |  |
| - Revise budgets and workplans of all sites in consultation with co-proponents to ensure that local capacity building of grassroots institutions are immediately undertaken & budgeted starting in the first year | Included in site budgets, but actual workplan depends on local facilitators |
| - Ensure that needs assessment and poverty mapping are undertaken simultaneously at site level - Conduct participatory needs assessment by gender and socio-economic groups at all sites; | Not yet done, but methodology established. Will conduct ToT in December 2005. |
| - Establish Technical Working Groups at site level | Done except for Kalahan (Philippines) where project implementers saw no need for this. |
| New sites/ site proposals/ associate sites |  |
| - To assist new site proposals, set aside and make available some funds to provide support for proposal preparation; select persons with necessary skills to undertake this task | No more new sites are now being selected |
| - Define RUPES’s working arrangements with designated “associate sites”; draw up flexible but defined partnership agreements through discussions in the ISC | ISC and TECs have identified associate sites and agreed working relations. |
| National Technical Committees (TECs) |  |
| - Encourage TECs to prepare their own annual workplans | COMMITTEES and Philippines TEC do this |
| - Facilitate the establishment of institutional attachments/ part-time secretariats for the TECs (Indonesia & Philippines) | RUPES is supporting Philippines TEC. Indonesia TEC has evolved into COMMITTEES |
| - Conduct discussions with FPE for purposes of inviting FPE to be member of the TEC; explore possible FPE support for the Philippine TEC secretariat | FPE joined TEC in September 2005 |
| - Invite WALHI to the Indonesian TEC | Did not join, but membership of COMMITTEES has been broadened. |
| - Follow-up on partners’ expressed interest in southern China (Yunan), Sri Lanka and Lao PDR to form Technical Committees in their respective countries | TECs established in China and Sri Lanka. Contact established in Laos via IUCN and DED but local capacity is very limited |
| International Steering Committee (ISC) |  |
| - Invite a representative of Forest Trends to the ISC | Forest Trends has observer status on ISC |
| - Strengthen this international partnership through maximized use of resource persons from partner organizations to undertake, at cost, technical work required by RUPES | IUCN economist hired for ES valuation study |
| - Follow-up on the earlier recommendation of the 2003 ISC meeting to jointly organize a regional seminar on transfer mechanisms with outside funding, as well as side events in related, upcoming international gatherings | Event planned for nearer to end of project in 2006 |
| - Establish contacts and links with private sector players interested in pursuing work related to ES/ ES markets | Associations of forest industries and mineral water bottlers are members of COMMITTEES, which also has links with banking organisations |
| RUPES logframe |  |
| - Revise RUPES programme logframe with a view of merging overlapping sets of tasks and activities | Done during this SM |
| - Review, at ISC level, the continuing validity & relevance of undertaking preparatory work for establishing a Regional Facility (under Goal 6) | ISC agreed to drop this |

D. Project cost and funding

Expenditure of IFAD RUPES funds is shown in Table 2.  Total expenditure in 2005 up to the end of October was US$135,510, compared with the budget for the whole year of US$384,141.  This leaves US$171,506 available for the rest of the project period, including any extension into 2007.

Table 2: IFAD project cost and allocation

US$

| Cost category | Project | Actual | Actual | Actual | Budget | Actual | Balance | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | allocation | 2002 | 2003 | 2004 | 2005 | 2005 | 2006-7 | 2002-2007 |
|  | 2002-2007 | Jan-Dec | Jan-Dec | Jan-Dec | Jan-Dec | Jan-Oct | Jan-Dec |  |
| Staff (Institutional Specialist and Project Leader) | 400000 | 57210 | 152091 | 97309 | 43979 | 22783 | 36743 | 387332 |
| Operational Costs | 420000 | 38321 | 75965 | 80039 | 75350 | 25406 | 36743 | 306418 |
| Consultations and Workshops | 80000 | 40793 | 7078 | 77953 | 72212 | 41790 | 28578 | 226614 |
| Action research / TA support | 500000 | 3429 | 73026 | 141139 | 192600 | 42531 | 69442 | 479636 |
|  | 1400000 | 139753 | 308160 | 396440 | 384141 | 132510 | 171506 | 1400000 |
| Staff and operational costs | 59% | 68% | 74% | 45% | 31% | 36% | 43% | 50% |

The last supervision mission thought that too great a proportion of funds were being spent on management and overhead costs, at the expense of field-based action research.  These overhead costs (staff and operational costs) accounted for 68% of total expenditure in 2002 and 74% in 2003 – compared with 59% in the original IFAD grant allocation table.  In line with the supervision mission’s recommendation these costs were reduced to 45% of expenditure in 2004 and 31% in the 2005 budget.   Current projections show these overhead costs amounting to 50% of total expenditure over the entire project period.  In fact, as spending on sub-projects financed by other donors will have mostly been for field activities, workshops and TA studies, project overhead costs, will have been more like one quarter of total costs when funding from other donors is taken into account.

Expenditure on the six pilot action-research sites is shown in Table 3.

Table 3: IFAD expenditure at pilot sites

US$

| Site | Actual | Actual | Budget | Budget | Total |
| --- | --- | --- | --- | --- | --- |
|  | 2003 | 2004 | 2005 | 2006-7 | 2002-2007 |
| Bungo |  | 6436 | 45733 | 22831 | 75000 |
| Bakun |  | 22740 | 13644 | 9097 | 45481 |
| Sumberajaya |  | 23060 | 30000 | 41940 | 95000 |
| Singkarkak |  | 21250 | 23750 |  | 45000 |
| Kalahan | 14948 | 21411 | 29823 |  | 66182 |
| Kulekhani | 18401 | 20682 | 52217 |  | 91300 |
| Total | 33349 | 115579 | 195167 | 73868 | 417963 |

The project grant agreement between IFAD and ICRAF states that ICRAF would mobilise an additional US$3.53 million  in funding alongside the US$1.4 million grant from IFAD.  These additional funds would come from ICRAF itself and from other donors.   The actual amount of additional funding mobilised will amount to about US$2.83 million (including an estimated US$1.01 million to be contributed by donors in 2006 – see Table 4).   This excludes the cost of ICRAF headquarters staff, staff time for partners on ISC and TEC meetings, and other in-find contributions.

Much of this money is for specific sub-projects, and most of the US$1.9 million shown in Table 1 above is included in the Table 4 amounts (funding for some sub-projects is likely to continue into 2007, and this may not be in Table 4).   In addition to these sub-projects, donors have also provided staff and other inputs for RUPES  - the value of which are included in Table 4.  The Grant Agreement envisages that this additional funding would be incorporated into AWPBs in order to ensure overall coherence of the programme.  This has not happened, possibly partly because sub-projects tend to have their own specific objectives and timeframe.

Table 4: RUPES Funding from Other Donors

US$

| Donor | 2002 | 2003 | 2004 | 2005 | 2006 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| ACAR | 80,961 | 283,971 | 166,124 | 119,462 | 138,122 | 788,640 |
| CIF | - | - | - | - | 107,656 | 107,656 |
| DFID | - | 30,000 | 23,250 | - | 198,154 | 251,404 |
| EEPSEA | - | - | - | - | 34,578 | 34,578 |
| EURU | 111,680 | 143,795 | 106,500 | 59,669 | - | 421,644 |
| FAO | - | - | 15,000 | - | - | 15,000 |
| FORD | 67,430 | 975 | - | - | 116,357 | 184,762 |
| GPW | 2,966 | - | - | - | - | 2,966 |
| IBRD |  | 65,892 | - | - | - | 65,892 |
| ICRAF CORE | - | 53,522 | 7,496 | - | - | 61,018 |
| IDRC | - | - | - | - | 348,944 | 348,944 |
| IFPR | 39,000 | - | 51,000 | 95,184 | 63,119 | 248,303 |
| IIED | - | - | 7,371 | 5,518 | - | 12,889 |
| IIEF | - | - | 15,000 | 15,800 | - | 30,800 |
| IRD | - | 3,821 | - | - | - | 3,821 |
| SIDA | - | 10,000 | - | - | - | 10,000 |
| SII |  | 50,946 | 5,466 | 12,809 | - | 69,222 |
| USAID | 76,336 | - | 94,207 | - | - | 170,543 |
| Total | 378,373 | 642,922 | 491,415 | 308,443 | 1,006,929 | 2,828,082 |

In addition another $49,000 will have been contributed by national partners (Table 5) at four of the six pilot sites.   There have also been significant national contributions at other pilot sites, including the six associate sites.

Table 5: RUPES Funding from National Partners Through Site Level Activities

US$

| RUPES site | 2002 | 2003 | 2004 | 2005 | 2006 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Kalahan | - | - | 7,070 | 7,070 | 2,842 | 16,982 |
| Kulekhani | - | 4,730 | 9,050 | 4,200 | 1,100 | 19,080 |
| Bakun | - | - | 1,543 | - | - | 1,543 |
| Singkarak | - | - | - | 3,000 | 9,000 | 12,000 |
| Total | - | 4,730 | 17,662 | 14,270 | 12,942 | 49,604 |

Although rather less additional funding has been mobilised than was envisaged when RUPES was planned, RUPES management is to be commended for mobilising from other donors over twice the amount IFAD has contributed.   Not only has this increased the scope and scale of project activities, but has created useful learning partnerships to spread RUPES findings to a considerable number of other major donors and international agencies.   This has significantly increased the impact of RUPES at the strategic level.

E. Project Management

RUPES has had a total of three project coordinators.  Marian Delos Angeles was replaced by Fiona Chandler in September 2003, who held the post up to December 2004.   The project is now being coodinated by Dr Meine van Noordwijk, who is also ICRAF’s Regional Coordinator based in Bogor.   Much of the day-to-day management has been delegated to Ms Beria Lemona, and ICRAF Research Officer.  The arrangement appears to be working well, and enables RUPES to maintain its high visibility within ICRAF while reducing project overhead costs (as recommended by the last supervision mission).

SECTION 3

Mission recommendations

1. Revision of logical framework

The current logframe being used by RUPES was developed at the project start-up workshop.   It varies slightly at purpose level from the logframe shown in the last IFAD supervision mission  report (March 2004).   The current RUPES logframe lacks a goal-level objective statement, and the goal in the last IFAD supervision mission report is largely repeated in the purpose level statement (see Table 6).   In addition, all of these goal and purpose level statements expect the project to generate poverty reduction and environmental rewards per se.  An action-research project, with only pilot-level field activities cannot be expected to have a significant direct impact on poverty, but rather should aim to develop new systems or mechanisms for poverty reduction and environmental rewards.   Some re-wording of the goal and purpose level statements has therefore been proposed, which should be reviewed by IFAD, RUPES and its ISC.

Table 6: Logframe statements at goal and purpose levels

| 2004 sUPERVISION Mission | RUPES Documents | proposed new logframe |
| --- | --- | --- |
| GOAL |  |  |
| Enhanced livelihood and resource security of poor upland communities in Asia through improving rewards for the environmental services they provide to global and national society | Ensure enhanced food security, income and welfare, improved nutritional status and greater access and control over the use of resources for poor upland communities in Asia (GRANT AGREEMENT) | Develop new mechanisms for enhanced livelihood and resource security of poor upland communities in Asia |
| Purpose |  |  |
| Ensure that the poor are recognised and rewarded commensurate to the environmental services they provide | Ensure that the poor are recognised and rewarded commensurate to the environmental services they provide for the global and national communities | Create the basis for systems to reward the poor for the environmental services they provide for the global and national communities |

These are:

Goal: Develop new mechanisms for enhanced livelihood and resource security of poor upland communities in Asia.

Purpose: Create the basis for systems to reward the poor for the environmental services they provide for the global and national communities

Some simplification of goal level indicators are suggested.

In consultation with the project management, and following the recommendations of the last supervision mission, some adjustments have been made at the output/activity level.  In particular to merge some activities and so simplify reporting.  Reports are written following the logframe layout, and the large number of activities listed in the logframe has meant that which has meant that reports has been rather repetitious.   In addition pilot site activities have been deleted from output 3 (A transparent enabling institutional environment at local, subnational, and national levels) and moved to output 2 (An array of mechanisms is developed and tested with communities in at least 6 sites), so all information on pilot sites can be in a single section of the report.  Reference to local level partnerships has been deleted from output 5 (partnerships) as this is part of pilot site activities (output 2).  These changes  should make reporting easier and less repetitive.   A full revised logframe is in Appendix 5.

Action: RUPES and ISC

2. Payments for Environmental Services

Payments for environmental services (ES) are part of the rewards that upland communities may get in return for providing ES.  At the moment payment for environmental services are limited to watershed functions, mostly paid by hydro-power, industrial water users and water utilities.  In some sites (e.g. Cidanau) payments are related to environmental benchmarks (such as the number of trees), but in others (e.g. Singkarak Lake) they take the form of a more general payment to the community to conserve the watershed, and may be alongside payments for social development activities.  At other sites (eg Sumbarjaya), no environmental payments are made in financial terms, but long standing conflicts over land tenure are resolved and tenurial security is provided on the basis of a commitment to maintain or restore ES..

It is suggested that RUPES hold discussions with buyers or potential buyers of the environmental services that are already being delivered, with a view to establishing a system for payments of other rewards related to specific environmental indicators.   There is evidence on increased willingness to pay by hydro-electricity producers provided that more clarity can be provided in what services these payments can actually deliver.

Action: RUPES

3. Evaluation of actual and potential impact on poverty

The overall goal of RUPES is to develop approaches for the use of rewards for environmental services (RES) to reduce the poverty of upland communities.  Before the project is completed, RUPES should carry out and evaluation of the extent to which this has taken place at pilot sites, or which potentially could take place.    Improved and more sustainable land-use practices could result in the following tangible rewards:

- Local environmental services that are directly utilised within the community – such as reduced soil erosion increasing fertility and crop yields, cleaner water, improved supply of forest products.

- Enhanced security and trust within the governance system leading to rights of access to land and natural resources and better local services

- Payments (mostly for labour) invested in ES such as tree planting in watersheds.

- Investment funds for profitable livelihood activities – which may be an alternative to payments for labour.

- Income from sales of “commoditised” ES – such as premiums for eco-label products or payments for carbon-sequestration

In case study locations (which may include some or all pilot and learning sites, and possibly other locations with different agro-ecological conditions), the study should quantify current income levels – including where appropriate incomes of different occupation/wealth classes (such as owner-tappers and share-tappers of jungle rubber) and then calculate how much additional income and other benefits (such as reduced time for household tasks) may be derived from ES rewards for these households.  This would show the extent to which RES can reduce poverty, and would also provide information on goal level logframe indicators.

Much of the information for this study may already be available.  Crop budgets for “before” and “after” (or “with” and “without”) situations have been calculated for major crops in some watersheds.  The participatory poverty surveys which are proposed should also aim to gather data on current sources of household income and how this income may have changed (or may change in future) with the provision of ES.

Action: RUPES

4. Exit strategy

With the time extension currently being processed by IFAD, the project will end in June 2007.   This leaves just over 18 months to complete work at pilot and learning sites, and to strengthen national level technical committees and other institutions.

At Sumberjaya it was apparent that the process of forming farmer groups and applying for leases on forest land has developed its own momentum that will continue after the end of the project.  Local NGOs and the Forestry Department have been trained and supported by the project, but should be able to continue without such support.  Farmers are taking the initiative to form groups.   RUPES needs to think about how it can wind up its activities at other sites, while as far as possible enabling local people and organisations to continue with tasks that will be required after the end of the project.  In general it seems that the adoption of a partnership approach at all sites has meant that there is a built-in exit strategy as these partners can continue to provide support after the end of the project.

The same applies to TECs and other institutions that have been established by RUPES as means of promoting rewards for environmental services, and supporting systems for payments of these rewards.  In Indonesia the TEC as evolved into COMMITTEEs, which is fully independent of RUPES.  The status and future functions of TECs in other countries should be reviewed.  If appropriate, they may be linked to other organisations for any continuing support that they require.

It is suggested that, as part of the 2005 annual report, brief information is included on the exit strategies for each site and each TEC (in a list or table format).

Action: RUPES

5. Reporting

The project reports annually (as per loan agreement) on its progress and achievements.  To make reports clearer to readers is would be useful if sub-sections on the five project outputs (which also have information on the related activities) could be headlined with one or two words that identify the contents of the sub-section.  For instance output 1 could be “studies and research”, output 2 “testing and pilots”, output 3 “policy and institutional environment”, output 4 “communications” and output 5 “partnerships”.

It would be useful of reports could include tables summarising information on the six RUPES pilot sites, with another on the associated learning sites.    The tables could have a column for each site and include rows for the following information:

- Site location (name, province, country)

- Area (ha), and population

- Lead institution

- Other collaborators

- Environmental services identified

- Reward and payment systems (identified, in place)

- Value of payments (and other benefits) actually being made

- Community mobilisation and institution building achievements

- Surveys completed (list)

- Training and workshops completed (list, no. of events)

- Other activities (list)

- Other remarks and comments

It would also be useful to list the status of RUPES policy and institution-building activities in each of the countries where it has worked, together with policy dialogue and advocacy activities (which may be at the multi-lateral as well as national levels).

Apart from listing publications produced by the project, summaries or abstracts could be included as an annex to the report.

Action: RUPES

6. Project completion report

RUPES should write a final project completion report.  The Grant Agreement with IFAD states that this report should include the following: (i) costs and benefits of the programme: (ii) the achievement of its objectives; (iii) the performance of the recipient, the programme partners and IFAD of their respective obligations under the Grant Agreement; (iv) lessons learned from the foregoing; and (v) and other issues that IFAD shall reasonably request.   This report should be completed prior to the draft closing date (six months after project completion).

Guidelines for Project Completion Reviews for IFAD loan projects provide more details on the information that can usefully be included in a completion report.  A copy of the guidelines will be sent to RUPES and could be followed where relevant for a grant project.

The key questions that IFAD need answered are where and how rewards for environmental services can be made into an effective approach in improving the livelihoods of the upland poor.  If so, what form should these rewards take, and how should they be delivered.

Action: RUPES

7.  Project period extension

IFAD needs to complete its processing of a contract amendment for the extension of the project implementation period to 30 June 2007.

Action: IFAD

8.  Linkage with other IFAD projects

An important part of the rationale for all IFAD grant funded projects is to learn lessons to be transferred to projects funded by IFAD loans.  On the advice of earlier IFAD supervision missions, RUPES invited IFAD-funded projects in the region to apply to become RUPES pilot sites.  Only one IFAD project has done this – CHARM in the Philippines.  This is disappointing, although it is understandable that these other projects will have different timeframes and may lack sufficient flexibility in their activities.  Future grant projects could include activities (workshops, publications) specifically designed to inform other IFAD programmes of their results and to invite collaboration.  In addition teams designing new loan funded projects also need to be made aware of IFAD grant programmes and their outcomes.

Action: IFAD

Appendix 1

Mission programme and list of persons met

November 28, 2005

Arrive in Jakarta

10.00 – 14.00 – briefing on RUPES

- Ms. Beria Leimona – RUPES Program Manager

- Mr. Suyanto – RUPES Sumberjaya Site Leader

- Ms. Grace Villamor – RUPES Philippines

Travel to Sumberjaya via Lampung

November 29, 2005

Field visit to Sumberjaya (with Mr Suyanto and Ms Villamor)

08.00 – 11.00

- Mr. Bruno Verbist, Ph. D Student at Department of Land Management, Faculty of Applied Bioscience and Engineering, Katholieke Universiteit Leuven. Title of his project is “Development of a negotiation support model for watershed management in an agroforestry landscape mosaic in Sumberjaya, Indonesia”

- Mr. Rudi, ICRAF staff working on participatory landscape assessment

- Ms. Indriani, ICRAF field staff

- Mr. Santo, ICRAF field staff

11.00 – 12.30

- Mr. Yoga – Head of local NGO

- Mr. Fuad – Local NGO

- Mr. Rasna – Forestry Extension Officer

- Mr. Cucu – Forestry Extension Officer

- Mr. Pratik – ICRAF Lampung Office Manager

- Mr. Warsijan – Head of sub-group of Tribudi Syukur, already possessing HkM Permit

12.30 – 14.00

- Mr. Ashim – head of Gunung Raya farmer group, facilitated by RUPES

- Mr. Warga, Secretary of Gunung Raya Farmer Group

- Mr. Sanan, Farmer

Return to Lampung

30 November

Travel to Jakarta

Meetings in Forestry Department with COMMITTEES and IIED

15.00 – 17.00

- Mr. Bustanul Arifin – Researcher at Lampung University (COMMITTEES Member)

- Mr. Tri agung – WWF Indonesia (COMMITTEES Member)

- Mr. Nanang Roffandi – Association of Forest Business People (COMMITTEES Member)

- Mr. Effendi Pasandaran – Senior researcher at the Department of Agriculture (COMMITTEES Member)

- Mr. Sandy – Field Officer at REBHUMI (Local NGO working in Cidanau)

- Mr. NP Rahadian – Director of  REBHUMI (Local NGO working in Cidanau)

- Mr. Rajab Tampubolon – Department of Forestry

- Mrs. Ernawati - Department of Forestry (COMMITTEES Member)

- Dr. Sonja Vermeulen – IIED

- Dr. Upik Rosalina Wasrin (PERHUTANI – ministry of Forestry) – COMMITTEES Member

- Dr. Santo Mahanti (Program Officer RECOFTC)

Travel to Bogor

1 December 2005:

Meetings in RUPES headquarters

1. 	Ms. Beria Leimona – RUPES Program Manager

2.	Mr. Chip Fay – Policy Analyst – ICRAF SEA

3. 	Mr. Jim Roshetko – Winrock International - ICRAF

Prepare draft mission recommendations

2 December 2005

RUPES Seminar

- Beria Lemona (ICRAF) – RUPES Program

- Aunul Fauzi (ICRAF) – RUPES Program Assistant

- Meine van Noordwijk (ICRAF) – Regional Coordinator

- Alimin Djisbar (RUPES Singkarak) – RUPES Singkarak Site Leader

- Kevin Jeanes  – Australian PhD Student  studying Singkarak

- Grace Villamor (ICRAF Philippines) – RUPES Philippines

- Susilo Ady Kuncoro (UCRAF) – RUPES Bungo Jambi

- Buyse, Nicolas   (ICRAF) – PhD Student from French

- Kurnianto, Sofyan   (CIFOR)

- Ilstedt, Ulrik   (CIFOR)

- Ekadinata, Andree   (ICRAF) – GIS Staff

- Komarudin, Heru   (CIFOR)

- Ford, Alison   (CIFOR)

- Chokkalingam, Unna   (CIFOR)

- Yoo, Byoung Il   (CIFOR)

- Agra, Flordeliz   (CIFOR)

- Lusiana, Betha   (ICRAF)

- Suyanto – ICRAF Sumberjaya program leader

- Desi A Suyamto (ICRAF) - Modeller

Meeting

- Beria Lemona (ICRAF) – RUPES Program

- Meine van Noordwijk (ICRAF) – Regional Coordinator

3 December 2005

Wrap-up meeting

- Beria Lemona (ICRAF) – RUPES Program

- Meine van Noordwijk (ICRAF) – Regional Coordinator

Appendix 2

Research Publications

The project has produced the following research papers on rewards for environmental services.

A. RUPES working papers

- Conceptual Framework for Economic Valuation of Environmental Services in Southeast Asia for the RUPES Program; Mikkel Kallesoe & Usman Iftikhar, 2005 (final draft version).

The paper develops a conceptual framework for policy relevant economic and environmental valuation of environmental services particularly suited to field sites in Southeast Asia. The framework is moulded around the four stages of scoping, brokering, negotiating and implementation and monitoring.

- Looking Through the Eyes of the Future: Rewarding Upland Poor for Environmental Services in the Philippines; Victoria O. Espaldon 2005 (final draft version).

A study was conducted to assess the social mobilization initiatives  and capacity to implement Rewarding Upland Poor for Environmental Services (RUPES) in two sites in the Philippines:  Bakun, Benguet;  and Imugan, Sta. Fe, Nueva Vizcaya.  This report presents the assessment of social mobilization activities and the capacity of the RUPES team to implement the project in Imugan and Bakun.  It also presents a list of recommendations related to capacity building and social mobilization strategies to accomplish the objectives set forth in the proposal as it was approved by ICRAF Bogor in 2003 and 2004.

- RUPES typology of environmental service worthy of reward; M. van Noordwijk, 2005

The development of transparent and sustainable reward mechanisms for environmental services provided by upland farmers to downstream communities requires clarity on the relationship between land use and the type of environmental services provided. In the context of the RUPES project ('rewarding upland poor for the environmental services they provide'), a typology of environmental services is discussed that leads to the distinction of twelve 'proto-types' of situations where the upland-lowland relationship is focused on a specific environmental service function.

- Agro-ecosystems, their population densities and land cover in Indonesia in the context of upland-lowland relationships; Hadi, D.P. and Van Noordwijk, M., 2005.

Appendices to the report provide statistics at district level.

- Hydrological Impacts of Forest, Agroforestry and Upland Cropping as a Basis for Rewarding Environmental Service Providers in Indonesia, Fahmudin Agus, Farida, and Meine van Noordwijk (Editors) Workshop Proceeding, 2005

With a high population pressure, there is pressure to intensify agricultural systems and for extending agriculture even to unsuitable steep slopes and marginal lands. At the same time, land is also needed for settlement, industrial and infrastructural developments. As land from forest is converted to agriculture and agricultural lands are converted to other non agricultural uses, many environmental services tend to disappear and thus the services will become more precious necessities.

Different agricultural systems provide also different environmental services. Smallholder plantations, characterized by complex agroforestry systems, sustain various positive functions including erosion control, flood mitigation, carbon sequestration, and biodiversity.  Monoculture tree-based systems have less biodiversity, but can still contribute to carbon sequestration, mitigate floods and control erosion.  Intensive paddy farming system has been able to control erosion to a level as low as that of forest. Monoculture annual crop-based farming systems have a low erosion control, low biodiversity and carbon stock but techniques to develop the systems into a more environmentally-benign practices are available, although are not necessarily affordable to farmers.

Since the demand for agricultural products and environmental services are increasing, and both are not mutually exclusive, rewarding farmers as environmental service providers is justifiable.  The beneficiaries of the services and government should participate in this endeavour.  Government support could be realized through realigning of current budgets for land rehabilitation and conservation to a more problem solving and people oriented approach so it can contribute in increasing environmental services while providing a better livelihood for farming communities.

- Institutional Constraints and Opportunities in Developing Environmental Service Markets: Lessons from Institutional Studies on RUPES in Indonesia, Bustanul Arifin, 2005

This report presents the major elements of institutional studies regarding the constraints and opportunities for developing environmental service markets in Indonesia. The institutional economic analysis within this report focuses on institutional mechanisms, institutional environments and directions for policy reforms, particularly regarding the requirement for and conditions of such reforms. These reforms would facilitate and enable environmental transfer agreements in Indonesia and possibly other parts of the world with the potential to develop

environmental service markets. Three RUPES sites — watershed services in Sumber Jaya of Lampung, biodiversity services in Bungo of Jambi, and carbon sequestration services in Singkarak of West Sumatra — have provided comprehensive case studies of the institutional constraints on and opportunities for future compensation and reward transfers to poor people who are providing the services.

- Review of the Development of Environmental Services Market in Indonesia, S. Suyanto, Beria Leimona, Rizki Pandu Permana and F.J.C. Chandler, 2005.

The objective of this study was to assess the development of the market for environmental services in Indonesia through a review of literature on related projects and research.  The focus of the assessment was on the identity of the buyers and sellers of environmental services, the payment/rewards, mechanisms, intermediaries, transaction costs, and other actors.  An assessment was included on the stage of development of the environmental service markets. By documenting the development of the market in environmental services, it is expected that concerned stakeholders will better understand the stages of development of the markets of environmental services in Indonesia, and to identify possible gaps in knowledge in recognizing the potential markets for environmental services and developing appropriate transfer mechanisms.  The review reveals that the development of environmental services in Indonesia is still at an early stage. However, there are many initiatives, emerging projects and research related to the development of markets for environmental services. Meanwhile, each environmental service market (watershed protection, carbon sequestration, biodiversity conservation and landscape beauty) shows different levels of market development. In terms of all four markets in Indonesia, the market for landscape beauty is relatively more progressive.

- An Introduction to the Conceptual Basis of RUPES, Meine van Noordwijk, F.J.C. Chandler, Thomas P. Tomich, December 2004

Payments for environmental services are normally discussed in terms of ‘buyers’ and ‘sellers’ – as if there are only two sides of a coin. However ‘brokers’ (those that act as a third party between the buyers and the sellers) are the third side of this coin. However, the chance that a coin will land on this side and reach a stable equilibrium is small – it normally falls to either of the two other sides.  The paper presents twenty ‘aspects’ of Rewarding the Upland Poor in Asia for Environmental Services They Provide (RUPES), suggesting that rewarding upland poor for environmental services ES is a well-polished diamond, rather than a coin. All these aspects can co-exist and all reveal insights into what is at the core, yet none of them are the full and only truth. Overall it is hoped that this collection of aspects can stimulate the wider intellectual debate and practical exploration and testing that we need to achieve the double goals of poverty alleviation and environmental protection that the world community has set itself as Millennium Development Goals.

- Review of Developments of Environmental Services Markets in Sri Lanka, Mikkel Kallesoe & Diana De Alvis, December 2004.

Sri Lanka holds great potential for developing PES and environmental service markets.  However this is a relative new concept and improving awareness and building institutional capacity remains a top priority. Therefore, site specific assessments in support of PES should be developed with the purpose of: identifying, assessing and prioritizing ecosystem services; and supporting the development of equitable institutional arrangements that ensure access to benefits by potential buyers. The entire agenda of rewards for environmental services has to be adopted at the practical, problem-solving level so that it can be pushed beyond the rhetorical plane to which it has been relegated because of competing policies and environment-related programs, the opportune investment climate for privatization of common resources in the light of global imperatives, and civil society demands. The identified policy gaps (at the implementation level) and institutional constraints, as the study shows, can be addressed by an agenda that promotes (a) policy enhancement and re-appreciation to recognize the requisites of commons management and benefit sharing, not an all-out reformulation process; (b) capacity and capability building in ES negotiation, valuation, and protection; and (c) research and advocacy on ES management and benefit sharing.

- Rewards for Environmental Services in the Philippine Uplands: Constraints and Opportunities for Institutional Reform, Rowena R. Boquiren,  December 2004.

This study examined the policy context and institutional arrangements guiding the payment of rewards and incentives for environmental services (ES) in the Philippines.   The review covered three general laws that provide the overall policy framework on natural resources use, access and control, 13 that define institutional arrangements within the environment sector, and a minimum of 15 specific issuances, either officially adopted or still in draft form, which deal with on-the-ground implementation or enforcement.   The study identified a healthy community of stakeholders in environmental services.   Institutional players in ES include the Philippine State as primary stakeholder, local  economic interest groups, external economic interest groups, internal state mediators,  external state mediators, civil society mediators, and the donor community.   The identified policy gaps (at the implementation level) and institutional constraints, as the study shows, can be addressed by an agenda that promotes (a) policy enhancement and re-appreciation to recognize the requisites of commons management and benefit sharing, not an all-out reformulation process; (b) capacity and capability building in ES negotiation, valuation, and protection; and (c) research and advocacy on ES management and benefit sharing.

- Case Study of the Maasin Watershed: Analyzing the Role of Institutions in a Watershed-Use Conflict, Jessica C. Salas, December 2004.

This case study analyzes the socio-institutional relationship of watershed protection over the past decade in the Maasin watershed in the Philippines.  In this study, the methodology of data gathering basically made use of a historical transect tool of Participatory Rapid Appraisal (PRA). Interviews, focus group discussion, workshops, photo documentations were conducted.  The analysis followed the framework of institutional channels described in the classification from Norman Uphoff, namely; (a) local administration (b) local government (c)  membership organization (d) cooperatives (e) service organizations in private philanthropy (f) service organizations in marketization, and (g) private business. Culture and practices could be institutions in themselves.

- Rapid Agrobiodiversity Assessment (RABA): A Tool to Capture the Understanding and Knowledge of Stakeholders on the Benefits of Agrobiodiversity,  Susilo Ady Kuncoro, Meine van Noordwijk, and Fiona Chandler,  September 2004.

Rapid Agrobiodiversity Assessment tries to link sellers with potential buyers of biodiversity conservation services to engage in an agreement for environmental services payment. It is a tool that provides guidance on what kind of general information that needs to be explored prior to engagement.  The scope of RABA comprises of delineating the interest groups and their domains and identifying potential partners. These are done by capturing the perspectives of each interest group, including intermediary, on what they perceive as substantial and relevant and what are not in regard to providing biodiversity conservation service

- Rewarding Upland Farmers for Environmental Services: Experience, Constraints, and Potential in Vietnam Bui Dung The, Dang Thanh Ha, and Nguyen Quoc Chinch, May 2004.

This report presents the findings of a study to explore constraints and potential to addressing important aspects of poverty in Vietnam Uplands through rewarding the upland poor for environmental services they  provide. The study was done by a team of three Vietnamese researchers, under the coordination and supervision of the International Center for Research in Agroforestry in South East Asia (ICRAF SEA).   The study was done to provide information for use by the Program Rewarding the Upland Poor in Asia for Environmental Services They Provide (RUPES) and Swedish International Development Cooperation Agency (Sida) in planning future activities.  This study was explicitly conceived as an analytical study, to attain better understanding of RUPES-related experiences, constraints and opportunities to the application of RUPES concept in Vietnam. This study is neither a project evaluation nor an operational planning.  However, it provides a background for the development of future RUPES activities in Vietnam.

- Developing Pro-Poor Markets for Environmental Services in the Philippines, Rina Maria P. Rosales,  2003.

Originally commissioned and published by IIED, this study was a a preliminary assessment of the development of markets for environmental services in the Philippines with a focus on the distribution of costs and benefits among different stakeholder groups, in light of widespread public concern about the impacts of market based instruments on the poor.   There are three objectives of the study (1) to document all efforts undertaken in developing markets for environmental services in the Philippines, (2) to conduct a rapid assessment of institutional mechanisms that have evolved in the development of markets for environmental services, (3) to develop and test a robust framework for monitoring and evaluating the efficacy of markets for environmental services in environmental, economic and social aspects

- Environmental Service “Payments”: Experiences, Constraints and Potentials in the Philippines H. Arocena-Francisco, 2003.

This paper reviews the form of incentives or rewards that have been provided to upland communities in a number of sites under different management leadership in the Philippines. It also discusses what the upland farmers have to do in return for these rewards. The goal of such a review is to evaluate what elements are present in these communities that will support an environmental reward system and in the process, assess the potential of the case study sites for inclusion in RUPES.

- Eco-Certification as an Incentive to Conserve Biodiversity in Rubber Smallholder Agroforestry Systems: A Preliminary Study, Anne Gouyon, 2003.

Rubber agroforests offer many economic advantages to smallholders, such as low development costs and minimal risks.  However, they offer a smaller return on land and labour than alternative land uses, such as the monoculture of high-yielding hevea clones, oil palm, and, in areas close to urban markets, intensive food crop production. In the absence of specific incentives, there are no reasons why smallholders should forego the benefits of more profitable land uses for the sake of biodiversity conservation. This means that the conservation community must be ready to reward the services rendered by smallholders willing to conserve their agroforests instead of converting them to higher-productivity land uses. One way of internalising the cost of the conservation services is through eco-labelling of the products coming from the agroforests. Selling eco-labelled products at a higher than average price would increase the economic returns from the agroforests. This report examines prospects for selling eco-certified products from agroforests and the potential benefits and constraints of eco-certification.

- Rewarding the Upland Poor for Environmental Services: A Review of Initiatives from Developed Countries, Anne Gouyon,2003.

Developed countries have already established a number of mechanisms to implement environmental transfers either within their own country, or towards other countries, including developing nations. The present review looks at a number such of mechanisms with a common matrix of analysis and tries to draw lessons for the design of RUPES mechanisms in Asia. All these mechanisms have been designed to provide reward to farmers for environmental services, and we put the priority on the ones which were clearly targeting upland farmers. Not all these schemes had poverty alleviation as their objective, but many did have a clear social orientation, and in all cases we tried to look at whether these schemes could be targeted to reach poor upland communities.

- Development Assistance to Upland Communities in the Philippines, Catalina Jensen,  2003.

Over the last two decades, there has been a growing concern about the alarming rate of Philippines forest degradation and upland poverty. The government have initiated and implemented programs, and policy reforms adopted to address the problem. The country has also been recipient to substantial development assistance of loans and grants from international funding agencies in support of sustainable forest management and poverty reduction. Although there were some successes, upland development assistance has been short of its targets in addressing poverty reduction and natural resource degradation attributable to the following: 1. Sustainable forest management is a long and costly process.  2. Community based forest management democratizes resource use rights, but politics still has the "distributive power".   3. Ineffective policy implementation contributes to deforestation. Ineffective policy implementation have been attributed to lack of understanding, inconsistent interpretations, constant policy changes due to change in administration, "patronage politics" and lack of political will.  4. Ecological values of the forest are implicit in the programs.  5. Good environmental governance is key to effective forest management as it promotes transparency and accountability, hence, could effectively address the systemic graft and corruption prevailing in the forest sector.

- Forest Area Rationalization in Indonesia: A Study on the Forest Resource Condition and Policy Reform, Harry Santoso, 2003.

There are two driving factors which can cause change in Indonesia's forest area: a juridical factor and a dynamic factor.   The susceptibility of Indonesia's forest area to change mentioned above, gives an indication about many constraint to the claim of state control of the forest area in Indonesia. So that the implementation of this study concerning forest area rationalization is quite reasonable. In relation to that, the World Bank (by consultation with several parties including ICRAF) has initiated a preliminary study about forest area rationalization in Indonesia. The result of this study will be used as country strategy for the World Bank to give input for the policy of Indonesian Government in arrangement and management of forest area.  In the framework of giving contribution of idea concerning the topic of the study, the author prepares this paper as one of contributors from several members of the study team, each with different focus of study.   Partly based on the knowledge and experience of the author, the material and opinions presented in this paper are also supported by the results of field visits (in Lampung province),  intensive discussion with several related parties such as experts, government officials, NGO, international institution, as well as the result of discussion in multi-stakeholder workshop.

- Assessing the Livelihood Benefits to Local Communities from the Profafor Carbon Sequestration Project, Ecuador, M. Milne and P. Arroyo, 2003.

This study assesses the actual and potential livelihood impacts of PROFAFOR, a carbon sequestration project in Ecuador. For PROFAFOR, addressing the livelihood needs of contracted communities will help to increase the duration of the carbon sequestered.  A modified sustainable livelihoods approach and financial budget analysis were adopted to examine the local livelihood implications for communities involved in the projects. The 'before project' status of community activities, income sources and capital endowments (financial, environmental, human, social and physical) were evaluated to provide a 'business as usual' scenario. The short-term and long term livelihood impacts of the projects were then assessed, in terms of actual and potential changes in activities, income sources and assets. Long-term financial profitability and expected revenues of community enterprises were calculated, considering best case and worst case scenarios. Primary data were obtained from 7 community workshops and four interviews on-site with individual landholders. The information was verified through interviews with the project teams, non-government organizations, government officials, research institutes and timber buyers.   Financial data were collected from the project managers and independent sources.

B. Other research reports

- An Outline of Requirements for a Spatial Information and Negotiation Support System, Luke Hanson, 2003

The purpose of the consultancy was to investigate the design requirements for a

RUPES spatial information and negotiation support system (SINSS). Such a system would allow standardized and consistent assessment of RUPES action research sites and outcomes, and promote transparent and informed negotiation between stakeholders involved in the development of environmental service rewards schemes (ESRSs). It would also establish an important baseline for spatial targeting, impact monitoring and adaptive management.

- Promoting Smallholder Projects through the Clean Development Mechanism by Afforestation and Reforestation, Mogens Buch-Hansen, 2004

Land Use, Land Use Change and Forestry Projects (LULUCF) were accepted as Clean Development Mechanism (CDM) projects as part of the Marrakech Accord in 2000 while rules and regulations were agreed for Afforestation and Reforestation (A/R) projects during the CoP 9 meeting in Milan in 2003. In order to allow smallholders who practice agroforestry to benefit from CDM payments, it is vital to establish institutional linkages between smallholder farming communities at the grassroots level, the designated national authority (DNA), other local and

national institutions, and the international carbon market. After presenting an overview of the CDM process concerning A/R projects and smallholders, this paper discusses the requirements for effective institutional mechanisms between the grassroots level and the national level. Fieldwork to study existing institutions was conducted in Claveria, Philippines and in Nyando, Western Kenya.  In Kenya the fieldwork included the start-up of a participatory research project aimed at determining what type of local-level institutions in Nyando could eventually empower the local population to participate in carbon trade at the national and global level. The paper concludes by discussing the need to further strengthen institutional mechanisms and possible modifications to procedures that will minimize transaction costs, to make it feasible for smallholders to participate in the CDM.

Appendix 3

Summary of RUPES activities at pilot action-research sites

|  | Sumberjaya | Singkarak Lake | Bungo | Kalahan | Bakun | Kulekhani |
| --- | --- | --- | --- | --- | --- | --- |
| Location | Sumberjaya Province, Indonesia | West Sumatra, Indonesia | Jambi Province, Indonesia | Nueva Vizcaya, Philippines | Benguet, Philippines | Makwanpur district, Nepal |
| Lead Institution | ICRAF | Wali Nagari Paninggahan | ICRAF | Kalahan Education Foundation |  | Winrock International |
| Other collaborators | WATALA | Bogor Agric. University and the Main Cooperative for the Improvement of Technology and Welfare of Agroforestry Communities | IRD, WARSI and Gita Buana | Upland Marketing Foundation, Inc. UMFI (NGO) | CHARM (IFAD funded) | Bagmati Integrated Watershed Management Programme (BIWMP) |
| Environmental Service | Watershed (drinking and hydroelectric power) Land tenure for forest land stewardship (HKm) | Watershed (hydroelectric power) | Biodiversity | Watershed (irrigation, domestic water) Carbon Biodiversity (eco-labels) | Watershed (hydroelectric power) | Watershed (hydroelectric power) |
| Activities to date | - Poverty Mapping - Awareness raising (local technical committee, cross visits) - Village policy advocacy workshop & institutional capacity building - Facilitate farmer groups to get land leases through HKm via mapping and proposal preparation - Participatory monitoring of water flow, water quality, sediment - Establish ‘river care’ groups | - A rapid hydrological assessment has been carried out and presented to the community and stakeholders in the project - Formation of a local technical steering committee - Local community have organized themselves into an “Paninggahan Environmental Management Body” - Assessment of land tenure & local ecological knowledge - Assessment of potential buyers and institutional system for ES - Assessment of potential providers of ES - Inventory of land ownership - Water balance modeling | - Quantification / valuation of biodiversity (IRD) - Technical Working Group establishment & meetings - Site characterization for testing RUPES mechanism, poverty analysis, stakeholder consultation - Review of potential payment mechanisms and feasibility studies of certification schemes - Follow up and proposals to potential buyers of biodiversity conservation - Enhancing stakeholder awareness of biodiversity | - Carbon: C measurement, tree growth monitoring, tree planting, negotiate with carbon buyer. - Plans for ecotourism lodge lodged with FPE - Willingness to pay for watershed functions confirmed (PREM project) - Community based production and marketing of bottled water, citrus, mushroom spawn, fruit vinegar. - Ecology seminars for farmers and students - Flora and fauna documented - Boundary delineation of Ancestral Domain - Land use planning and management will community - Water flow measurement and monitoring - Research on transpiration | - Start-up workshop for CHARM & partners - Orientation Meeting on the Project for the prospective members of the Technical Advisory Group (TAG). - Orientation on Bakun RUPES for the Bakun LGU and BITO - Planning workshop with TAG - Dialogue re PES with hydroelectric co. - BITO orientation with village officials & community leaders. - Ethnobotanical res. survey for Bakun Ancestral Domain - Rapid Hydrological Assessment - Valuation studies of watershed services - Cross visit to KEF RUPES site | - Social mobilization (watershed forum formed and active) - Economic and hydrology studies providing technical advice - Increased level of awareness including among beneficiaries - Interaction and sensitization of buyers of environmental services - Sensitization of policymakers on the value of environmental services and importance of rewarding upland communities - Assessment of development needs of upstream watershed and identification of priority development programs - Organization of workshop to discuss sharing of hydropower royalty |
| Other sources of finance for the site | - ACIAR project on biophysical aspects of hydrology (2002-06) - Participatory activities with the Centre for Soil Conservation and Agroclimatology (2001-03) - DFID Negotiation Support for Land Tenure & Policy Development (2002 to 2005) - BASIS with IFPRI and Michigan State University. - EEPSEA and BASIS Project “Willingness to Pay for Environmental Services”. - PhD Student (Belgium) on development of a negotiation support model for watershed management. | - Million Trees Planting Program and Nagari Nursery Program funded by GoI and APHI. GoI will fund about USD0.5 million for 2003/04 for various activities. - Provincial Government plans to fund about USD4.1 million for 2003-2007 to rehabilitate land, fish and forest conservation, - JIFPRO (Japanese NGO) USD25,000 to rehabilitate 50 ha of degraded forest. Pilot for AR-CDM project - PhD on impact of forest loss and land use change on rive flow and limnology (ANU, Australia) | IRD provides in-kind resources for site work. Technical advice and funds for workshops from CIFOR | Possibility of UNDP funding and a Peace Corp Volunteer to help with bio-diversity research and ecology education. |  | BIWMP has already invested about US$650,000.00 in Kulekhani watershed area. Winrock’s Equitable Hydro Program has a total budget of US$150,000 part of which is spent in research studies in Kulekhani hydropower site. |

Appendix 4

Rewards for Environmental Services – experience of RUPES action research sites

The mission was able to visit one RUPES action research site – Sumberjaya in Sumatra.  At this location rewards for environmental services (RES) in terms of actual payments (PES) was not functioning – in terms of buyers of environmental services making payments to sellers of ES.  However significant improvements were taking place in terms of watershed management due to coffee growers getting secure tenure to their occupation of forest land (which they had settled illegally).  This can be described as a reward for environmental services – farmers getting more secure tenure in return for undertaking to plant an maintain a certain density of tree cover.  However, given secure tenure of their land, it will be in farmer’s own interest to take a longer term view of their production system, and switch from coffee monoculture (which gives a high yield, but only for a few years) to a more sustainable multi-storey agro-forestry system – as already practiced by those farmers with private land.   Although the multi-storey cropping system does reduce erosion (and so is an environmental service), the major “consumers” of the environmental service are the “producers” - the farmers who gain a more sustainable production system.

The coffee/tree agro-forestry system does however reduce soil erosion – which is of direct benefit to the farmer who now has a longer term stake in his land.  Reducing erosion and so silt in river water is also of value to downstream water users – in this case domestic users and a hydro-power company.  However these users have been unwilling to pay farmers to adopt practices that may reduce silt in water.   Two systems have been constructed to provide people living in villages with piped water supplies.  Users of such water systems have shown themselves unwilling to pay for the piped system itself, let alone ES to ensure silt-free water.  In one case, rather than pay for the system, individuals have laid their own unburied plastic pipes to the source.  In the other they have refused to renew a silt extraction system that was swept away in a flood, with richer households installing their own or shared pumped wells, and poorer households tolerating silty piped water or going back to collecting water from the river.

The hydro-power company suffers from siltation of its reservoir.  The system was designed to be flushed periodically to remove silt – an additional cost that might have been avoided if silt levels in water had been very low.   Until two years ago the company funded social development activities for people living in the area.  By law, these payments should be continuing, and could be expanded to cover ES.  However faced with a siltation problem, the company is talking of removing farmers from land near its reservoir so it can plant trees or bamboo.

Although there has been little progress in terms of payment for ES by users of ES, there has been some significant building of social capital and local institutions.   Five farmer groups have already obtained five-year leases from Forestry Department, which will be extended to 25 years if farmers keep to lease terms.    Another 23 groups are in the process of applying for leases.  In total these groups cover about 80% of the watershed forest area of 15,000 ha.  Some groups have been formed with little or no external support, and groups are being used as a forum for other issues such as seeking advice on pest control from Agricultural Extension.

Other RUPES sites report more obvious PES for watershed functions.   In west Lombok, there are payments by the main town (Matteram) to upstream communities in watersheds providing domestic water supplies, and also payments to communities where rivers are being used for white water rafting.   These payments seem partly motivated on the basis of equity – to share the benefits of tourism to a wider community.  At the Cidanau, payments for water-related ES are made by an industrial water buyer.  For a 50 ha pilot plot they amount to Rp175 million per year. In return the land owners have to maintain over 500 canopy-type trees per ha of at least 3 m height.

At Singkarak Lake taxes are paid by the hydropower authority amount to US$100,000 per year.  Previously all this was paid to the province, but now 70% go to the two districts in the lake watershed, who pass 80% of this on to nagaris – a recently revived traditional form of local government.  However the division between districts is by their relative area of lake, not watershed, and total payment by the hydropower authority relates to the amount of power generated, not water used.  Moreover the distribution of payments partly relate to damage done by the hydropower scheme (which has increased fluctuations in the lake level), cover social programmes such as education and mosques, and for clearing water hyacinth.  RUPES has raised awareness on the need for watershed conservation, and identified other potential ES of landscape beauty, biodiversity and carbon sequestration.  However, given the large area and population in this catchment (58,460 ha of watershed, 400,000 people), an annual payment for one nagari only amounted to US$10,000 – or US$1 per person.

In the Philippines hydropower schemes make the payments shown in the table below.   At Bakun payments from two hydropower schemes are quite small – in 2004 they amounted to US$6,300 for watershed management and US$8,000 for poverty and social programmes.

Payments by Hydropower Authorities in the Philippines

|  |  | Distribution of payment  local level government |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Baranguy | Municipality | Province | Region |
| Tax | 1% of gross revenue | 35% | 45% | 20% |  |
| Electrification fund | P0.0025/kwh |  |  |  |  |
| Development and livelihood fund | P0.0025/kwh | 20% | 25% | 25% | 30% |
| Reforestation, watershed management, health and environmental enhancement | P0.0050/kwh |  |  |  |  |

However these payments seem mostly limited to watershed conservation services aimed at improving or safeguarding water supplies.   Payments are limited (in west Lombok Rp500 per household per month), which may partly be due to the lack of a direct connection between conservation activities involving modifications to land use and silt content of water.  Soil loss from farmland is not the only type of erosion or source of silt.  High silt levels have been recorded in streams emerging from relatively undisturbed forests.  Soil is also washed out of paddy fields, erosion takes place along roads and trials, while rivers erode their banks which can result in substantial landslides.   Transaction costs may be high, especially if the time factor required to mobilise communities is taken into account – in Sumberjaya it has been calculated at around Rp0.5m per household, compared with average farm income of Rp1.0m/year.

Although watershed services (such as stabilising river flows, reducing erosion, lower silt content in water) are the major ES at a number of RUPES site, there is a growing consensus that land use and vegetation do not have a great impact on river flow – and hence the value of ES, at least in terms of down stream users can be overstated.  What has become known as “new hydrology” reduces the role of forest in watershed conservation and river flow.  The need to preserve forest in order to safeguard river flows from catchments is being called a “useful myth” – useful in terms of maintaining river flows, but a myth in terms of maintaining river flows – in fact transpiration from trees can reduce the volume of water available for downstream users.

Research at Singkarak Lake linked to RUPES (a PhD student from Australia) is investigating if forest cover helps maintain river flows and water quality.  In particular it is seeking to establish if the new hydrology really is correct in suggesting that forest cover has little or no impact on  regulating river flows, reducing  flooding,  or that forest cover does not always reduce erosion and sediment transport and maintain water quality.  In particular it is seeking to separate the relative influence of landscape (landform, geology & soils) and climate from land cover for all watershed function indicators; and also to separate the influence of ‘land cover’ from ‘other disturbances’ (including human) with respect to influence on erosion levels, sediment transport & other water quality indicators.  A survey of stakeholders – local development agencies, policy makers and the public, reveals that local ecological knowledge supports the “useful myth” and decline in forests and conversion of land to agriculture is blamed for reduced dry season river flows, floods, reduced infiltration (and so fall in groundwater and reduced spring flow) sedimentation and even a collapse of the lake fishery.  In fact, examination of rainfall records shows no significant change in climate.    Modelling, building on earlier models developed by RUPES, suggests that even quite drastic changes in land cover and watershed conservation (both positive and negative) would have little impact on the amount of hydropower generated – at least partly because of the considerable influence of the lake in buffering river flows.

Arguments over the “new hydrology” are also being investigated at Sumberjaya.   Although results from controlled plots show that multi-story agro-forestry and other conservation methods can significantly reduce erosion, it is difficult to translate this into impacts for downstream water users.  Measurement of sediment loans in streams coming out of sub-catchments show that erosion is, to a large extent, a natural process and takes place regardless of human intervention - high levels of sediment have been measured in streams emanating from relatively undisturbed forest.  At the same time, significant erosion can take place immediately downstream of forest and agro-forest areas, as rivers erode their banks and from paddy terraces.   All this dilutes the impact of reducing erosion from agro-forest land use.

ES payments may also be made for preserving biodiversity – but these tend to be limited to the best preserved pockets of natural forest – with payments often made by international NGOs.    There seems limited scope for biodiversity PES in the agro-forestry situations found in most RUPES sites – or indeed in other locations where there is a significant number of poor people who may benefit from such payments.   At the Bungo site in Indonesia, the jungle rubber ecosystem, although rich in flora and fauna (especially relative to alternative plantation land uses), however it lacks the major “flagship” species such as orang-utans.   The best option maybe to designate the area as a corridor between areas of natural forest – which have more “marketable” biodiversity.   Another option for Bungo was to market jungle rubber as an eco-labelled product – however its quality is not high enough.  Overall the potential for eco-labelling is constrained by limited consumer demand.  A RUPES study (Review of the Development of Environmental Services Market in Indonesia, Suyanto et al, 2005) has concluded that payments for preserving landscapes may have more potential for wider application.

A final type of PES is payment for carbon sequestration.   The possibility of such payments seem to have been a major incentive to establish RUPES, but have not materialised as expected – partly because of slow progress in the implementation of Kyoto, and partly because of an excessively complicated payment system resulting in very high transaction costs for small landowners or communities.  However proposals for carbon sequestration projects are being developed at the Kalahan site in the Philippines.

Appendix 5

Proposed modified logical framework

| narrative summary | measurable indicators | means of verification | important assumptions |
| --- | --- | --- | --- |
| GOAL |  |  |  |
| Develop new mechanisms for enhanced livelihood and resource security of poor upland communities in Asia | Increased income and food security, ensured security of access to land, and better welfare of households and communities managing environmental services in upland watersheds Improved and safeguarded environmental values including hydrological/watershed functions, biodiversity/landscape, and carbon sequestration. | Socio-economic surveys conducted in target areas GIS/remote sensing analysis of vegetative cover change Monitoring of watershed functions Review of project and mission reports | Effective government commitment to providing an appropriate support infrastructure for environmental transfer payments. Effective government commitment to decentralization of natural resource management Necessary policy and institutional reforms are in place Sufficient political & economic stability exists Participating country and donor interest and support for poverty alleviation of the upland poor in the target countries and regions |
| Purpose |  |  |  |
| Create the basis for systems to reward the poor for the environmental services they provide for the global and national communities | Agreements have been activated in at least 6 project sites that recognise local communities' land use rights in recognition for their efforts to improve the environmental services provided by their local watersheds. Increased adoption of agroforestry and community forestry practices by large numbers of small holder households across at least 6 project sites More effective locally-led natural resource management institutions are in place that actively manage environmental services in upland watersheds in partnership with local and national government bodies in at least 6 project sites. | Documents that verify changes in land tenurial status cross-checked Estimates of the extent of adoption of innovations Publications containing evidence that the transfer payments mechanisms were agreed and implemented Evidence from governments that support for locally-led NRM has increased | Practical, cost-effective methods for achieving participation of the poor in environmental service payments programs and projects are identified. Appropriate technical innovations that enable enhanced both prosperity and improved environmental services have been identified and are practicable for widespread adoption by upland communities. Appropriate methods, databases, technologies, institutional mechanisms, and policy options can be identified or developed. There is sustained commitment of national collaborating institutions to the goal of improving the rewards to upland communities for the environmental services they provide. |

| OUTPUTS | ACTIVITIES | Measurable indictors and means of verification |
| --- | --- | --- |
| 1. Identification of environmental service functions in a range of settings, and assess where and how the benefits of these services currently are distributed. | - Develop a typology that identifies the characteristics of the environmental services, including the degree to which these services can be achieved by alternate solutions, and how they depend upon the land use practices of upland communities. - Identify the needs of the upland communities providing the services, and elucidate the constraints to the maintenance or enhancement of these environmental service functions. - Identify the beneficiaries of the environmental service functions who have a stake in these services. - Quantify the benefits currently received by the various stakeholders | - The typology is developed, published, and placed on the project web site. 1.2 A study of the communities' needs and constraints to effectively benefiting from environmental service payments mechanisms has been completed, published, and disseminated. 1.3 Stakeholder analysis surrounding the environmental services completed for the key action pilot sites and disseminated. 1.4 Analysis of the benefit distribution for the major environmental services completed. |
| 2. An array of mechanisms is developed and tested with communities in at least 6 sites, across a range of settings, that will reward the poor for the environmental services they provide. | 2.1 Identify and engage key partners, and identify and select representative action research pilot sites. 2.2 Test new environmental service transfer payments methods in an action research mode in the pilot areas. 2.3 Develop replicable models for benefit sharing, and identify the factors that contribute to success and risk in the pilot studies 2.4 Identify policy issues emerging from the experience of these sites to inform Output 3. | 2.1 An appropriate group of local, national, and international partners are shown to have been working actively together to accomplish the activities and a network of at least 6 action research sites has been established. 2.2 Successful methods for new environmental service payments have been derived and have been fully documented and shared widely throughout the region. 2.3 Practical benefit sharing service payments mechanisms have been operationalised in the action pilot sites, and these experiences have been replicated in a range of sites outside the pilot action network. |
| 3. A transparent enabling institutional environment at local, subnational, and national levels has been supported, so as to deliver rewards that are effective, equitable, and sensitive to marginalised groups (including ethnic groups and women). | 3.1 Identify the conditions necessary to enable environmental transfer payments, and the extent to which they now exist. These include political, legal, financial and social conditions. 3.2 Build the capacity of stakeholders to support and engage in environmental transfer payments activities (including negotiation skills and processes) 3.3 Assist collaborators to put in place a conducive policy framework for environmental service payments to poor communities undertaken. | 3.1 A policy review analysing the necessary conditions underlying successful transfer payments to communities is completed and published. 3.2 Consultations, training, and knowledge dissemination conducted to increase capabilities for successful engagement in environmental transfer payments. Reports published. 3.3. Action to assist collaborators in installing conducive policy frameworks at the key action pilot sites has been implemented. Policy memos and reports are available. |
| 4. Awareness of the potential for rewards to enhance environmental services has been raised among government officials, and the producers and consumers of these services. | - A platform for the exchange of views has been firmly established through the programme, initially in the targeted pilot areas, and later expanded to broader domains. - Tools have been developed and deployed to educate and increase the awareness of various audiences about the issues and opportunities surrounding environmental service payments systems for the upland poor, through such media as radio, video, print, and the internet. | - Fora for the exchange of views have been implemented, and reports on the outcome of these for a have been produced. 4.2. Various media products are available as outputs of this activity. |
| 5. Effective partnerships among consortium member institutions and regional and national organisations have been developed and managed. | - The specific needs for partnerships to accomplish the various outputs will be determined. - Specific partnerships to achieve each of the outputs are identified, developed, managed and monitored effectively. | 5.1 Analysis of the partnership needs to achieve the objectives of the project has been completed and reported. 5.2 A strong consortium of international, national, and local partners has been established and is shown to be effective. |