1.2 Enhanced Capacity for Carbon Finance

| Year | Activity | Inputs | Cost (in US $) |
| --- | --- | --- | --- |
| 2005 | Gases and Institutions Studies | - Other ICRAF Staff - ICRAF Scientist - Lab fees - Consultant for Institutions | 13,500 24,000 14,000 15,000 |
| 2006 | Gases and Institutions Studies | - Other ICRAF Staff - ICRAF Scientist - Lab fees | 13,500 33,000 6,000 |
| 2007 | Gases and Institutions Studies | - Other ICRAF Staff - ICRAF Scientist - Lab fees | 13,500 33,000 6,000 |
| 2008 | Gases and Institutions Studies | - Other ICRAF Staff - ICRAF Scientist - Lab fees | 13,500 33,000 6,000 |
| 2009 | Gases and Institutions Studies | - Other ICRAF Staff - ICRAF Scientist | 13,500 33,000 |
| Total |  |  | 270,500 |

Note:

- 4.5 staffmonths – other ICRAF staff time in years 1-5

- 2 staffmonths – ICRAF Scientist staff time in year 1 and 2.75 staffmonths in years 2-5