## Summary
WKIEMP budgets
| Actual expenditures | Budget | Redidual
Contractual budget
July 2005-June 2006 | 260676.83 | 232300
July 2006-June 2008 | 435024.67 | 447100
Extra budget expenses for Baseline
July 2005 - Jun 2007 |  | 69500.86
July 2007 - Nov 2007 |  | 48226.72
Totals | 695701.5 | 797127.58 | 101426.08 | This is how much we have underspent

## Jul 2006 - Feb 2008
WESTERN KENYA INTEGRATED ECOSYSTEM MANAGEMENT PROJECT (WKIEMP)
CONTRACT BETWEEN KARI AND ICRAF FOR THE BACKSTOPPING OF WKIEMP BY ICRAF
2005/2006 WORK PLAN
FUNDED BY: THE KENYA AGRICULTURAL RESEARCH INSTITUTE
GRANT PERIOD: JULY 2006 TO JUNE 2008
PROJECT ID:
FINANCIAL REPORT FOR THE PERIOD 01 JULY 2006 TO 29TH FEB 2008
|  |  | Actuals | Total | Total
|  |  | Expenditure | Expenditure | Budget
|  |  | 2006-07-01 | 2006-07-01 | 2007-07-01
|  |  | Feb 2008 | Feb 2008 | 2008-06-01
|  |  | USD | USD | USD
| FUND RECEIVED |  | 0 | 0
EXPENDITURE
1.2: Enhanced Capacity for Carbon Financing
.01 | Technical Assistance | Technical Assistance | 192728.68 | 192728.68 | 105000
.02 | Equipment | Equipment | 1095.86 | 1095.86 | 0
2.0: Technical Bacstopping
.03 | Field Trials | Field Trials | 37754.93 | 37754.93 | 43500
.04 | Technical Assistance | Technical Assistance | 77208.59 | 77208.59 | 77000
3.0: Monitoring & Evaluation
.05 | Technical Assistance | Technical Assistance | 63788.36 | 63788.36 | 221600
.06 | Equipment | Equipment | 62448.25 | 62448.25 | 0
| TOTAL EXPENSES |  | 435024.67 | 435024.67 | 447100
| FUNDS BALANCE (DUE TO ICRAF) |  | -435024.67 | -435024.67

## Jul 05 - Jun 06
WESTERN KENYA INTEGRATED ECOSYSTEM MANAGEMENT PROJECT (WKIEMP)
CONTRACT BETWEEN KARI AND ICRAF FOR THE BACKSTOPPING OF WKIEMP BY ICRAF
2005/2006 WORK PLAN
FUNDED BY: THE KENYA AGRICULTURAL RESEARCH INSTITUTE
GRANT PERIOD: JULY 2005 TO JUNE 2006
PROJECT ID: PO72981
FINANCIAL REPORT FOR THE PERIOD 01 JANUARY TO 31 JUNE 2006
|  |  | Actuals | Actuals | Actuals | Total | Total
|  |  | Expenditure | Expenditure | Expenditure | Expenditure | Budget
|  |  | Jul - Dec | Jan - Mar | Apr - Jun | Jul05 to | Jan to Jun
|  |  | 2005 | 2006 | 2006 | 2007-06-06 | 2006
|  |  | USD | USD | USD | USD | USD
FUND RECEIVED
|  |  | 0 | 0 | 0 | 0
EXPENDITURE
1.2: Enhanced Capacity for Carbon Financing
.01 |  | Technical Assistance | 3367.64 | 21185.19 | 31433.7 | 55986.53 | 66500
.02 |  | Equipment | 0 | 0 | 0 | 0 | 0
2.0: Technical Bacstopping
.03 |  | Field Trials | 4259.6 | 985 | 8280.48 | 13525.08 | 24000
.04 |  | Technical Assistance | 12941.83 | 0 | 22557.85 | 35499.68 | 37500
3.0: Monitoring & Evaluation
.05 |  | Technical Assistance | 27845.76 | 69251.62 | 58568.16 | 155665.54 | 104300
.06 |  | Equipment | 0 | 0 | 0 | 0 | 0
| TOTAL EXPENSES |  | 48414.83 | 91421.81 | 120840.19 | 260676.83 | 232300
| FUNDS BALANCE (DUE TO ICRAF) |  | -48414.83 | -91421.81 | -120840.19 | -260676.83
I certify that records and supporting payment documents are in file at ICRAF Headquarters
(Nairobi,Kenya) and are available for review by the KARI representatives
upon request.
| Signature: _____________________________ |  |  |  |  | 3 April 2007
Name : Laksiri Abeysekera
Position : Director of Finance and Operations

## Baseline Period 1
WESTERN KENYA INTEGRATED ECOSYSTEM MANAGEMENT PROJECT (WKIEMP)
CONTRACT BETWEEN KARI AND ICRAF FOR THE BACKSTOPPING OF WKIEMP BY ICRAF
2005/2006 WORK PLAN
FUNDED BY: THE KENYA AGRICULTURAL RESEARCH INSTITUTE
GRANT PERIOD: JULY 2005 TO JULY 2009
PROJECT ID: PO72981
FINANCIAL REPORT FOR THE PERIOD 01 JULY 2005 TO 31 JUNE 2007
|  |  | Actuals | Actuals | Actuals | Actuals | Actuals | Total
|  |  | Expenditure | Expenditure | Expenditure | Expenditure | Expenditure | Expenditure
|  |  | Jul - Sept | Oct - Dec | Jan - Mar | Apr - Jun | Jul06 to | Jul05 to
|  |  | 2005 | 2005 | 2006 | 2006 | 2007-06-06 | 2007-06-06
|  |  | USD | USD | USD | USD | USD | USD
FUND RECEIVED
|  |  | 0 |  | 0 | 0 | 0 | 0
EXPENDITURE
31380 | Temporary staff |  |  | 0 | 0 | 645.91 | 20687.4 | 21333.31
31370 | Casual Labour |  | 1619.89 | 919.87 | 2373.66 | 3819.12 | 6487.92 | 15220.46
32010 | Consultancy |  | 0 |  | 0 |  | 677.48 | 677.48
34110 | Travel Costs |  | 0 | 0 | 0 | 0 | 0 | 0
35034 |  | Upper/Mid/Lower Yala Nzoia& Nyando | 200 | 17.07 | 0 | 0 | 7515.06 | 7732.13
35500 | Field supplies/Lab Expenses |  | 96.48 | 843.87 | 22.01 | 289.38 | 2164.51 | 3416.25
Motor Vehicle costs
36320 |  | Fuel | 432.49 | 913.01 | 437.53 | 1479.74 | 8114.24 | 11377.01
36310 |  | Maintenance & repairs | 395.7 | 210.13 | 294.18 | 457.56 | 6800.67 | 8158.24
36315 |  | Insuarance | 0 | 0 | 0 | 0 | 1585.98 | 1585.98
| TOTAL EXPENSES |  | 2744.56 | 2903.95 | 3127.38 | 6691.71 | 54033.26 | 69500.86
| FUNDS BALANCE (DUE TO ICRAF) |  | -2744.56 | -2903.95 | -3127.38 | -6691.71 | -54033.26 | -69500.86
I certify that records and supporting payment documents are in file at ICRAF Headquarters
(Nairobi,Kenya) and are available for review by the KARI representatives
upon request.
| Signature: _____________________________ | [6 empty] | 2007-11-01
Name : Laksiri Abeysekera
Position : Director of Finance

## Baseline Period 2
WESTERN KENYA INTEGRATED ECOSYSTEM MANAGEMENT PROJECT (WKIEMP)
CONTRACT BETWEEN KARI AND ICRAF FOR THE BACKSTOPPING OF WKIEMP BY ICRAF
2005/2006 WORK PLAN
FUNDED BY: THE KENYA AGRICULTURAL RESEARCH INSTITUTE
GRANT PERIOD: JULY 2005 TO JULY 2009
PROJECT ID: PO72981
FINANCIAL REPORT FOR THE PERIOD 01 JULY 2007 TO 30TH NOVEMBER 2007
|  |  | Actuals | Total
|  |  | Expenditure | Expenditure
|  |  | Jul 07 to | Jul 07 to
|  |  | 2007-11-01 | 2007-11-01
|  |  | USD | USD
FUND RECEIVED
|  |  | 0 | 0
EXPENDITURE
31380 | Temporary staff |  | 3010.12 | 3010.12
31370 | Casual Labour |  | 23262.01 | 23262.01
32010 | Consultancy |  | 0 | 0
34110 | Travel Costs |  | 0 | 0
35034 |  | Upper/Mid/Lower Yala Nzoia& Nyando | 13115.92 | 13115.92
35500 | Field supplies/Lab Expenses |  | 438.56 | 438.56
Motor Vehicle costs
36320 |  | Fuel | 4257.93 | 4257.93
36310 |  | Maintenance & repairs | 4142.18 | 4142.18
36315 |  | Insuarance | 0 | 0
| TOTAL EXPENSES |  | 48226.72 | 48226.72
| FUNDS BALANCE (DUE TO ICRAF) |  | -48226.72 | -48226.72
I certify that records and supporting payment documents are in file at ICRAF Headquarters
(Nairobi,Kenya) and are available for review by the KARI representatives
upon request.
| Signature: _____________________________ |  |  | 2008-03-12
Name : Laksiri Abeysekera
Position : Director of Finance and Operations