|  | Indicators | Data collection methodology | Task responsibility | When (How often) |
| --- | --- | --- | --- | --- |
| Activities - Community mobilization and sensitization - Block baseline data collection - Stratified micro-catchment delineation within blocks - Community PAPs development - Establishment of tree screening trials - Establishment of tree nurseries - Establishment of cover crops, fallow, fodders in degraded lands - Conservation activities for local and indigenous bio-diversity resources - Project Input deliveries -equipment, seeds, fertilizers, etc. - De-silting of check dams & water pans in Lower Nyando block - Construction of soil conservation structures to control soil and water loss - Capacity building training activities for community leaders - Capacity building training activities for technology transfer - PAP Grant proposals developed - Capacity training in carbon trading - Targeted research to develop procedures for monitoring GHGs - ICRAF building KARI’s capacity to measure carbon baselines, end of project carbon stocks and national capacity for carbon M&E - CBO capacity building for carbon contracting - Capacity building in M&E for project staff, extension and communities | - Activities carried out as planned | - Back to office reports - Proceedings of Community mobilization and sensitization meetings - PCO logistical records - Back to office reports - Delivered questionnaires for data entry - Updated database shared with ICRAF for data analysis - Microcatchment boundary verification from maps - PAP development forms duly completed - Field visits - Field visits - field visits - District Environment Action Plans - Environmental assessment reports - PCO and CBO records - Field visit - Field visit - Training workshop report - Training workshop report - PCO records, BTC reports - Training reports - Field visits - Research reports - Training reports - Training reports - Training reports | - CPO, FO - M&E - FO, M&E - CPO, FO - FO, ICRAF - FO, M&E - FO, M&E, LO - FO, M&E, District Environment Officer (DEO) - PCO, CBO - FO, DEO, M&E - FO, DEO, M&E, District Agriculture Officer (DAO) - CPO, FO, M&E - CPO, FO, DAO, - PCO - ICRAF - ICRAF, FO, M&E, - ICRAF, PCO - ICRAF, PCO - M&E. FO, PCO | - Weekly - Weekly - Once for every microcatchment - Monthly after opening the block - Monthly - Monthly - Bimonthly - Quarterly - Weekly - Monthly upon commencement of works - Monthly - Bimonthly upon block entry - Monthly - Monthly upon block entry - Quarterly - Ongoing - Quarterly - Quarterly upon engagement - Monthly upon block entry |
| Output - Block baseline data reports - Strong community structures - Micro-grants implemented - Better land management practices demonstrated - New check dam built - Old dams de-silted and maintained - Tree seedlings and fodders established in degraded hotspots - Community and project tree nursery initiatives begun - Alternative livelihood strategies provided to reduce pressure on critical habitats - Tree screening trials established | - Reports written and shared - Minutes of CBO meetings - Elections held according group constitution - Proposals received and vetted - Number of best bet practices demonstrated on-farm - NEMA compliant project report - Physical construction completed - Acquisition of desilting equipment - Total number of seedlings planted - 80% survival rate of the seedlings and fodders - Community preferred tree species planted - Number of tree nurseries established - At least 80% indigenous tree species in the nursery - Equitable distribution of tree nurseries across the microcatchment - Number of new livestock enterprises demonstrated and upscaled - Number of farms identified for the trials - Number of trials implemented. | - Training session held by ICRAF to PCO on baseline data analysis - Regular meeting by KARI and ICRAF to analyse data - Regular M&E for CBOs - Number of proposals received at PCO - Minutes of BTC meetings held - Field verification visits of on-farm demonstrations - District Environment Committee minutes of proposed check dam - Field Observation - Progress reports from the contractor - Completion certificate received from contractor - Contracts for desilting works signed - Georeferenced tree planting sites - Records of tree seedlings sold and/or given - Population counts of surviving tree seedlings - Community preferences for trees determined from baselines and continuous community interactions - Survey of existing tree nurseries - Field verification of composition of indigenous trees in nurseries - Georeferenced maps of tree nurseries distribution within microcatchment - Field verification of demonstrated and upscaled livestock activities - Field reports - Field verification visits on tree screening trials implemented. | - ICRAF and PCO - CPO, FOs, M&E - CPO, PC, FO, PC - FO, M&E - FO, M&E, NEMA - FO, M&E, PC - FO, M&E, ICRAF - FO, M&E, ICRAF, CPO - FO, M&E, LO - ICRAF, M&E - ICRAF, M&E, FO | - Once in the 3rd Quarter 2006/2007 - Monthly in 3rd and 4th quarter 2006/7 - Monthly - Quarterly - Quarterly - Bimonthly - Bimonthly - Monthly - Monthly - Once per contract - Once per contract - Monthly - Bimonhtly - Monthly - Once at every start of tree nursery establishment - Bimonthly - Bimonthl - Quarterly - Bimonthly - Monthly - Quarterly |
| Purpose/Outcome - Strong community structures taking leading role in IEM - To improve river water quality by checking rain water run-off in degraded hotspots which causes sediment load in river courses - To reverse land degradation through erosion control in hot spots - To reduce below and above ground carbon banks through carbon sequestration measures - Increased land productivity - IEM awareness in communities created | - Community participation in assessment, planning, decision making, implementation, and evaluation of integrated ecosystem management activities - Participation of local and regional institutions in planning and coordinating ecosystem management activities - Negative trend in erosion rates from farming plots receiving interventions by end of project - Increasing trend in abundance & diversity of plant species in at least 30% of local areas intervention sites - Sequestration of 3.3 tons ha1 of carbon from blocks - Community application of IEM practices | - Field visits, CBO reports - DEO reports, water engineer reports, field visits - NEMA reports, water engineer reports, field visits - NEMA reports, ICRAF reports - Extension reports, CBO reports, field observations - CPO reports, CBO reports, DSDO reports | - CPO, FO, M&E - FO, ICRAF NEMA, CPO - ICRAF NEMA, ICRAF - FO - FO, CPO, - FO, CPO, M&E | - Biannually - Biannually - Bi-annualy - Annually - Quarterly - Annually |
| Goal/Impact - Promote a set of IEM interventions reduce land degradation, increase land productivity, reduces atmospheric GHGs, improved bio-diversity & decreased erosion in river basins on Nyando, Yala & Nzoia | - 20% adoption rates of IEM interventions in project area and 10% surroundings after 3 years and 80% at the end of project - Negative trend in P runoff from demo plots in at least 50% of the focal area by end of project - 50% community participation in village integrated ecosystem management planning exercises - 60% of ecosystem management planning activities inclusive of local and/or regional institutions - 20% of households in pilot villages, 10% in surrounding villages adopting IEM practices on farm - 20% increase in organic matter content of soils in plots where the improved SLM technologies have been adopted - 10 % increase in abundance and diversity on farms, 5 % increase in off-farm ecosystem richness indicator, 50% of communities identifying a conservation strategy for specific threatened or endemic species in community plans - 10% reduction in erosion rates from farming plots receiving interventions | - Monitoring survey - Soil analysis studies - Plant tissue analysis - Monitoring survey - Stakeholder analysis - Monitoring survey - Soil analysis studies - Plant tissue analysis - Biodiversity assessment study - Erosion studies | - PCO, ICRAF - PCO, ICRAF - PCO, ICRAF - PCO, ICRAF - PCO, ICRAF - PCO, ICRAF - PCO, ICRAF, NEMA - PCO, ICRAF | - Biannual - Biannual - Biannual - Biannual - Biannual - Biannual - Biannual - Biannual |