THE SOCIO ECONOMIC SURVEY PROGRESS REPORT

LOWER YALA BLOCK

16TH NOV-22ND DEC

We moved in to lower Yala block on the 16th of November and were able to go through with the interviews up to the above indicated date.

Enumerators:		Azenapher Mideva

George Odhiambo

Salome Aoko.

Sampling Method:

By the help of the GPS we managed to locate the clusters.

On reaching the indicated points we would spread moving towards the direction shown by the arrow. There we sample 10 households.Inorder for us not to be bias we decided that we should not interview very close relatives like brothers staying in the same homestead or even those staying very close to one another

Timing:

The questionnaire entails very intensive work, we therefore had to first of all convince the respondents by introducing the work to a level that they would understand and also making them aware of the duration that we would take.Ofcourse this was a setback because others declined to go through with the interviews.

There were also some respondents who at the beginning of 	the interviews were very willing but at some point they became very hesitant in answering the questions therefore wasting a lot of time. So generally some interviews went on fast enough while others very slow.

All in all we managed to meet our target of > 20 house holds per week thus in three clusters except for the weeks when we had a holiday and the day for the contracts.

Work done:

We managed to work in a total of 14clusters where we interviewed a total of 143 household as represented below:

Sub locations			Cluster			Hh done

1. Kanyardet			1			10

2. Ndori			2			10

3. Kambare+ Onyinyore	3			10

4. West Katieno		4			10

5. Kanyadet + Ndori		5			10

6. Rera				6			10

7. Kambare			7			10

8. Kambare			8			10

9. Dienya East			9			10

10. Onyinyore			10			10

11. Onyinyore			11			10

12. Ramula			12			0

13. Nguge			13			0

14. Uriri			14			10

15. Gombe			15			10

16. Uranga			16			10

Some clusters were shared by more than one cluster thus:

Kanyadet + Ndori

Kambare + Onyinyore

Some sub locations fell in more than one cluster

Kambare

Onyinyore

Kanyadet

Ndori

Gombe

We have another two clusters with a total of 17 house holds to do as soon as we come back from the holiday thus 12 and 13.

General comments:

Most farmers that we interviewed are willing to plant trees. Some schools are also calling for the tree planting groups to visit them.

Most of the time we shared cars and a lot of time was spent dropping different groups in different clusters.

Yala block is a shrub land , homes are very sparse and so we spent a lot of time locating them.