20th-24th Nov. 2006 Lower Yala Tree screening report

| Date | Activities | Remarks |
| --- | --- | --- |
| 20/11/2006 | Went to lower Yala site to inform our field guys of a short training that will take place on a Thursday at one of the sites and thereafter kick-off the exercise of taking the measurements. | This is aimed at equipping the field staff with adequate knowledge on the measurements needed from the field. This will speed up the activities in the field. |
|  | Purchased materials. | These are materials needed for various activities to take place during establishment and monitoring of screening trial studies in lower Yala. |
| 21/11/2006 | Generating list of selected farmers in lower Yala block for screening trial | The list is to assist field persons in lower Yala identify selected farmers for measurements and follow-up. |
| 22/11/2006 | Generating list of selected farmers in lower Yala block for screening trial | The list is to assist field persons in lower Yala identify selected farmers for measurements and follow-up. |
| 23/11/2006 | Training, measuring and taking measurements of screening plot in kanyadet | We trained the four field foremen in lower Yala on how to measure screening plots in their respective areas. Soil samples, infiltration and plot characterization was done. Managed to work in one plot. |
| 24/11/2006 | Measuring and taking plot measurements of screening trial in Kanyadet. | Soil samples, infiltration and plot characterization was done. Managed to work in one plot. This activity also involved training of the field foremen. |

Summery - Lower Yala block.

2 farms have been measured, soil samples collected, plot characterization and 2 infiltrations done per plot.