Work plan as from June 2007

Subject

Tree management

Objective

To train farmers on good tree management to enhance good tree management

Plan

Train 160 farmers in lower Yala region

Methodology

Training to be done in clusters

Cluster 1

Osodo’s area (Osodo is a resource person)

Four meetings planned for this area because the area is very expansive covering five large sub locations (Kambare, Onyinyore, Gombe, Rera and Uriri)

Each meeting to take two days

Day 1

Instructions/ Training

Day 2

Validation/Practical

Duration: 	8 days

Cluster 2

Mack Ocholla’s area (Mack Ocholla is a resource person)

Three meetings planned for this area. Is also an expansive area covering four sub locations (Dienya East, Uriri, Wagai East and Wagai West)

Each meeting to take two days

Day 1

Instruction/ Training

Day 2

Validation/Practical

Duration: 	6 days

Cluster 3

Leonard Aleng’s area (Aleng is a resource person)

Three meetings planned for this area. Is also an expansive area covering three sub locations namely Rera, Ndori and Kanyadet both lower and upper Kanyadet

Each meeting to take 2 days

Day 1

Instruction/ Training

Day 2

Validation/ Practical

Duration: 	6 days

Cluster 4

George Anindo’s area (Anindo is a resource person)

Three meetings planned for this area. Is also an expansive area covering three sub locations (Ndori, Rera and Kambare)

Each meeting to take 2 days

Day 1

Instruction/ Training

Day 2

Validation/ Practical

Duration: 	6 days

Target: 	To finish training and Validation in the 2nd week of July 2007 (26 working days)

Survival counts

Start survival counts in the 3rd week of July 2007

Plan: 		Four farms per day

Duration: 	35 working days

Target: 	To finish survival counts in August 2007

Tree measurements

Start tree measurements in September 2007

Plan: 		Three farms per day

Duration: 	47 working days

Target: 	To finish first measurements in November

Weekly activities as from the month of June 2007

| WEEK | ACTIVITY |
| --- | --- |
| 4th to 8th June | Meeting at Onyinyore and Gombe sublocations |
| 11th to 15th June | Meeting at Kambare and Uriri (lower) sublocations |
| 18th to 22nd June | Dienya East and Wagai West sublocations |
| 25th to 29th June | Uriri (upper)and Wagai East |
| 2nd to 6th July | Kanyadet(Lower) and Kanyadet (Upper) sublocations |
| 9th to 13th July | Rera (upper) and Ndori sublocations |
| 16th to 20th July | Kambare(Lower)and (Lower) Rera |
| 23rd July to 31st August | Survival counts |
| 3rd September to 30th November | Tree measurements |