From: Walter Adongo

To: Anya Boye

### Subject: Provisional work plan seedling production- GEF

Date: 1st Dec. 2006

Kindly find a review of the budget and activities for December 2006.

1. Provisional budget for the GEF

(a) Tree seed

| Species | Quantity (Kgs) | Unit price (KES) | Total | Remarks |
| --- | --- | --- | --- | --- |
| 1. G. robusta | 5 | 3,000 | 15,000 | 2 kgs to the farmer groups |
| 2. C. equisetifolia | 2 | 3,000 | 6,000 | 1 kg to the farmer groups |
| 3. Syzygium cuminii | 4 | 1,000 | 4,000 |  |
| 4. Prunus africana | 3 | 2,000 | 6,000 |  |
| 5. Senna siamea | 5 | 1,000 | 5,000 | 2kgs to the farmer groups |
| 6. A. indica | 6 | 1,500 | 9,000 | 2 kgs to the farmer groups |
| 7. M.eminii | 20 | 300 | 6,000 | 10 kgs to the farmer groups |
| 8. T. emitica | 7 | 1,000 | 7,000 | 2 kgs to the farmer groups |
| 9. A. coriaria | 4 | 800 | 3,200 | 2 kgs to the farmer groups |
| 10. M. lutea | 2 | 1,000 | 2,000 | 2 kgs to the farmer groups |
| 11. W. ugandensis | 2 | 2,000 | 4,000 |  |
| 12. C. megalocarpus | 2 | 800 | 1,600 | To Lower Yala groups |
| 13. C. abssyinica | 2 | 1,500 | 3,000 | To Lower Yala groups |
| Total |  |  | 71,800 |  |

ICRAF

| Species | Quantity (Kgs) | Unit price (KES) | Total |
| --- | --- | --- | --- |
| 1. G. robusta | 3 | 3,000 | 9,000 |
| 2. C. equisetifolia | 1 | 3,000 | 3,000 |
| 3. Syzygium cuminii | 4 | 1,000 | 4,000 |
| 4. Prunus africana | 3 | 2,000 | 6,000 |
| 5. Senna siamea | 3 | 1,000 | 3,000 |
| 6. A. indica | 4 | 1,500 | 6,000 |
| 7. M.eminii | 10 | 300 | 3,000 |
| 8. T. emitica | 5 | 1,000 | 5,000 |
| 9. A. coriaria | 2 | 800 | 1,600 |
| 10. M. lutea | 1 | 1,000 | 1,000 |
| 11. W. ugandensis | 2 | 2,000 | 4,000 |
| 12. C. megalocarpus | 1 | 800 | 800 |
| 13. C. abssyinica | 1 | 1,500 | 1,500 |
| Total |  |  | 53,900 |

Nyando

| Species | Quantity (Kgs) | Unit price (KES) | Total |
| --- | --- | --- | --- |
| 1. G. robusta | 1 | 3,000 | 5,000 |
| 2. C. equisetifolia | 0.5 | 3,000 | 1,500 |
| 3. Senna siamea | 1 | 1,000 | 1,000 |
| 4. A. indica | 1 | 1,500 | 1,500 |
| 5. M.eminii | 5 | 300 | 1,500 |
| 6. T. emitica | 1 | 1,000 | 1,000 |
| 8. A. coriaria | 1 | 800 | 800 |
| 9. M. lutea | 0.5 | 1,000 | 500 |
| Total |  |  | 12,800 |

Lower Yala

| Species | Quantity (Kgs) | Unit price (KES) | Total |
| --- | --- | --- | --- |
| 1. G. robusta | 1 | 3,000 | 3,000 |
| 2. C. equisetifolia | 0.5 | 3,000 | 1,500 |
| 3. Senna siamea | 1 | 1,000 | 1,000 |
| 4. A. indica | 1 | 1,500 | 1,500 |
| 5. M.eminii | 5 | 300 | 1,500 |
| 6. T. emitica | 1 | 1,000 | 1,000 |
| 7. A. coriaria | 1 | 800 | 800 |
| 8. M. lutea | 0.5 | 1,000 | 500 |
| 9. W. ugandensis | 2 | 2,000 | 4,000 |
| 10. C. megalocarpus | 1 | 800 | 800 |
| 11. C. abssyinica | 1 | 1,500 | 1,500 |
| Total |  |  | 16,600 |

## Labour, materials, tools and equipment (Central nurseries)

| ### Item | Details | ### Total (KES) | ### Remarks |
| --- | --- | --- | --- |
| Labour | ### Potting 200MD x KES 250 | 50,000 |  |
|  | Pricking out and maintenance 2 persons x KES 7,000 x 6 months | 84,000 |  |
| Poly tubes | 300kgs x KES 300 | 90,000 | 100 kgs to farmer groups |
| Soil | 4 lorries x KES 4,000 | 16,000 |  |
| # Sand | 2 lorries x KES 6,000 | 12,000 |  |
| Manure | 2 lorries x KES 5,000 | 10,000 |  |
| Wheel burrows | 20 x KES 3,000 | 60,000 | To farmer groups |
| Watering cans | 20 x KES 500 | 10,000 | To farmer groups |
| Shovels | 20 x KES 250 | 5,000 | To farmer groups |
| Pruning knives | 25 x KES 150 | 3,750 | To farmer groups |
| ### Total |  | 340,750 |  |

ICRAF

| ### Item | Details | ### Total (KES) |
| --- | --- | --- |
| Labour | ### Potting 200MD x KES 250 | 50,000 |
|  | Pricking out and maintenance 2 persons x KES 7,000 x 6 months | 84,000 |
| Poly tubes | 200kgs x KES 300 | 60,000 |
| Soil | 4 lorries x KES 4,000 | 16,000 |
| # Sand | 2 lorries x KES 6,000 | 12,000 |
| Manure | 2 lorries x KES 5,000 | 10,000 |
| Total |  | 232,000 |

Lower Nyando

| ### Item | Details | ### Total (KES) |
| --- | --- | --- |
| Poly tubes | 50kgs x KES 300 | 15,000 |
| Wheel burrows | 10 x KES 3,000 | 30,000 |
| Watering cans | 10 x KES 500 | 5,000 |
| Shovels | 10 x KES 250 | 2,500 |
| Pruning knives | 12 x KES 150 | 1,800 |
| ### Total |  | 54,300 |

Lower Yala

| ### Item | Details | ### Total (KES) |
| --- | --- | --- |
| Poly tubes | 50kgs x KES 300 | 15,000 |
| Wheel burrows | 10 x KES 3,000 | 30,000 |
| Watering cans | 10 x KES 500 | 5,000 |
| Shovels | 10 x KES 250 | 2,500 |
| Pruning knives | 13 x KES 150 | 1,950 |
| ### Total |  | 54,450 |

NB: Following our discussions and prevailing weather conditions it shall be prudent to make the following adjustments:

(i) Double the soil, manure and sand requirements for Maseno Central tree nursery.

(ii) Increase the MD (man days) because of the wet soil. I had to have 5 people mixing the media and arranging the pots. Therefore, we hired 5 people extra for 10 days at a rate of 400Kshs per day.

(iii) Purchase 3 wheel burrows, 4 watering cans and 5 pruning knives for Maseno.

(iv) Purchase 5 plastic basins for Kisumu Central tree nursery.

(v) Purchase 50 petri-dishes, 5 packets of filter paper and 2 wash bottles to help rejuvenate the seed lab and hire a casual for one month to run the seed tests.

(vi) Agree with KARI on how they are going to source the materials as it is not clear.

(vii) Source for tilt net – we still need to assess the area.