From: Walter Adongo

To: Anya Boye

### Subject: Provisional work plan seedling production- GEF

Date: 3rd October 2006

The following meetings refer. The ICRAF staff meeting on 12th October, our meeting with KARI staff on 30th October and meeting with KEFRI staff in Maseno on 2nd November. To help us realize our objectives in seedling production, I wish to bring forth the following budget with the work plan

1. Provisional budget for the GEF

(a) Tree seed

| Species | Quantity (Kgs) | Unit price (KES) | Total | Remarks |
| --- | --- | --- | --- | --- |
| 1. G. robusta | 5 | 3,000 | 15,000 | 2 kgs to the farmer groups |
| 2. C. equisetifolia | 2 | 3,000 | 6,000 | 1 kg to the farmer groups |
| 3. Syzygium cuminii | 4 | 1,000 | 4,000 |  |
| 4. Prunus africana | 3 | 2,000 | 6,000 |  |
| 5. Senna siamea | 5 | 1,000 | 5,000 | 2kgs to the farmer groups |
| 6. A. indica | 6 | 1,500 | 9,000 | 2 kgs to the farmer groups |
| 7. M.eminii | 20 | 300 | 6,000 | 10 kgs to the farmer groups |
| 8. T. emitica | 7 | 1,000 | 7,000 | 2 kgs to the farmer groups |
| 9. A. coriaria | 4 | 800 | 3,200 | 2 kgs to the farmer groups |
| 10. M. lutea | 2 | 1,000 | 2,000 | 2 kgs to the farmer groups |
| 11. W. ugandensis | 2 | 2,000 | 4,000 |  |
| 12. C. megalocarpus | 2 | 800 | 1,600 | To Lower Yala groups |
| 13. C. abssyinica | 2 | 1,500 | 3,000 | To Lower Yala groups |
| Total |  |  | 71,800 |  |

## Labour, materials, tools and equipment

| ### Item | Details | ### Total (KES) | ### Remarks |
| --- | --- | --- | --- |
| Labour | ### Potting 200MD x KES 250 | 50,000 |  |
|  | Pricking out and maintenance 2 persons x KES 7,000 x 6 months | 84,000 |  |
| Poly tubes | 300kgs x KES 300 | 90,000 | 100 kgs to farmer groups |
| Soil | 4 lorries x KES 4,000 | 16,000 |  |
| # Sand | 2 lorries x KES 6,000 | 12,000 |  |
| Manure | 2 lorries x KES 5,000 | 10,000 |  |
| Wheel burrows | 20 x KES 3,000 | 60,000 | To farmer groups |
| Watering cans | 20 x KES 500 | 10,000 | To farmer groups |
| Shovels | 20 x KES 250 | 5,000 | To farmer groups |
| Pruning knives | 25 x KES 150 | 3,750 | To farmer groups |
| ### Total |  | 340,750 |  |

Note: The farmer groups are designated as Lower Yala and Nyando. It is envisaged that we shall have at least ten groups for each of the blocks.

Provisional work plan for the GEF seedling production and out planting

October 2006 – April 2007

| Activity | Time /Months |
| --- | --- |
| !. Seed sourcing | 1st week Nov. 2006 |
| 2. Soil, sand and manure collection | 1st week Nov. 2006 |
| 3. Potting | Nov-Dec. 2006 |
| 4. Pricking out | Nov.- Dec 2006 |
| 5. Maintenance | Continuous |
| 6. Farmers’ training for Lower Yala | 1st and 2nd weeks Nov. 2006 |
| 7. Follow-up trainings | 3rd week Nov. – Dec. 2006 |
| 8. Land preparation | Feb. – March 2007 |
| 9. Out planting | March – April 2007 |