On station nursery – ICRAF Kisumu office

Report on progress since Oct. 2006 when Walter Adongo and Anja Boye joined the project

(November 20th 2006)

The first meeting for the ICRAF nursery in Kisumu was held on Oct. 13th 2006. The following people attended:	Luka, Walter Adongo, James Owek, Robert Nyambati from KEFRI, and Anja Boye.

The target is to raise 200,000 seedlings before the long rains start in March 2007.

At the time of the meeting, James Owek was in charge of the nursery with Reuben as the nursery attendant in charge of watering and pricking. The 5 casuals were to be doing the potting. The situation in the nursery was the following:

- 6100 seedlings have been pricked and 10,400 tubes filled. 7800 seedlings are ready for planting.

It was agreed that the current speed in the nursery was too slow and that the casuals should be put on a new type of contract where they would be paid per unit tube filled, e.g. 300Kshs per 500 tubes filled. Progress was to be followed closely.

Walter Adongo is to take the lead in the nursery and prepare work plans and budgets.

Robert Nyambati produced 1 petty cash voucher for signature for 3kg Grevellia Robusta seeds, however, it was turned back since it was not for the project but for Markus. This petty cash voucher (No. 1801) has been signed by Markus Walsh – however, the seeds were not for the nursery. Consequently, I have instructed the Ass. Accountant and the Administrator, that Robert Nyambati is not formally part of any ICRAF activities and therefore cannot sign out petty cash after reviewing the Oct. expenditures for 2006.

In addition to the petty cash voucher mentioned above, there also 2 other petty cash vouchers, No.1840 (24,400Kshs) and 1841 (32,490), which should be looked into. Both are signed out in the GEFZ charge code. We (Walter and I) are still trying to trace where the seeds and other inputs went. These petty cash vouchers were prepared on Oct. 13th and 17th, hence after our meeting where it was made clear that Walter Adongo was now in charge. Both vouchers have been signed by Markus Walsh. The GRN notes dated Oct 13th for no. 1840 and Oct 17th for No. 1841.

On Oct. 26th, the situation is the nursery was the following:

- 13,320 seedlings are ready to be planted, hence only 7,220 seedlings have been produced since the 13th of Oct.

A meeting was called with Walter Adongo on Oct. 27th, where the continued low productivity was raised. The casuals were only filling 219 tubes per day and not the required min. 500. He promised to look into the situation and reported back on Oct. 30th that he has identified the problem and sorted it out.

During this month one staff in the nursery was given a verbal warning since he had not reported to work and also had had to leave early because of the influence of alcohol.

On Oct. 30th a meeting was held at KARI for plan for the on-farm nurseries in Lower Yala (minutes of the meeting is attached – Appendix 1). ICRAF committed to assist in the initial meeting for identifying suitable groups and in the subsequent trainings. KARI was to meet all expenses. Walter Adongo was to prepare a budget for the ICRAF and KARI expenses for raising seedlings and training for on-farm / community based nurseries (budget is attached, Appendix 2). ICRAF expenditures amounted to 106,600Kshs for seeds and other inputs. The budget was sent to KARI but as of today there has been no response. Two trainings have been carried out so far at the expense of KARI. Inputs still need to be given to the 2 groups.

It was further agreed in the meeting that KARI would be able to get/buy 30,000 seedlings from the central ICRAF nursery). We are still working on the unit price.

On Nov 1st a meeting was held with KEFRI to discuss the possibility of re-possessing the nursery in Maseno. It was agreed that we were to meet the following day and go through all the office and store space currently in the name of ICRAF (minutes of the meeting is attached – appendix 3). It was agreed that ICRAF can repossess the nursery and seed store. All other office space and stores were reverted back to KEFRI. Two people were hired for 1 week to clear the stores – however, they could not get access to the store where Dr. Bashir’s samples are kept. ICRAF is therefore today preparing a letter stating that the store is not officially KEFRI’s along with the cleared offices and one other store.

On November 14th Walter Adongo and I had another meeting regarding the nursery. At this point the situation is the nursery was the following:

- 75,100 seedlings had been raised

Walter gave the following plan for the remaining 124,900 seedlings:

- 2 weeks potting – 25 man days for 10 days. Agreed on a salary of 400 per 500 tubes filled

- 2 weeks pricking – 1 person can do 1000 tubes per day, e.g. 125 man days – will therefore need 9 people for 2 weeks

Walter signed out 166,600 Kshs for seeds and inputs on Nov. 14th:

Appendix 1

Minutes of the planning meeting for the block of Lower Yala held at KARI on October 30th between KARI and ICRAF

Present:

Eva Gacheru		-	KARI Field officer Yala

Christi			-	KARI

Bernard Wawuru	-	KARI student attached to ICRAF

Luka Anjeho		-	ICRAF Senior Technician

Walter Adongo	-	ICRAF Technician

Dr. Anja Boye		-	ICRAF Scientist

Robert Nyambati	-	KEFRI Scientist / PhD student

Agenda

- Progress report from KARI and ICRAF on activities in the Lower block of Yala

- Time frame for activities for on-going and up-coming activities

- Logistics

AD. 1

Each team informed the other team of their activities. KARI has started 4 nurseries so far in the Wangai area (South-gem). The plan is to establish 6 more nurseries within the coming weeks: 2 more in Wangai, 2 in North-east and 2 in North-west. That gives a total of 10 nurseries in Lower Yala before the long rains in March 2007.

ICRAF reported on the bio-physical survey – 11 clusters have been sampled and 5 are remaining. The timeframe is that by Nov 24th the 16 clusters will have been sampled.

The socio-economic team will start their survey around March 13th.

The tree-screening trials are being identified. So far 64 farmers are interested, but of these only 57 qualify for the study. The remaining 7 farms will be planted as woodlots. All 150 farmers have to have been identified and fenced by Dec.15th.

The meeting then discussed tree species and no. of trees to be planted for the various experiments:

Tree-screening trials (ICRAF):

| Trial |  |
| --- | --- |
| Screening trial | 25,000 |
| Woodlot | 5,000 |
| TOTAL | 30,000 |

Planting on boundaries and degraded areas (KARI):

| Trial |  |
| --- | --- |
| Boundaries |  |
| Degraded areas |  |
| TOTAL | 60,000 |

The breakdown gives a total of 90,000 seedlings that have to be raised before March 2007. Nursery groups can raise 30,000 seedlings for KARI, but KARI will need ICRAF to raise the remaining 30,000 seedlings. Therefore, the central nurseries need to raise 60,000 seedlings for Lower Yala before March 2007.

The following tree species were given by ICRAF and KARI:

| Tree species | ICRAF | KARI |
| --- | --- | --- |
| Grevilea robusta | 5,000 | 10,000 |
| Senna siamea | 3,000 | 2,000 |
| Markhamia lutea | 3,000 | 5,000 |
| Casuarina equisetofolia | 5,000 | 5,000 |
| Croton macrostachyus | 2,000 | 1,000 |
| Croton … | 3,000 | 2,000 |
| Maesopsis eminii | 2,000 | 2,000 |
| Albizia coriara |  | 2,000 |
| Zyzigium cumin |  | 2,000 |
| Prunus Africana |  | 1,000 |
| Calliandra spp. |  | 10,000 |
| Trichilia emetica |  | 5,000 |
| Gliricidia sepium |  | 5,000 |
| TOTAL | 23,000 | 50,000 |

Christi mentioned that is Katuk dam. The Koyombe umbrella group consisting of more than 50 members, are interested in the following species: Grevilea spp., Casuarina spp., Markhamia spp., Gliricidia spp., Albizia spp., Senna spp., Azadiracthta spp. (Neem), Teminalia spp., Acacia spp., Calliandra spp., and fruit trees.

This information should be given to the field officer of Nyando, Samuel Obaga

The tree-database at ICRAF Nairobi should be sourced for – Anja Boye to take the lead.

AD.2

With regards to the nurseries, Eva Gacheru is to make contact to the Social Service Department and the Forest office to identify groups suitable for the project. A meeting is to be held Friday Nov. 3rd where the project will identify the 4 groups for North-east and west.

The training for the 6 new nurseries is to start next week with Eva and Walter taking the lead. Walter will also draw a budget – KARI to meet expenses for on-farm nurseries and ICRAF to meet expenses for the central nurseries at ICRAF in Kisumu and KEFRI in Maseno. Need to consult Dr. Verchot on the 30,000 seedlings ICRAF is raising for KARI with regards to budgets.

AD.3

It was agreed upon that the logistics for the establishment of the nurseries is on KARI. ICRAF will provide the expertise and carry out the trainings. However, KARI is to participate in all trainings of farmer groups.

Eva and Walter to give logistics for the up-coming trainings.

Appendix 2 – Budget Nursery

From: Walter Adongo

To: Anya Boye

### Subject: Provisional work plan seedling production- GEF

Date: 3rd October 2006

The following meetings refer. The ICRAF staff meeting on 12th October, our meeting with KARI staff on 30th October and meeting with KEFRI staff in Maseno on 2nd November. To help us realize our objectives in seedling production, I wish to bring forth the following budget with the work plan

1. Provisional budget for the GEF

(a) Tree seed (Yellow indicates expenditure for ICRAF)

| Species | Quantity (Kgs) | Unit price (KES) | Total | Remarks |
| --- | --- | --- | --- | --- |
| 1. G. robusta | 5 | 3,000 | 15,000 | 2 kgs to the farmer groups |
| 2. C. equisetifolia | 2 | 3,000 | 6,000 | 1 kg to the farmer groups |
| 3. Syzygium cuminii | 4 | 1,000 | 4,000 |  |
| 4. Prunus africana | 3 | 2,000 | 6,000 |  |
| 5. Senna siamea | 5 | 1,000 | 5,000 | 2kgs to the farmer groups |
| 6. A. indica | 6 | 1,500 | 9,000 | 2 kgs to the farmer groups |
| 7. M.eminii | 20 | 300 | 6,000 | 10 kgs to the farmer groups |
| 8. T. emitica | 7 | 1,000 | 7,000 | 2 kgs to the farmer groups |
| 9. A. coriaria | 4 | 800 | 3,200 | 2 kgs to the farmer groups |
| 10. M. lutea | 2 | 1,000 | 2,000 | 2 kgs to the farmer groups |
| 11. W. ugandensis | 2 | 2,000 | 4,000 |  |
| 12. C. megalocarpus | 2 | 800 | 1,600 | To Lower Yala groups |
| 13. C. abssyinica | 2 | 1,500 | 3,000 | To Lower Yala groups |
| Total |  |  | 71,800 |  |

## Labour, materials, tools and equipment (Yellow indicates expenditure for ICRAF)

| ### Item | Details | ### Total (KES) | ### Remarks |
| --- | --- | --- | --- |
| Labour | ### Potting 200MD x KES 250 | 50,000 |  |
|  | Pricking out and maintenance 2 persons x KES 7,000 x 6 months | 84,000 |  |
| Poly tubes | 300kgs x KES 300 | 90,000 | 100 kgs to farmer groups |
| Soil | 4 lorries x KES 4,000 | 16,000 |  |
| # Sand | 2 lorries x KES 6,000 | 12,000 |  |
| Manure | 2 lorries x KES 5,000 | 10,000 |  |
| Wheel burrows | 20 x KES 3,000 | 60,000 | To farmer groups |
| Watering cans | 20 x KES 500 | 10,000 | To farmer groups |
| Shovels | 20 x KES 250 | 5,000 | To farmer groups |
| Pruning knives | 25 x KES 150 | 3,750 | To farmer groups |
| ### Total |  | 340,750 |  |

Note: The farmer groups are designated as Lower Yala and Nyando. It is envisaged that we shall have at least ten groups for each of the blocks.

Provisional work plan for the GEF seedling production and out planting

October 2006 – April 2007

| Activity | Time /Months |
| --- | --- |
| !. Seed sourcing | 1st week Nov. 2006 |
| 2. Soil, sand and manure collection | 1st week Nov. 2006 |
| 3. Potting | Nov-Dec. 2006 |
| 4. Pricking out | Nov.- Dec 2006 |
| 5. Maintenance | Continuous |
| 6. Farmers’ training for Lower Yala | 1st and 2nd weeks Nov. 2006 |
| 7. Follow-up trainings | 3rd week Nov. – Dec. 2006 |
| 8. Land preparation | Feb. – March 2007 |
| 9. Out planting | March – April 2007 |

Appendix 3

Minutes of the meeting held between KEFRI and ICRAF at KEFRI Maseno Research station on November 2nd, 2006

Present:

Dr. Mercy Gichora	-		Centre Director KEFRI Maseno

Mark Shiakamiri	-		Administrator KEFRI Maseno

Patrick Shamia	-		Stock supplies officer KEFRI Maseno

Walter Adongo	-		Field Technician ICRAF Kisumu

Dr. Anja Boye		-		Scientist ICRAF Kisumu

Agenda

- To assess offices and nursery space currently occupied by ICRAF

- To assess the future need for accommodation for ICRAF in Maseno

- To discuss the way forward

All participants except for the Centre Director toured the KEFRI Maseno station and looked at the offices and nursery space currently under ICRAF according to KEFRI.

| Specification | Current use | Future use for ICRAF | Agreement with KEFRI as per Nov. 2nd 2006 | ICRAF assets |
| --- | --- | --- | --- | --- |
| Seed store | Office for Technician Walter Adongo | Office for Technician Walter Adongo | ICRAF can keep this office | Computer, office furniture, several fridges and 1 freezer |
| Glass house | Empty | To be used for grafting of fruit trees | ICRAF can re-posses the space previously used, e.g. half the green house | None |
| Nursery store and ground space including seed beds etc. | Office for nursery foreman James Owek. Seed beds are empty | Office for nursery foreman James Owek. Approx. 60.000 seedlings to be produced before March 07 | ICRAF can re-possess the nursery and the surrounding area | Office: Many files from previous projects, old computers, shelves, tables and chairs |
| Solar dries for soil samples | Empty | Not sure | Can be used by other projects | None |
| Store No. 1 – IMPALA | Full of soil samples | None | To be reverted to KEFRI | Samples and 2 tables. Tables to be moved to Kisumu and samples to the seed store |
| Store No. 2 – samples from NM trials | Partly used by ICRAF to store soils from the NM trials | None | To be reverted to KEFRI | Samples to be discarded |
| Office No. 1 - Photocopy room | Box with photo copier | None | To be reverted to KEFRI | Photo copier to be moved to Kisumu |
| Office No. 2 - IMPALA | Empty | None | To be reverted to KEFRI | None |
| Other | Nematode lab | None | Has been handed over to KEFRI | 1 table to be moved to Kisumu |

The keys held by ICRAF for the IMPALA office and Store No. 1 is to be handed over to KEFRI. The soils kept in store No. 1 are to be moved to the seed lab within the coming 3-4 weeks. Office No. 1 and No.2 are to be handed over to KEFRI immediately.

It was mentioned by ICRAF that some more computers, office furniture etc. will be moved to Kisumu to be disposed of in the near future.

During the meeting, KEFRI mentioned that the glass house and the seed store are due for renovation.

According to the Centre Director, the formal agreement for the future collaboration is to be made by between the headquarters of KEFRI and ICRAF. All communications between KEFRI and ICRAF for the last six months was given to Dr. Anja Boye of ICRAF. It was also agreed upon that Dr. Boye is to formally inform KEFRI of the activities and staff that ICRAF intends to undertake and employ at the research station.