13th-17th Nov. report on Yala block.

| Date | Activities | Remarks |
| --- | --- | --- |
| 13/11/06 | Selected screening trials in Dienya East sub location. | Visited 8 farmers. All qualified for screening trials. |
| 14/11/06 | Selected screening trials in Dienya East sub location | Visited 13 farmers. 11 qualified for screening trials. 2 qualified for woodlot |
| 15/11/06 | Selected farmers in Uriri sub location | Visited 11 farmers. 10 farmers qualified for screening trials while 1 farmer qualified for woodlot. One farmer needs afforestation of assorted trees in addition to screening plot. Same applies to Uriri primary school. |
| 16/11/06 | Selected farmers in Wagai sub location | Visited 9 farmers. 8 qualified for screening trials. 1 qualified for afforestation of assorted trees as place already has trees. |

Problems encountered

Farmers in the sub locations covered this week namely Dienya, Uriri and Wagai had not been sensitized about the project at the sub location level. They admitted that they heard about the project at the locational meeting sometimes back and since then they’ve never heard about it again. They blame their local leaders for not passing them information in time. Village elders from Uriri and Wagai said when contacted that its when the Ass. Chiefs from these areas were preparing to hold a baraza on 16/11/06 to inform people about the project.

# Summery table as from last week on selections of screening trials in Yala block

|  | Total No. of farmers selected | No. of farmers for screening trials | No. of farmers for woodlots | Balance out of 150 farmers |
| --- | --- | --- | --- | --- |
| Last week (6th-10th Nov.) | 121 | 102 | 19 | 48 |
| Current week (13th-17th) | 162 | 139 | 23 | 11 |

Plans as from Nov.20th –30th 2006

- Plot measurements for preparation of holes

- Soil sampling using Y-frame method

- Plot characterization (biophysical measurements)

- Infiltration- 2 points per plot for 50 randomly selected plots