# Annex 4: Detailed Workplan and Budget for the Year 2005

| Objectives | Planned activities | Location | Inputs | Cost (USD) | Expected output | Monitorable indicators | Time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 Capacity building for community driven integrated Ecosystem Management: Improved capacity for local communities, farmer associations, and national institutions to formulate integrated ecosystem management plans | Community mobilization and sensitization | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | Meals for farmers for 1 day 1 block consists of 20 focal areas x 5 people = 100 for 4 blocks = 400 @$13.2 - Transport for 400 people @$6.6 Resource persons - Per diem for 5 persons @$40 for 4 days - Transport for 5 persons @$13.2 x 4 days - Stationery =$80 per block | 5,280 2,640 800 264 320 | Development of PAPs | - No. of sensitization meetings held and total attendance | Apr/Jun |
|  | PRA and PAP facilitators | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | - Per diem for 4 persons for 10 days @$40 for 4 blocks - 4 Key informers for 10 days @$20 x 4 blocks - Stationery | 6,400 3,200 400 | - PRA reports - Community Action Plans | - 8 PRA’s, 2 per block | Jun/Jul |
|  | - Workshops and training in focal areas | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | 30 participants per block of 4 - Transport =30 x $6.6x 4 - Per diem =30 x $13.2 - Conference facilities =$81x4 | 792 1,584 324 | - People trained on NRM | - No. of farmers, extension experts and service providers trained | Jul/Aug |
|  | - Workshops and training at the catchment level | - Nyando and Yala catchments | 60 participants (20 per block) - Transport =60x 2 daysx$13.2 - Per diem =60x2 days x $13.2 - Conference facilities etc. - Stationery Resource Persons - Per diem=6x2x$20 - Accomodation=6x2x$40 - Transport=6x$26 | 1,600 1,600 1,000 920 240 480 160 | - People trained on NRM | - No. of farmers, extension experts and service providers trained | Aug/Sep |
|  | - 3 days training for CBO’s development, once a year for every catchment | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | - Accommodation – 36x3x$40 - Per diem 36x30x$13.2 - Transport @36x$13.2 - Stationery etc - Miscellaneous charges ## Resource persons - Accommodation 6x3x$40 - Per diem 6x3x$20 - Transport 6x$26 | 4,320 1,430 475 1,000 835 720 360 160 | - Report on training | - Number of CBO’s trained | Aug/Sep |
|  | Development of extension messages | - Nyando - Yala - Nzoia catchments | - Publications - Media services - Purchase of digital camera | 5,000 3,000 800 | General awareness to the public | - No. of publications - No. of broadcasts and interviews with the electronic media | Apr/Dec |
|  | - Field staff costs | - Kisumu | - 4 field staff @24 staff months | 12,000 |  |  | Apr/Dec |
| 1.2 Enhanced capacity for carbon finance | - Purchase of lab equipment | - ICRAF laboratories | - Gas standard - Gas chamber - Disposables - Valves - Pumps | 5,000 12,000 5,000 1,800 300 | - Building capacity through purchase of equipment and training to measure carbon baseline | - Establishment of a national carbon monitoring and evaluation within the national research system | April |
|  | - Technical assistance – ICRAF | - ICRAF offices | - ICRAF staff - ICRAF scientist - Consultant for institutions study - Lab fees | 13,500 24,000 15,000 14,000 |  |  | Jul/Dec |
|  | - Equipment to KARI | - KARI | - Spectrophotometer - Water De-ionizer - Double Distillation Water Still - Flame Photometer - Hollow Cathode (AAS) lamps - Field GPS - Flatbed Colour Scanner - Wide Format Scanner - ArcGIS Software & licenses - Desktop computers –2 - HP Colour Laserjet printer - USB Flash Drives –4 - UPS-2 - Toshiba Laptop - Software & Licenses | 9,500 2,700 2,000 8,000 7,000 3,600 1,450 13,900 17,000 2,900 1,190 310 2,000 2,600 2,450 | - Building capacity for KARI through purchase of equipment and training to measure carbon baseline | - Establishment of a fully equipped national carbon monitoring and evaluation within the national research system | Apr |
| 2.0 Technical backstopping | (a) Seedlings and nurseries | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | - Seedlings for agroforestry species, medicinal trees and fruit trees for 4 blocks @13,050 | 52,200 | - Development of village nurseries to support agroforestry, medicinal trees and fruit trees - Development of land management interventions to sequester carbon in agricultural landscapes - Development of existing biodiversity resources | - Increased carbon sequestration through use of cover crops and tree planting - Increase in OM content in the soil where SLM technologies have been adopted - Improved nutritional levels the people in target areas - Decreased sediment load in surrounding water courses due to reduced erosion - Improved awareness and conservation of biodiversity at the community level | Apr/Dec |
|  | (b) Water pans and tools | - Katuk Odeyo | - 7 water pans @$1,286 - Excavation tools | 9,000 4,640 | No. of water pans Area | - Increased areas under vegetation | Apr/Dec |
|  | (c) Soil fertility management | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | - Fertilizers 35 bags per community for 20 communities = 35x20x$23.2 | 16,240 | Improved crop yields | - No. of bags of crop harvested | Apr/Dec |
|  | (d) Improved livestock | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | - 50 Starter bucks @$130 - 80 She goats (does) @$160 - 2,960 Local poultry @$5.3 | 6,500 12,800 15,700 | Improved livestock | - No. of improved goats and chicken | Apr/Dec |
|  | (e) Grants for future PAP activities | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | - Germplasm for 24 communities @2710 per community = 6x4x2,710 | 65,000 | - Improved fallows - Improved OM in the soil - Sustainable land management - Afforestation of hilly and badly degraded lands - Establishment of woodlots - Re-establishment of plants of economic value | - More healthy animals - Stabilized gully heads and sides - No. of well conserved farms with increased agricultural production - Clean water in the streams | Apr/Dec |
|  | (f) PAP research trials | - Nyando - Yala catchments | - Field trials in Nyando/Yala - Type 3 trials/demonstration plots | 20,000 4,000 |  |  | April/Dec |
|  | Technical Assistance to ICRAF | - Kisumu | - ICRAF scientist - ICRAF other staff | 24,000 13,500 |  |  | Apr/Dec |
|  | - Field staff costs | - Kisumu office | - 12 staff months | 6,000 |  |  | Apr/Dec |
|  | Biodiversity conservation: - Identification of critical habitat conservation strategies | - Katuk Odeyo - Londiani - Tiriki East - Cherangani | - (lumpsum amount) - Travel & accommodation - Transport and operating expenses - Stationery | 10,000 | - Thematic maps - Land use reports | - No. of reports | Apr/Dec |
|  | - Recurrent cost - Labour compensation | - Kisumu office | - Per diem & local travel | 10,000 |  |  | Apr/Dec |
|  |  | - Nyando - Yala | - To various deserving cases | 8,000 |  |  | Apr/Dec |
| 3. Monitoring and evaluation | - Socio- economics baseline surveys - Socio-economics consultant | - Yala catchment | - Per diem for 10 people @$40 x 40 days - Transport = 200km x 40 days x $ 0.6 - Stationery - Consulting time | 16,000 4,800 1,000 750 | Information on: - Household dynamics - Income levels - Livelihood strategies - Education levels - Gender - Strategies for soil management - Income diversification strategies - Technologies and problems identified | - No. of strategies at community level being undertaken - No. of new initiatives for soil management - No. of strategies for Agroforestry at community level - No of households involved in project implementation - Report | Apr/Aug October |
|  | (b) Bio physical baseline studies | - Yala catchment | - Accommodation for 169 days@$58.4 - Transport & operating for 44,000 kms @$0.564 - Labour costs - Soil analysis for 382 samples @$12.5 - GIS output & stationery | 9,870 12,409 1,550 4,781 11,450 | - Thematic maps - Soil & land use data - Soil & land use reports | - No. of reports | Jul/Sept |
|  | (c) Biodiversity Conservation - Biodiversity expert - Biodiversity baseline surveys | - Nyando - Yala - Nzoia catchments | - Consulting time (Lumpsum amount) - Transport & Accommodation - Transport & operating - Stationery | 8,000 15,000 | - Vegetation maps - Endangered species - Species of economic value - Hotspots | - Report - Report and Maps | Jul/Oct. |
|  |  | - KARI | - Data entry | 1,000 |  |  | Jul/Dec |
|  | - Field Survey equipment | - ICRAF | - NOx analyzer - Survey GPS - Gas chromatograph - Infra red gas analyzer - Misc. lab equipment | 25,000 4,800 31,000 35,000 12,000 |  |  | April |
|  | Technical assistance to ICRAF | - ICRAF | - ICRAF scientist time - Other ICRAF staff time - Lab costs - Imagery - Field team misc. expenses | 48,000 27,000 10,000 16,800 2,500 |  |  | Apr/Dec |