Kenya Agricultural Research Institute

Western Kenya Integrated Ecosystem Management Project (WKIEMP)

Project ID: P072981

2005/2006 Work plan and Budget

Contract Agreement between KARI and World Agroforestry Centre (ICRAF) for the backstopping of WKIEMP by ICRAF.

January 2006

Content										Page

- Background								3

- Objectives								5

- Activities and Time schedule					5

- Cost Estimates								7

- Reporting								8

- Publication of Results						9

- Publicity									9

- Payments								9

- Annex 1									10

- Background

The Kenya Agricultural Research Institute (KARI) and the World Agroforestry Centre (ICRAF) have been collaborating for many years. A Memorandum of Understanding (MoU) between the two institutes was signed in August 1989 and has been in force ever since. It is within the framework of this MoU that KARI has collaborated with ICRAF on the following projects:

  - National Agroforestry Research Programme funded by SIDA and implemented at KARI’s regional research centre in Embu.

  - Soil fertility recapitalization and replenishment pilot project, funded by various donors, including EU, Rockefeller foundation, the government of the Netherlands, implemented at the KEFRI centre at Maseno and the KARI regional research centres at Kakamega and Kisii.

  - Strategic soil fertility recapitalization research project, funded by the World Bank through KARI’s NARP II project, implemented in Western Kenya.

  - The African Highlands Initiative implemented at KARI regional research centre Embu and the KEFRI centre at Maseno and supported be various donors.

  - Investigations to establish the magnitude of potassium deficiencies in Kenya with a view of developing appropriate soil fertility management recommendations to combat potassium related constraints to crop production. This project was implemented at the National Agricultural Research Laboratories and supported by the EU under the Agriculture/Livestock Research Support Programme Phase II

  - Short term consultancy on the improvement of laboratory services at NARL with practical recommendations and outputs on soil critical nutrient levels to be used in developing crop specific fertilizer recommendations, also implemented with the support from the EU under ARSP II

In addition, KARI has collaborated with ICRAF on an ad hoc basis on various activities such as: (i) Soil Fertility Initiative, which is a sub-Saharan Africa initiative aiming at promoting improved soil fertility management; (ii) training of several KARI scientists using ICRAF facilities and expertise; and (iii) offering joint courses, in which clients i.e. NGO’s extension staff and farmers are trained on various technologies. These joint activities have been very successful and have generated a range of technologies, which have been widely adopted by farmers.

A new project; Western Kenya Integrated Ecosystem Management Project (WKIEMP) has been initiated with support from the World Bank for implementation. The project, which became effective in July 2005, seeks to improve the productivity and sustainability of land use systems in selected watersheds in the Nzoia, Yala and Nyando river basins through adoption of an integrated ecosystem management approach. In order to achieve this the project will: (i) support on-and off-farm conservation strategies; and (ii) improve the capacity of local communities and institutions to identify, formulate and implement integrated ecosystem management activities (including both on-and off-farm land use planning) capturing local global environmental benefits. The project based in Kisumu would achieve its objectives through a community driven development process whereby communities would decide on resources for infrastructure investments, technical assistance and implementation of ecosystem management activities.

KARI has collaborated with ICRAF in the generation of baseline information used in the Project Appraisal Document (PAD). KARI is therefore requesting ICRAF to further continue this backstopping in the 2005/2006 Work plan with the specific objectives of building capacity of KARI scientists, other local institutions, and communities to manage carbon assets including the establishment of a system to monitor and evaluate the biophysical impact of project activities, particularly the impact on net carbon absorption.

It has also been realized that ICRAF is already undertaking on-farm experiments involving Participatory Action Plans (PAPs) by farmers at several sites within the target river basins. KARI has therefore requested ICRAF to provide additional backstopping of this activity within the framework of WKIEMP.

2.	Objectives

The main objectives of this backstopping are to assist KARI to:

      - Establish interventions that mitigate land degradation

      - Evaluate and document the potential of different tree species to sequester carbon on degraded land

      - Evaluate options for river bank protection

      - Establish interventions that sequester carbon on agricultural systems

      - Establish PAP intervention plots at several sites

      - Establish a system for monitoring and evaluating changes in carbon stocks.

      - Build capacity of KARI staff, other local institutions and communities to actively undertake monitoring and evaluation of changes in carbon stocks.

3.	Activities and Time schedule

3.1	Activities and inputs

The timeframe for implementation of the activities to meet the above objectives will be as shown in Table 1.

Specifically the backstopping will support the following activities:

- Develop a manual for the methods of measuring and monitoring carbon stocks

- Develop a manual for the methods of measuring non CO2 Green House Gases

#### Train KARI Scientists on methods of measuring carbon stocks including data collection, laboratory procedures, monitoring and statistical analysis

- Train KARI Scientists on measurements of non CO2 Green House Gases including data collection, laboratory procedures, monitoring and statistical analysis

- Establish and document training needs of various institutions in Western Kenya on carbon trade

- Establish village tree nurseries to support Agro forestry

- Establish and implement species screening trials

- Increase tree cover on severely degraded sites

- Establish and document the status of the environment in the initial 4 blocks including satellite, biophysical and socio-economic baseline data

- Develop a manual for the project Monitoring and Evaluation (M & E) procedures

- Provide hands on training to KARI scientists on M & E procedures

The input needed from ICRAF will be 26 person months of scientist time.

3.2	 Time schedule

Table 1: Timeframe

| Activity | 2005 |  | 2006 |  |
| --- | --- | --- | --- | --- |
|  | Quarter |  |  |  |
|  | 3 | 4 | 1 | 2 |
| I Develop a manual for the methods of measuring and monitoring carbon stocks | X | X | X | X |
| ### II Develop a manual for the methods of measuring non CO2 Green House Gases | X | X | X | X |
| ### 111 Train KARI Scientists on methods of measuring carbon stocks including data collection, laboratory procedures, monitoring and statistical analysis | X | X | X | X |
| ### 1V Train KARI Scientists on measurements of non CO2 Green House Gases including data collection, laboratory procedures, monitoring and statistical analysis |  |  | X | X |
| ### V Establish and document training needs of various institutions in Western Kenya on carbon trade | X | X | X |  |
| VI Establish village tree nurseries to support Agro forestry | X | X | X | X |
| ### VII Establish and implement species screening trials | X | X | X | X |
| ### VII Increase tree cover on severely degraded sites | X | X | X | X |
| ### IX Establish and document the status of the environment in the initial 4 blocks including satellite, biophysical and socio-economic baseline data | X | X | X | X |
| ### X Develop a manual for the project Monitoring and Evaluation (M & E) procedures | X | X | X | X |
| ### XI Provide hands on training to KARI scientists on M & E procedures |  |  | X | X |

The detailed work plan for the activities as agreed upon during planning meetings between KARI staff and ICRAF is attached in Annex 1.

This work plan will become effective with the endorsement of the annual work plan and cost estimate of WKIEMP for 2005/2006 but not before 1 July 2005.

4.	Cost Estimate

The cost estimate for the activities outlined above are indicated in Table 2 and cover only activities to be funded under the WKIEMP 2005/2006 Work plan.

Table 2: Cost estimate

| Component | Item | Cost US$ |  |
| --- | --- | --- | --- |
| 1.2: Enhanced capacity for carbon financing (Interventions to mitigate land degradation, potential of trees to sequester carbon, options for river bank protection, interventions to sequester carbon on agricultural land) | Technical Assistance | - | 66,500 |
|  | Equipment | 24,100 | - |
| 2.0: Technical Backstopping (Establishment of PAP intervention plots (trees stocking plots) | Field trials | - | 24,000 |
|  | Technical assistance | - | 37,500 |
| 3.0 M&E (Improved capacity for monitoring carbon stocks and a net-net accounting of GHC accumulation) | Technical assistance | - | 104,300 |
|  | Equipment | 107,800 | - |
| Total |  | 131,900 | 232,300 |

5.	Reporting

ICRAF shall provide the following reports to KARI, which amongst others shall serve KARI as the basis for the preparation of consolidated project reports to the World Bank:

- All socio-economic and biophysical baseline reports initially on 2 blocks on target river basins (Nyando, Yala, and Nzoia).

- A manual for the methods of measuring and monitoring carbon stocks

- A manual for the methods of measuring non CO2

- Report on  training needs of various institutions in Western Kenya on carbon trade

- A manual for the project Monitoring and Evaluation (M & E) procedures

- Detailed sub proposals giving problem statements, rationale, materials and methods and expected outputs for each of the sub-objectives listed in section 2 above.

- Quarterly reports to give detailed insight on the progress of the sub-projects being executed as proposed in (ii) above. Each quarter report must be received by KARI latest the last day of the quarter to allow timely reporting by KARI to the World Bank

- Annual reports covering a calendar year of the project (latest one month after the end of the calendar year being reported)

- A Final report covering the entire project duration (before the formal end date of the project) giving the results, conclusions and recommendations for each of the sub-projects proposed in (ii).

- Any other materials e.g., bulletins, manuals, posters being outputs of the sub-projects.

NB: All reports and developed packages have to be submitted to KARI as hard copy (three copies) and as electronic file.

6.	 Publication of results

- Both KARI and ICRAF shall not publish any information related to the project being contracted without informing the other institution well in advance before the material is submitted for publication with a view of giving an opportunity to the other institution to participate.

- After publication, each institute shall provide the other institution with at least three copies of such publications and shall subsequently supply as many copies as the other institution may reasonably request.

7.	 Publicity

In case of communication to the press including press releases, both KARI and ICRAF shall inform the other institution in writing within a reasonable time to allow participation. In such media releases both parties shall endeavor to portray both institutions as partners in the implementation.

8.	Payments

Upon signature of this work plan by both parties, payments will be made to ICRAF in accordance with the World Bank accounting procedures. The first payment to ICRAF will be a quarterly allocation as provide in this work plan, with the next allocation being made the next quarter after accounting for the first disbursement. The Payments for subsequent work plans will be made upon submission of satisfactory reports by ICRAF to KARI.

9. Equipment

ICRAF shall provide KARI with specifications for equipment and justification for single sourcing after which KARI shall prepare the bidding documents as per laid down GoK and World Bank procurement regulations. KARI shall purchase the equipment after obtaining the necessary clearances from the World Bank and hand over the equipment to ICRAF. The equipment purchased by under this agreement shall revert to KARI at the end of the project.

Signed on behalf of the Kenya Agricultural Research Institute (KARI)

Director KARI

Date: ………………………………

Signed on behalf of the World Agroforestry Centre (ICRAF)

Director General ICRAF

Date: ……………………………….

9. Annex 1

Component 1.2: Enhanced capacity for developing carbon finance proposals.

| Activity | Indicators | Means of Verification (MoVs) | TIMEFRAME |  |  |  |  |  |  |  |  |  |  |  |  | Responsible | Partners | Resources required | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2005 |  |  |  |  |  | 2006 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J |  |  |  |  |
| 1.2 Develop capacity for carbon finance administration and market development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 Train 1 KARI scientists on Carbon Stocks | 1 PhD by end of project period | PhD Thesis |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Shepherd | Universities | Staff time |  |
| 1.2.2 Train 1 KARI scientist on non C02 GHG | 1 PhD by end of project period | PhD Thesis |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Verchot | Universities | Staff time Student stipend Uni. fees |  |
| 1.2.3 Study on Western Kenya Institution s on carbon trade | Institutional status and capacity building needs identified by February 2006 | Report |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Verchot Shepherd Awiti | NALEP | Staff time Transport Lab. costs |  |
| 1.2.4 Develop procedures for measurement and monitoring of carbon stocks | Field measurement and analysis manuals ready by June 2006 | Manuals Progress report |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Shepherd | Universities | Staff time |  |
| 1.2.5 Build capacity for carbon and non-CO2 GHG accounting | Two students complete their PhD studies by 2010 | PhD thesis |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Verchot | Universities | Staff time Student stipend Uni. fees | Subject to funding and acceptance of proposal |
| 1.2.6 Hands-on training on carbon and non-CO2 GHG data collection, laboratory procedures analysis, monitoring and statistical interpretation. | Training programme started by Dec 2005 No. of KARI and other staff trained | Training progress report |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Verchot Shepherd Awiti | NALEP KEFRI KARI/ICRAF | Staff time Transport Lab. costs | Concurrent with M&E training activities (see Component 3) |

Component 2: Scaling up and financing IEM interventions.

| Activity | Indicators | MoV | TIMEFRAME |  |  |  |  |  |  |  |  |  |  |  |  | Responsible | Partners | Resources required | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2005 |  |  |  |  |  | 2006 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J |  |  |  |  |
| 2.1 Develop village nurseries to support Agroforestry | No. of new nurseries established No. and types of seedlings produced. | Field reports Project Progress reports (quarterly and annually) |  |  |  |  |  |  |  |  |  |  |  |  |  | Awiti FOs | KEFRI NALEP VI Agroforestry | Staff time Transport Seedling and nursery materials Casual labour |  |
| 2.2 Establish species screening trials | No. of geo-referenced reps. No. tree seedlings planted | Progress reports |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Awiti FOs | KEFRI | Staff time Transport Seedlings & nursery materials |  |
| 2.3 Increase tree cover on severely degraded sites | Area protected and/or no. of seedlings planted | Progress reports |  |  |  |  |  |  |  |  |  |  |  |  |  | Awiti Walsh FOs | NALEP | Staff time Transport Seedlings & nursery materials Casual labor costs |  |

Component 3: Establishing a monitoring and evaluation system.

| Activity | Indicators |  | MoV | TIMEFRAME |  |  |  |  |  |  |  |  |  |  |  |  | Responsible | Partners | Resources required | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2005 |  |  |  |  |  | 2006 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J |  |  |  |  |
| 3.1 Establish the status of environment in the 4 blocks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 Process satellite data | satellite images for the 4 blocks available by Dec 2005 and analyzed by June 2006 |  | - Image archive - GIS databases Ground sampling plans |  |  |  |  |  |  |  |  |  |  |  |  |  | Awiti Walsh Awiti | KARI NALEP | - Quick Bird satellite images - Staff time | Actual acquisition subject to cloud cover |
| 3.1.2 Establish a biophysical baseline | Baselines available by: Katuk-odeyo and Yala by Dec 2005 Londiani and Nandi by June 2006 |  | GIS database Report Website |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Awiti Shepherd FO’s PC | NALEP NEMA | Staff time Transport Laboratory costs Casual labor costs | - Analysis timeline subject to image acquisition. 1 month per block (concurrent with socioeconomic surveys) |
| 3.1.3 Develop an integrated pest management plan | A plan developed by Dec 2005 for first two blocks and June 2006 for the other two blocks |  | IPM plan documents |  |  |  |  |  |  |  |  |  |  |  |  |  | Consultant costs | PC | Starting Oct – June 2006 |  |
| 3.1.5 Establish socio-economic baseline survey | Socio-economic baseline available by: Katuk-odeyo and Yala by Dec 2005 Londiani and Nandi by June 2006 |  | Progress report available by Jan 2006 and Technical report by June 2006 GIS database |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Awiti Shepherd FOs M&E socio-economics | NALEP | Staff time Casual labour Transport | 1 month per block concurrent with biophysical surveys. |
| 3.2 Establish a monitoring system for greenhouse gases (GHG) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 Install and calibrate Equipment for measuring non CO2 GHG’s | Equipment in place and functioning by April 2006 | Kisumu laboratory facilities operational |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Verchot 3 months Consultant | KARI | - Staff time - Consultancy costs - Equipment costs Laboratory costs | Single sourcing owing to nature of equipment |
| 3.2.2 Develop manual for project M&E procedures | Manuals ready by June 2006 | Quality M&E manuals Websites |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Verchot Shepherd Awiti PCO | KARI NALEP | Staff time |  |
| 3.3.3 Hands-on training on M&E procedures | # of persons trained and certified | Training reports Project progress report |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Walsh Verchot Shepherd Awiti PCO FOs | KARI | Staff time Transport Lab. costs | Concurrent with carbon accounting training activities (see Component 1.2) |