## Sheet1
Objectives | Planned activities | Location | Inputs | Cost | Expected output | Monitorable indicators | Time
(USD)
1.1 Capacity building for community driven integrated Ecosystem Management: Improved capacity for local communities, farmer associations, and national institutions to formulate integrated ecosystem management plans | Community mobilization and sensitization | · Katuk Odeyo | Meals for farmers for 1 day |  | Development of PAPs | - No. of sensitization meetings held and total attendance | Apr/Jun
|  | · Londiani | 1 block consists of 20 focal areas x 5 people = 100 for 4 blocks = 400 @$13.2
|  | · Tiriki East | - Transport for 400 people @$6.6 | 5280
|  | · Cherangani | Resource persons
|  |  | - Per diem for 5 persons @$40 for 4 days | 2640
- Transport for 5 persons @$13.2 x 4 days
- Stationery =$80 per block
800
264
320
| PRA and PAP facilitators | · Katuk Odeyo | - Per diem for 4 persons for 10 days @$40 for 4 blocks | 6400 | - PRA reports | - 8 PRA’s, 2 per block | Jun/Jul
|  | · Londiani | - 4 Key informers for 10 days @$20 x 4 blocks |  | - Community Action Plans
|  | · Tiriki East | - Stationery
|  | · Cherangani |  | 3200
400
| - Workshops and training in focal areas | · Katuk Odeyo | 30 participants per block of 4 |  | - People trained on NRM | - No. of farmers, extension experts and service providers trained | Jul/Aug
|  | · Londiani | - Transport =30 x $6.6x 4 | 792
|  | · Tiriki East | - Per diem =30 x $13.2 | 1584
|  | · Cherangani | - Conference facilities =$81x4 | 324
| - Workshops and training at the catchment level | · Nyando and Yala catchments | 60 participants (20 per block) |  | - People trained on NRM | - No. of farmers, extension experts and service providers trained | Aug/Sep
|  |  | - Transport =60x 2 daysx$13.2 | 1600
|  |  | - Per diem =60x2 days x $13.2 | 1600
|  |  | - Conference facilities etc. | 1000
|  |  | - Stationery | 920
Resource Persons
|  |  | - Per diem=6x2x$20 | 240
|  |  | - Accomodation=6x2x$40 | 480
|  |  | - Transport=6x$26 | 160
| - 3 days training for CBO’s development, once a year for every catchment | · Katuk Odeyo | - Accommodation – 36x3x$40 | 4320 | - Report on training | - Number of CBO’s trained | Aug/Sep
|  | · Londiani | - Per diem 36x30x$13.2 | 1430
|  | · Tiriki East | - Transport @36x$13.2 | 475
|  | · Cherangani | - Stationery etc | 1000
|  |  | - Miscellaneous charges | 835
Resource persons
|  |  | - Accommodation 6x3x$40 | 720
|  |  | - Per diem 6x3x$20 | 360
|  |  | - Transport 6x$26 | 160
| Development of extension messages | · Nyando | - Publications | 5000 | General awareness to the public | - No. of publications | Apr/Dec
|  | · Yala | - Media services | 3000 |  | - No. of broadcasts and interviews with the electronic media
|  | · Nzoia catchments | - Purchase of digital camera | 800
| - Field staff costs | · Kisumu | - 4 field staff @24 staff months | 12000 |  |  | Apr/Dec
1.2 Enhanced capacity for | - Purchase of lab equipment | · ICRAF laboratories | - Gas standard | 5000 | - Building capacity through purchase of equipment and training to measure carbon baseline | - Establishment of a national carbon monitoring and evaluation within the national research system | April
carbon finance |  |  | - Gas chamber | 12000
|  |  | - Disposables | 5000
|  |  | - Valves | 1800
|  |  | - Pumps | 300
| - Technical assistance – ICRAF | · ICRAF offices | - ICRAF staff | 13500 |  |  | Jul/Dec
|  |  | - ICRAF scientist | 24000
|  |  | - Consultant for institutions | 15000
|  |  | study | 14000
- Lab fees
| - Equipment to KARI | · KARI | - Spectrophotometer | 9500 | - Building capacity for KARI through purchase of equipment and training to measure carbon baseline | - Establishment of a fully equipped national carbon monitoring and evaluation within the national research system | Apr
|  |  | - Water De-ionizer | 2700
|  |  | - Double Distillation Water Still | 2000
|  |  | - Flame Photometer | 8000
|  |  | - Hollow Cathode (AAS) lamps | 7000
|  |  | - Field GPS | 3600
|  |  | - Flatbed Colour Scanner | 1450
|  |  | - Wide Format Scanner | 13900
|  |  | - ArcGIS Software & licenses | 17000
|  |  | - Desktop computers –2 | 2900
|  |  | - HP Colour Laserjet printer | 1190
|  |  | - USB Flash Drives –4 | 310
|  |  | - UPS-2 | 2000
|  |  | - Toshiba Laptop | 2600
|  |  | - Software & Licenses | 2450
2.0 Technical backstopping | (a) Seedlings and nurseries | · Katuk Odeyo | - Seedlings for agroforestry species, medicinal trees and fruit trees for 4 blocks @13,050 | 52200 | - Development of village nurseries to support agroforestry, medicinal trees and fruit trees | - Increased carbon sequestration through use of cover crops and tree planting | Apr/Dec
|  | · Londiani |  |  | - Development of land management interventions to sequester carbon in agricultural landscapes | - Increase in OM content in the soil where SLM technologies have been adopted
|  | · Tiriki East |  |  | - Development of existing biodiversity resources | - Improved nutritional levels the people in target areas
|  | · Cherangani |  |  |  | - Decreased sediment load in surrounding water courses due to reduced erosion
- Improved awareness and conservation of biodiversity at the community level
| (b) Water pans and tools | · Katuk Odeyo | - 7 water pans @$1,286 | 9000 | No. of water pans | - Increased areas under vegetation | Apr/Dec
|  |  | - Excavation tools | 4640 | Area
| (c) Soil fertility management | · Katuk Odeyo | - Fertilizers |  | Improved crop yields | - No. of bags of crop harvested | Apr/Dec
|  | · Londiani | 35 bags per community for 20 communities = 35x20x$23.2
|  | · Tiriki East |  | 16240
· Cherangani
| (d) Improved livestock | · Katuk Odeyo | - 50 Starter bucks @$130 | 6500 | Improved livestock | - No. of improved goats and chicken | Apr/Dec
|  | · Londiani | - 80 She goats (does) @$160 | 12800
|  | · Tiriki East | - 2,960 Local poultry @$5.3 | 15700
· Cherangani
| (e) Grants for future PAP activities | · Katuk Odeyo | - Germplasm for 24 communities @2710 per community = 6x4x2,710 | 65000 | - Improved fallows | - More healthy animals | Apr/Dec
|  | · Londiani |  |  | - Improved OM in the soil | - Stabilized gully heads and sides
|  | · Tiriki East |  |  | - Sustainable land management | - No. of well conserved farms with increased agricultural production
|  | · Cherangani |  |  | - Afforestation of hilly and badly degraded lands | - Clean water in the streams
- Establishment of woodlots
- Re-establishment of plants of economic value
| (f) PAP research trials | · Nyando | - Field trials in Nyando/Yala | 20000 | - | - | April/Dec
· Yala catchments
|  |  | - Type 3 trials/demonstration plots | 4000
| Technical Assistance to ICRAF | · Kisumu | - ICRAF scientist | 24000 | - | - | Apr/Dec
|  |  | - ICRAF other staff | 13500
| - Field staff costs | · Kisumu office | - 12 staff months | 6000 | - | - | Apr/Dec
| Biodiversity conservation: | · Katuk Odeyo
| - Identification of critical habitat conservation strategies | · Londiani
|  | · Tiriki East | - (lumpsum amount) | 10000 | - Thematic maps | - No. of reports | Apr/Dec
|  | · Cherangani | - Travel & accommodation |  | - Land use reports
- Transport and operating expenses
- Stationery
| - Recurrent cost | · Kisumu office | - Per diem & local travel | 10000 | - | - | Apr/Dec
| - Labour compensation | · Nyando | - To various deserving cases | 8000 | - | - | Apr/Dec
· Yala
3. Monitoring and evaluation | (a) Socio- economics baseline surveys | · Yala | - Per diem for 10 people @$40 x 40 days |  | Information on: | - No. of strategies at community level being undertaken | Apr/Aug
|  | catchment | - Transport = 200km x 40 days x $ 0.6 | 16000 | - Household dynamics | - No. of new initiatives for soil management
|  |  | - Stationery |  | - Income levels | - No. of strategies for Agroforestry at community level
|  |  |  | 4800 | - Livelihood strategies | - No of households involved in project implementation
|  |  |  | 1000 | - Education levels
- Gender
- Strategies for soil management
- Income diversification strategies
- Report
- Technologies and problems identified
- Socio-economics consultant
- Consulting time
|  |  |  | 750 |  |  | October
| (b) Bio physical baseline studies | · Yala catchment | - Accommodation for 169 days@$58.4 |  | - Thematic maps | - No. of reports | Jul/Sept
|  |  | - Transport & operating for 44,000 kms @$0.564 | 9870 | - Soil & land use data
|  |  | - Labour costs |  | - Soil & land use reports
|  |  | - Soil analysis for 382 samples @$12.5 | 12409
|  |  | - GIS output & stationery | 1550
4781
11450
| (c) Biodiversity Conservation | · Nyando
· Yala
| - Biodiversity expert | · Nzoia catchments
|  |  | - Consulting time | 8000 | - Vegetation maps | - Report | Jul/Oct.
| - Biodiversity baseline surveys |  |  |  | - Endangered species
- Species of economic value
|  |  | (Lumpsum amount) | 15000 | - Hotspots | - Report and Maps
- Transport & Accommodation
- Transport & operating
- Stationery
|  | · KARI | - Data entry | 1,000 |  | - | Jul/Dec
| - Field Survey equipment | · ICRAF | - NOx analyzer | 25,000 |  | - | April
|  |  | - Survey GPS | 4,800
|  |  | - Gas chromatograph | 31,000
|  |  | - Infra red gas analyzer | 35,000
|  |  | - Misc. lab equipment | 12,000
| Technical assistance to ICRAF | · ICRAF | - ICRAF scientist time | 48,000 |  | - | Apr/Dec
|  |  | - Other ICRAF staff time | 27,000
|  |  | - Lab costs | 10,000
|  |  | - Imagery | 16,800
|  |  | - Field team misc. expenses | 2,500