Kenya Agricultural Research Institute

Western Kenya Integrated Ecosystem Management Project (WKIEMP)

Project ID: P072981

2005/2006 Workplan and Budget

Contract Agreement between KARI and World Agroforestry Centre (ICRAF) for the backstopping of WKIEMP by ICRAF.

August 2005

Content										Page

- Background								3

- Objectives								4

- Activities and Time schedule					5

- Cost Estimates								6

- Reporting								7

- Publication of Results						7

- Publicity									8

- Payments								8

- Annex 1									9

.

- Background

The Kenya Agricultural Research Institute (KARI) and the World Agroforestry Centre (ICRAF) have been collaborating for many years. A Memorandum of   Understanding (MoU) between the two institutes was signed in August 1989 and has been in force ever since. It is within the framework of this MoU that KARI has collaborated with ICRAF on the following projects:

  - National Agroforestry Research Programme funded by SIDA and implemented at KARI’s regional research centre in Embu.

  - Soil fertility recapitalization and replenishment pilot project, funded by various donors, including EU, Rockefeller foundation, the government of the Netherlands, implemented at the KEFRI centre at Maseno and the KARI regional research centres at Kakamega and Kisii.

  - Strategic soil fertility recapitalization research project, funded by the World Bank through KARI’s NARP II project, implemented in Western Kenya.

  - The African Highlands Initiative implemented at KARI regional research centre Embu and the KEFRI centre at Maseno and supported be various donors.

  - Investigations to establish the magnitude of potassium deficiencies in Kenya with a view of developing appropriate soil fertility management recommendations to combat potassium related constraints to crop production. This project was implemented at the National Agricultural Research Laboratories and supported by the EU under the Agriculture/Livestock Research Support Programme Phase II

  - Short term consultancy on the improvement of laboratory services at NARL with practical recommendations and outputs on soil critical nutrient levels to be used in developing crop specific fertilizer recommendations, also implemented with the support from the EU under ARSP II

In addition, KARI has collaborated with ICRAF on an ad hoc basis on various activities such as: (i) Soil Fertility Initiative, which is a sub-Saharan Africa initiative aiming at promoting improved soil fertility management; (ii) training of several KARI scientists using ICRAF facilities and expertise; and (iii) offering joint courses, in which clients i.e. NGO’s extension staff and farmers are trained on various technologies. These joint activities have been very successful and have generated a range of technologies, which have been widely adopted by farmers.

A new project; Western Kenya Integrated Ecosystem Management Project (WKIEMP) has been initiated with support from the World Bank for implementation. The project, which became effective in July 2005, seeks to improve the productivity and sustainability of land use systems in selected watersheds in the Nzoia, Yala and Nyando river basins through adoption of an integrated ecosystem management approach. In order to achieve this the project will: (i) support on-and off-farm conservation strategies; and (ii) improve the capacity of local communities and institutions to identify, formulate and implement integrated ecosystem management activities (including both on-and off-farm land use planning) capturing local global environmental benefits. The project based in Kisumu would achieve its objectives through a community driven development process whereby communities would decide on resources for infrastructure investments, technical assistance and implementation of ecosystem management activities.

KARI has collaborated with ICRAF in the generation of baseline information used in the Project Appraisal Document (PAD). KARI is therefore requesting ICRAF to further continue this backstopping in the 2005/2006 Workplan with the specific objectives of building capacity of KARI scientists, other local institutions, and communities to manage carbon assets including the establishment of a system to monitor and evaluate the biophysical impact of project activities, particularly the impact on net carbon absorption.

It has also been realized that ICRAF is already undertaking on-farm experiments involving Participatory Action Plans (PAPs) by farmers at several sites within the target river basins. KARI has therefore requested ICRAF to provide additional backstopping of this activity within the framework of WKIEMP.

2.      Objectives

The main objectives of this backstopping are to assist KARI to:

      - Establish interventions that mitigate land degradation

      - Evaluate and document the potential of different tree species to sequester carbon on degraded land

      - Evaluate options for river bank protection

      - Establish interventions that sequester carbon on agricultural systems

      - Conduct special studies on C sequestration and non-CO2 greenhouse emissions and sinks from different land-use activities

      - Establish PAP intervention plots at several sites

      - Establish a system for monitoring and evaluating changes in carbon stocks.

      - Build capacity of KARI staff, other local institutions and communities to actively undertake monitoring and evaluation of changes in carbon stocks.

3.      Activities and Time schedule

3.1    Activities and inputs

The timeframe for implementation of the activities to meet the above objectives will be as shown in Table 1.

Specifically the backstopping will support the following activities:

#### -Development of PAPs  and PAP intervention plots will be ongoing during the year and will begin in the first quarter of the project activities.

#### Activities for mitigation of land degradation will be ongoing during the year and will begin in the first quarter of the project activities.

#### River-bank protection activities will be ongoing during the year and will begin in the first quarter of the project activities.

#### Data collection for the monitoring and evaluation system will be ongoing during the year and will begin in the first quarter of te project activities.

- ICRAF will work with KARI procurement to purchase the equipment for the special study on C sequestration and non-CO2 greenhouse gas emissions and sinks will begin in the first quarter of the project.  Laboratory activities will begin as soon as equipment ahs arrived.  Field activities will begin during the long rains of 2006

- The institutions study will begin during the second quarter of 2005

- -

- -

- -

The input needed from ICRAF will include 8 person months of senior scientist time and 18 months of other staff time.

3.2    Time schedule

Table 1: Timeframe

| Activity 2005 2006 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Quarter | 3 | 4 | 1 | 2 |
| ### I PAPS | X | X | X | X |
| ### II Activities for mitigation of land degradation | X | X | X | X |
| ### III River bank protection activities | X | X | X | X |
| ### IV Data collection for monitoring and evaluation | X | X | X | X |
| ### V Special study on GHGs | X | X | X | X |
| ### VI Institutions study |  |  | X | X |
| ### VII + + + |  |  |  |  |

The detailed workplan for the activities as agreed upon during planning meetings between KARI staff and ICRAF is attached in Annex 1.

This workplan will become effective with the endorsement of the annual workplan and cost estimate of WKIEMP for 2005/2006 but not before 1 July 2005.

4.      Cost Estimate

The cost estimate for the activities outlined above are indicated in Table 2 and cover only activities to be funded under the WKIEMP 2005/2006 Workplan.

Table 2: Cost estimate

| Activity/Item | Ksh |
| --- | --- |
| I |  |
| II |  |
| III |  |
| IV |  |
| V |  |
| VI |  |
| VII + + + |  |

5. Reporting

ICRAF shall provide the following reports to KARI, which amongst others shall serve KARI as the basis for the preparation of consolidated project reports to the World Bank:

(i) All socio-economic and biophysical baseline reports for three river basins (Nyando, Yala, and Nzoia).

(ii) Detailed proposals giving problem statements, rationale, materials and methods and expected outputs for each of the sub-objectives listed in section 2 above.

(iii) Short quarterly reports on activities to give detailed insight on the progress of the sub-projects being executed as proposed in (ii) above. Each quarter report must be received by KARI at the latest one month following the last day of the quarter to allow timely reporting by KARI to the World Bank

(iv) Annual activity and financial reports covering a calendar [are you sure you want this on a calendar year basis and not an annual project cycle year?] year of the project (latest one month after the end of the calendar year being reported)

(v) A Final report covering the entire project duration (before the formal end date of the project) giving the results, conclusions and recommendations for each of the sub-projects proposed in (ii).

(vi) Any other materials e.g, bulletins, manuals, posters being outputs of the sub-projects.

NB: All reports and developed packages have to be submitted to KARI as hard copy ( three copies) and as electronic file.

6. Publication of results

- ICRAF shall inform KARI of any publications generated from this work

- ICRAF shall provide three copies of such publications to KARI and shall subsequently supply as many copies as KARI may reasonably request.

7. Publicity

ICRAF shall not make any communication to the press, or any public media, about the progress of the sub-projects or results without prior written agreement with KARI. [ not sure about this one]

9.Payments

Upon signature of this workplan by both parties, payments will be made to ICRAF in accordance with the World Bank accounting procedures. The first payment will be the total amount as provide in this workplan by the ICRAF. Payments for subsequent workplans will be made upon submission of satisfactory reports by ICRAF to KARI.

Signed on behalf of the Kenya

Agricultural research institute(KARI)             ……………………………

Director KARI

Date: …………………………..

Signed on behalf of the World Agroforestry

Centre (WAC)

……………………………………

Director General ICRAF

Date: ………………………………

10. Annex 1

Below is the specific activities under WKIEMP WP 2005/2006 for which backstopping by ICRAF is contracted

| ANNUAL WORKPLAN FOR WKIEMP | Result No 1: Capacity of communities and local institutions to undertake IEM strengthened | Planning Period: 10/2005 – 6/2006 Prepared: Sep 2005 |
| --- | --- | --- |

| NO. ACTIVITY | INDICATOR/MILESTONE | MEANS OF VERIFICATION | 2005/2006 |  |  |  |  |  |  |  |  |  |  |  | RESPONSIBILITY |  | RESOURCES | BUDGET (KSH) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | J | A | S | O | N | D | J | F | M | A | M | J |  |  |  |  |
| 1.1 Capability of local communities to formulate, write and submit Participatory Action Plans (PAPs) proposals for funding enhanced 1.1.1 Facilitate training workshops for community based groups on PAPs 1.1.2 Facilitate training on project formulation and project management 1.1.3? 1.1.4? 1.1.5? | One day training workshops on PAPs held for at least x CBOs by 1/06 | Workshop reports |  |  |  | x | x | x |  |  |  |  |  |  |  | Who in WAC? | Transport 750 Km Subsistance, ROs, Driver, 20 days Training materils Teas and lunches at traing centres | 1,000 30,000 30,000 45,000 |