## Sheet1
Key objective | Target what | By When | Activities | Constraints
Empowering communities to sustainably use their natural resources and increase land productivity | 60 CBO's mobilized and sensitized to undertake IEM driven PAP's in initial blocks | 2007-12-01 |  | Free grazing
| At least 30 CBO's in initial blocks raising 500 seedlings |  |  | High expectations for the communities
| At least 3 CBO's in initial blocks raising suitable fodder for silk production |  | Follow up with ICIPE and existing projects, tree types and commercial viability | Clanism within some communities
| At least 15 CBO's n initial blocks are raising fodder for livestock |  |  | Lack of MOU between participating stakeholders
| At least 6 CBOs in the initial 3 blocks are raising commercial local poultry |  |  | Briefcase CBO's
| At least 15 CBO's in the initial blocks are planting trees suitable for bee keeping |  |  | Erratic disbursement of funds to CRAFT and KARI
At least 60 CBO's in initial 3 blocks on various technologies as per training plan available
At least 30 CBO's in intial blocks in crop production using improved agronomic practices and yields increased by 100%
| At least 3 sub-catchments in 3 blocks delineated and appropriate S&W conservation structures that lead to reduced soil loss identified | 2007-06-01
At least 3 umbrella groups covering each sub-catchment unit in 3 blocks are mobilised to implement synchronised soil and water conservation leading to improved environment in the sub continent
Reducing land degradation, improving soil quality and vegetation | 50% of existing wetland conserved | End of project | Desilting of water pans | Free grazing
| 50% of the community aware of the importance of wetland benefit and sustainable use options |  | Introduce perennial grasses, promote improved rangeland management | Inappropriate land use practices
| Acreage of problem fragile soils under cultivation reduced by 50%- sodic, steep slopes, shallow and hard setting soils |  | Communities put in appropriate soil conservation structures
| Increase water infiltration in hard setting soils |  | Increase fertiliser use, promote conservation farming techniques
| Increase in the number of small scale harvesting structure ( small pen) |  | Sensitize communities on the dangers of inappropriate land use practices
| Reduce permanent bare areas by 50% |  | Introduce appropriate techniques to mitigate
Increase % of perennial grasses by 40%
Reduce the prevalence of P -deficiency by 30%
Soil Carbon and Nitrogen increased by 10%
All relative to baseline
Increase the cover to 15% baseline
Increase carbon sequestration, conduct research and empower communities to participate in carbon trade | 180,000 tons Carbon sequestered | 2010 | Determine the baselines | Only 100 ha planted so far
|  | Any shorter time frame targets? | Identify communities with which to develop PAP's | Only 165,000 seedlings ready for long rains planting season in 2007 ( 450,000 per season are needed to meet 2.5million target)
|  |  | Identify key areas for afforestation and rehabilitation | Seedling survival rate
|  |  | Capacity building for communities on seed/seedling production and maintenance | Water limitation rate in Nyando
|  |  | Actual tree nursery establishment and seedling production and tree planting | Free grazing
|  |  | Measurement of Co2 | Degree of project ownership in communities
|  |  | Marketing capacity building with the G.O.K. | PAP development is slow
In principle this is not about doing everything ourselves, we must leverage
How easy is this if Field Officers are not living in the basins as originally planned. Apparently due to too few cars.
Integrated and effective Monitoring and Evaluation | Draft plan to be shared | Monday January 29th | Follow up discussions with George, Lou, Maurice / full team