| Project | Western Kenya Integrated Ecosystem Management Project (WKIEM) |
| --- | --- |
| Implementing Agency | International Centre for Research in Agroforestry (ICRAF) in collaboration with the Kenyan Agricultural Research Institute (KARI), Climate change Office of the Ministry of Environment, Natural Resources and Wildlife, the Kenyan Forestry Research Institute (KEFRI), Maseno University, regional and local NGOs, CBOs |
| Geographic Focus | Kenyan portion of the Lake Victoria Watershed |
| Goal | The goal of the project is to create synergies between rural development objectives and regional and global environmental objectives through the reversal of land degradation. The project will promote income generating activities for rural farmers in western Kenya, increase C sequestration in soils and vegetation in the agricultural landscapes of the region, contribute to reducing pollutant loads into an degrading international water body (Lake Victoria), and reduce the loss of biodiversity in the agricultural landscapes of western Kenya. |
| Objectives | - Improve capacity for local communities, farmer associations, national, and international institutions to identify opportunities, and formulate and implement policies in support of integrated ecosystem management (IEM) approaches, combining local and global benefits; - Enhance potential to sequester additional above- and below-ground carbon in the project area, and develop scientifically sound and cost effective procedures and protocols to measure, monitor and validate above- and below-ground carbon sinks in different land-use systems; - Promote agroforestry and other improved land management activities in upland areas to rehabilitate degraded lands, improve erosion and sediment control, and reduce nutrient delivery to Lake Victoria from agricultural activities; - Improve on-farm and off-farm biodiversity through agrobiodiversity and decreased pressure on “natural habitats” (remnant forests, riparian areas, wetlands, etc.); - Reduce rural poverty and improve food security by introducing new land management technologies to increase yields, and new and improved value-added cropping systems. - Create synergies between sustainable agricultural development and global environmental benefits such as mitigation of greenhouse gas accumulation in the atmosphere, forestry, biodiversity loss, and degradation of international waters; |
| Outputs | - Rehabilitated rural landscapes with improved agricultural and forestry productivity, improved stocks of soil organic matter, improved soil fertility, and improved erosion and sediment control; - Assessment of carbon sinks, sources, and reservoirs in representative land use systems, scientifically sound estimates of potential gains and rates of change, development of procedures to monitor, assess, and implement total green house gas accounting in tropical rural landscapes; - Reduced sediment and nutrient loads to rivers and streams feeding into Lake Victoria - Increased incidence of endemic species in agricultural landscapes, and reduced pressure on protected areas and other biodiversity-rich areas of global importance; - Improved rural livelihoods and economic performance of local, small-scale farming systems through yield increases and value added cropping; - Promotion of IEM approaches and increased community involvement in IEM activities (assessment, planning, decision making, implementation, evaluation, etc.); - Strengthened institutional capacity to identify opportunities, and formulate and implement policies in support of IEM approaches; - Results and lessons learned disseminated in the country and internationally. |
| Project Structure | The gross project area currently includes the Nyando, Yala, and Nzoia basins of the Lake Victoria watershed. This large area, consisting of 19,898 km2, will include specific monitoring focal areas (FA) which will receive detailed attention for monitoring and evaluation of project and environmental objectives, and the remainder of the area which will not receive the same degree of treatment but in which farmer/community associations have indicated that they also want to participate. The net project area will consist of fifteen 1010 km focal blocks spread out across the western Kenya landscape. These blocks are allocated to cover upper, middle and lower portions of each river basin and are thus representative of the types of land degradation found in western Kenya. These blocks are specifically designed for monitoring and evaluation, which will provide valuable information to project managers, and will also allow for monitoring of the progress against the environmental objectives of the project. The monitoring and evaluation system is very rigorous and builds upon approached used by environmental management agencies in developed countries. This monitoring system will also meet all of the requirements of the Clean Development Mechanism for carbon sequestration. - 20 randomly selected (64 ha) focal areas per block (= 180 FA’s, = 11,520 ha) Distributed across: 5 major river basins 3 elevation zones 9 blocks - Estimate: Funds have been secured for work with 8,000-12,000 representative households - Estimate: 65-100 U$ per household per yr total project investment. Because of the wide geographic dispersion and large area coverage within the region, and the spatial structure of the block distribution, this project will provide a rigorous learning framework for solving problems of land degradation at a large scale. The lessons learned in this project will be applied in a new World Bank initiative on rehabilitation of degraded lands that is being planned for 2007. This new World Bank initiative will ensure the sustainability of the work of the WKIEM project. Operations have begun on the ground for this project in 2004. |
| Financial plan | This project requires US$7.5 million to become fully functional. Because of the block structure of the project, financing and implementation can be done in a modular form. We currently have been successful in raising US$ 4.5 million from the Global Environment Facility (GEF) through the World Bank. These funds are supporting operations in the first 9 blocks in Nyando, Yala and Nzoia river basins. We have raised an additional US$ 500,000 for capacity building in support of this project within the Kenyan Government from the Policy and Human Resources Development Fund (PHRD) from the Japanese Government. This grant, entitled Capacity Building to Support Carbon Finance Transactions will facilitate the carbon sequestration portions of the WKIEM Project through capacity building within the Ministry of Environment, Natural Resources and Wildlife. We are seeking an additional US$3 million to expand this work to cover a total of 15 blocks in western Kenya. Our plans are to expand into the Sondu Miru and Mara River Basins and to add three blocks in the Nzoia River Basin. We estimate that we need to be able to intervene intensively in a block for three to five years to achieve the desired impact. The modular approach allows investors to fund additional blocks and leverage their investment for a large-scale impact. Funding requirements for a block are US$ 500,000 for a five year investment, or an annual investment of US$ 100,000 per block over a five year period. |