| Component 1.2: Enhanced capacity for developing carbon finance proposals. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | MoV | Responsible | Resources required | Timeline | Remarks |
| Development of procedures for measurement and monitoring of carbon stocks | Field measurement and analysis manuals | Walsh Shepherd | Staff time | Jun. 2006 |  |
| Recruitment of PhD student and dissertation proposal development for … carbon accounting … | Research proposal accepted by local Uni. | Walsh | Staff time Student stipend Uni. fees | Jun. 2006 | Subject to funding ? |
| Recruitment of PhD student and dissertation proposal development for … non-CO2 GHG accounting … | Research proposal accepted by local Uni. | Verchot | Staff time Student stipend Uni. fees | Jun. 2006 | Subject to funding ? |
| Hands-on training on carbon and non-CO2 GHG data collection, laboratory procedures analysis, monitoring and statistical interpretation. | No. of KARI and other staff trained | Walsh Verchot Shepherd Awiti | Staff time Transport Lab. costs | Jun. 2006 | Concurrent with M&E training activities (see Component 3) |

| Component 2: Scaling up and financing IEM interventions. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | MoV | Responsible | Resources required | Timeline | Remarks |
| Development of village nurseries to support agroforestry | No. of new nurseries established No. and types of seedlings produced. | Awiti | Staff time Transport Seedling and nursery materials | Jun. 2006 |  |
| Establish species screening trials | No. of georeferenced reps. No. tree seedlings planted | Walsh Awiti | Staff time Transport Seedlings & nursery materials | Katuk-Odeyo Yala |  |
| Activities to increase tree cover on severely degraded sites | Area protected and/or no. of seedlings planted | Awiti Walsh | Staff time Transport Seedlings & nursery materials Casual labor costs | Katuk-Odeyo Yala |  |

| Component 3: Establishing a monitoring and evaluation system. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | MoV | Responsible | Resources required | Timeline | Remarks |
| Acquire QuickBird satellite images | Image archive | Awiti | Staff time | Acquisition scheduled Oct. 2005 | Actual acquisition subject to cloud cover |
| Satellite data processing | GIS database (e.g. vegetation cover) and analyses Ground sampling plans | Walsh Awiti | Staff time | 1 week per block | Analysis timeline subject to image acquisition. |
| Conduct biophysical baseline surveys | GIS database established | Walsh Awiti Shepherd Block FO’s | Staff time Transport Lab. costs Casual labor costs | Katuk-Odeyo Londiani Nandi Yala | 1 month per block concurrent with socioeconomic surveys |
| Analysis and reporting of biophysical baseline surveys | Survey reports 1 per block | Walsh Awiti Shepherd PCO | Staff time | Katuk-Odeyo Londiani Nandi Yala | 1 week per block after lab. analyses |
| Conduct socioeconomic baseline surveys | GIS database established | Walsh Awiti Block FO’s | Staff time Transport Casual labor costs | Katuk-Odeyo Londiani Nandi Yala | 1 month per block concurrent with biophysical surveys. |
| Analysis and reporting of socioeconomic baseline surveys | Survey reports | Walsh Awiti PCO | Staff time | Katuk-Odeyo Londiani Nandi Yala | 1 week per block concurrent w. analyses of biophysical surveys |
| Equipment purchase, installation and testing for measuring non CO2 GHG’s | Kisumu laboratory facilities operational | Verchot 3 months. Consultant | Staff time Consultancy costs | Apr. 2006 |  |
| Development of M&E procedures | Field measurement and analysis manuals | Walsh Verchot Shepherd Awiti PCO | Staff time |  |  |
| Hands-on training on M&E procedures | No. of KARI and other staff trained | Walsh Verchot Shepherd Awiti PCO | Staff time Transport Lab. costs |  | Concurrent with carbon accounting training activities (see Component 1.2) |