Progress report of Lower Nzoia Block from 18th – 21st December 2006

By Joash Mango and Isaac Learamo

The main objective of the biophysical work is to characterize the landform, soil types and vegetation cover, there by giving the conditions and the ecological indicators.

The baseline survey of the biophysical started on 11th December 2006 with a bad start in that the Global positioning system that we were suppose to use was not loaded with the points as we expected. We had to come back and start the work on 18th December 2006 with a team of six people including the driver. The team had to operate from Busia to the block due to the long distance of the place from Kisumu that could take atleast two and half hours.

To meet the target of the work we were forced to take one local person to help us in the sampling of the soil for the depth sampling of the 120cm, the area assistant chief of Namuduru sub location provided the person.

Clusters activities

We started by tracing cluster one that took us up to Nyadorera B in the lower part of the block, due to the current status of the place of flooding we opted to leave the cluster until the water goes down. Cluster two around Rwambwa was also still under water and same with cluster three. These three clusters are in Siaya district bordering river Nzoia.

We traced cluster four in the upper part of the block which is in Busia district, Funyula division, Bwiri location, and Namuduru sub location. We did cluster four and part of cluster seven which comprises of six plots in Busia side.

On Siaya district, Ukwala division, West Ugenya location and East Sifuyo sub location side we covered cluster eight and part of cluster seven at the border. In general the clusters done are clusters four, seven and eight.

- Cluster Four

Cluster four is mostly made up of range of hills with permanent restriction to access due to the thickets formation with evergreen to semi deciduous bush lands with perennial grassland. At the lower part of the hills agricultural production is going on with mainly cassava and sweet potatoes being grown. Maize growing is not of a priority to the community in this cluster.

- Cluster Seven

This cluster is partly under seasonal wet land and most of the crop fields have been abandoned by the communities due to the frequent flooding of the farms. This particular cluster is part of the flood plains and it is in the border of Busia and Siaya district.

- Cluster Eight

Most of this cluster is on a plateau and falls in Siaya district, Ukwala division, North West Ugenya location and Karadolo sub location. The plots spread around Mulambo village an area of mainly very sparsely populated. Most of the area is under agricultural production though most of the land remains fallow with thicket formations. In this cluster plot number two fell inside the Milambo dam so we abandoned the plot and did adjacent plot next to the dam at the edge.