Report for 31st oct.-3rd Nov.2006

| Date | Activities | Remarks |
| --- | --- | --- |
| 31/10/06 | Visited individual farmers from Aluor widows and Moyier support group | Out of 8 farmers visited, 4 farmers’ plots qualified for screening trials while the remaining 4 qualified for woodlot. |
|  | Visited Nguono women group and Otodo youth group in Ndori sub-location | Made appointment with these group leaders to meet their group members who will in turn take us to individual farms for assessment on 6/11/06 as from 9.30am |
|  | Visited Ndori primary school | Met deputy head teacher who took to areas they feel should be planted with trees as away of preventing wind from breaking their classroom roofs. He further stressed that the incident of the roofs being blown away by wind had occurred three times occasionally. The site will have both screening trial and afforestation of various tree /tree fruit species. |
| 1/11/06 | Identified some farmers from Onyinyore and Gombe sub-locations for screening trials | 10 farmers Visited qualified for screening trials |
| 2/11/06 | Attended a focal area meeting held by Wagai divisional soil and water conservation officer at Malele primary school | Met group leaders of various sub-locations in Wagai division and with the officers permission, we used the opportunity to pass the information about WKIEMP project and its intension to Improve peoples’ livelihood through: - Scaling up community tree nurseries - Rehabilitation of degraded areas - Setting up trials on different tree species. Identified Kanyadet sub location as one that falls under our research block and made appointment to meet their group members and other individuals with interest at malele chief camp on 7/11/06 as from 9.30 am |
| 3/11/06 | Visited degraded area of Lekwenyi in Nyando block | Met area Ass. Chief and made an appointment to meet the community around the degraded area for discussions on possible rehabilitation strategies on 9/11/06 as from 12.00noon |
|  | Bought and delivered 2 bags of Maize to Kowala group | This is the project’s incentive contribution towards the group’s rehabilitation program at Kowala. The group is entitled to receive 2 bags of maize every Friday totaling to 8 bags per month as from Nov.2006. |

Total plots screening trials 71

Total Plots expected 150

Remaining 79