12th-14th April 07 report

| Date | Activity | Remarks |
| --- | --- | --- |
| 12/4/07 | Planted screening trials in Kanyadet sub location | A total of 3 plots were planted with a total of 144 tree seedlings per plot. |
| 13/4/07 | Planted screening trials in Rera sub location | A total of 3 plots were planted with a total of 144 tree seedlings per plot. |
| 14/4/07 | Planted screening trials in Rera sub location | A total of 4 plots were planted with a total of 144 tree seedlings per plot. |

Note;

- We couldn’t plant more plots because we have limitation of transportation.

- Most seedlings which were planted a week before the week of 9th April 2007 shall need to be gapped as they have dried up because a short drought which occurred during that period.

- We’ve planted a total of 11,259 tree seedlings in Lower yala screening plots by the end of this week.

- A total 80 screening plots have been planted in lower yala block.