16th-21st April 2007 report

| Date | Activity | Remarks |
| --- | --- | --- |
| 16/4/07 | Planted screening trials in Dienya East sub location | A total of 4 plots were planted. 3 plots had a total of 144 seedlings per plot while 1 plot had a total of 141 seedlings. |
| 17/4/07 | Planted screening trials in Dienya East and Uriri sub locations | A total of 4 plots were planted. 2 plots had a total of 144 seedlings per plot while the other 2 plots had 96 and 120 seedlings respectively. |
| 18/4/07 | Planted screening trials in Uriri sub location | A total of 4 plots were planted with a total of 144 seedlings per plot |
| 19/4/07 | Planted screening trials in Gombe and Onyinyore sub locations | A total of 4 plots were planted. 3 plots had a total of 144 seedlings per plot while 1 plot had 82 seedlings. |
| 20/4/07 | Planted sceening trials in Rera sub location | A total of 4 plots were planted with a total of 144 seedlings per plot |
| 21/4/07 | Filling/gapping tree seedlings in Rera sub location. | A total of 171 seedlings of assorted spp were gapped. |

Note:

A total of 100 screening plots have been planted in lower Yala.

To date, a total of 14,000 seedlings of assorted tree spp have been planted in lower Yala

Out of the expected 23040 tree seedlings to be planted in lower Yala, we need a bout 10,000 seedlings of assorted spp to complete the remaining plots including gapping.