2nd- 7th April 07 report

| Date | Activity | Remarks |
| --- | --- | --- |
| 2/4/07 | Planted screening trials in Kanyadet sublocation | A total of 6 plots were planted with a total of 144 tree seedlings per plot. |
| 3/4/07 | Call off planting exercise in lower yala but purchased ant termite chemical. | Activity called off because of persisted drought until rains come back but field resource persons to continue applying chemicals to the already planted plots which has been attacked by termite as they prepare others to get ready to receive the seedlings immediately the rains start |

Note:

- The exercise was held after we have planted 70 farmers out of the expected 140 farmer as we anticipate 20 to abort the exercise.

- We closed the week after we’ve planted a total of 9,866 tree seedlings in lower yala.