29th-2nd Feb 07 LY report

| Date | Activity | Remarks |
| --- | --- | --- |
| 29/1/07 | Did infiltration in Kanyadet Sub location | Did infiltration in 1 plot as the Kari Driver had some commitments in Town about getting a school for his child. |
| 30/1/07 | Did infiltration in Ndori and Rera sub locations | Did infiltration in 2 plots. We were not sure of the second day, as the Kari driver had informed as that he was given only 2 days to be with us. |
| 31/1/07 | Did infiltration in Rera sub location | Did infiltration in 1 plot in Rera sub location, which was later aborted at the Eightieth minutes because of the rains. We were very fortunate to get another Vehicle from Kari with a driver. |
| 1/2/07 | Did infiltration in Gombe sub location | Did infiltration in 1 plot. We could not do the second infiltration because it had already started raining. |
| 2/2/07 | Did infiltration in Kanyadet sub location | Did infiltration in 1 plot. |

# Summery

Note: This is a cumulative summery report for Lower Yala.

| Week | No of plots Characterized | No of plots done Infiltrations | Comments |
| --- | --- | --- | --- |
| 20th Nov-24th Nov | 2 | 4 | - Soil samples collected; plot characterization and infiltrations done per plot. - It also acted as a training ground for LY field foremen |
| 27th Nov-1st Dec | 15 | 12 | - Soil samples collected; plot characterization; infiltrations done in 6 plots. |
| 4th Dec-8th Dec. | 13 | 8 | - Soil samples collected; plot characterization; infiltrations done in 4 plots. |
| 11th Dec-15th Dec | 18 | 8 | - Soil samples collected; plot characterization; infiltration done in 4 plots. |
| 18th Dec- 22nd Dec | 35 | 12 | - Soil samples collected; plot characterization; infiltration done in 6 plots |
| 2nd Jan-5th Jan 07 | 20 | 10 | - Soil samples collected; plot characterization; infiltration done in 5 plots |
| 8th –12th Jan 07 | 15 | 10 | - Soil samples collected; plot characterization; infiltration done in 5 plots |
| 15th-19th Jan 07 | 21 | 6 | - Soil samples collected; plot characterization; infiltration done in 3 plots. |
| 22nd-26th Jan 07 | 22 | 14 | - Soil samples collected; plot characterization; infiltration done in 7 plots; |
| 29th-2nd Jan 07 | 0 | 12 | - Infiltration done in 6 plots; |

Total plots Characterized 		160

Total plots done infiltration 		  46

Plots remaining for characterization 		0

Plots remaining for infiltration 		4

Time frame (incase our program is not interfered with)

To complete infiltration 2W/D i.e. first week of February 07

## Work plan

For the remaining few weeks to march 07, we shall Mobilize 160 selected farmers to complete digging holes before mid February and return the dug soils mixed with manure back into their respective holes. This would give us an easier time during tree planting which we anticipate to start in the last week of February in the weather (rains) stand the way it is at present.