15th-19th Jan 07 report.

| Date | Activity | Remarks |
| --- | --- | --- |
| 15/1/07 | Measured and collected plot measurements in Wagai East and Uriri sub locations. | Collected soil samples and plot characterization in 8 plots, did infiltration in 2 plots. |
| 16/1/07 | Measured and collected plot measurements in Rera sub location. | Collected soil samples and plot characterization in 1 plot, started infiltration that was later aborted at the 3rd reading stage due to heavy rains with hailstorm. The rains started at a round 12.20pm |
| 17/1/07 | Measured and collected plot measurements in Rera sub location | Collected soil samples and plot characterization in 2 plots, did infiltration in 1 plot, which was later aborted after 1hr because of logistics. |
| 18/1/07 | Measuring and taking plot measurements in Gombe sub location | Collected soil samples and plot characterization in 5 plots. Did 1 infiltration. We could not manage to start the second infiltration as the rains were almost falling. |
| 19/1/07 | Measuring and taking plot measurements in Ndori and Kanyadet sub locations. | Collected soil samples and plot characterization in 5 plots, started infiltration in 1 plot, which was later aborted at the 5th reading when it started raining. |

# Summery

Note: This is a cumulative summery report for Lower Yala.

| Week | No of plots Characterized | No of plots done Infiltrations | Comments |
| --- | --- | --- | --- |
| 20th Nov-24th Nov | 2 | 4 | - Soil samples collected; plot characterization and infiltrations done per plot. - It also acted as a training ground for LY field foremen |
| 27th Nov-1st Dec | 15 | 12 | - Soil samples collected; plot characterization; infiltrations done for 6 plots. |
| 4th Dec-8th Dec. | 13 | 8 | - Soil samples collected; plot characterization; infiltrations done for 4 plots. |
| 11th Dec-15th Dec | 18 | 8 | - Soil samples collected; plot characterization; infiltration done for 4 plots. |
| 18th Dec- 22nd Dec | 35 | 12 | - Soil samples collected; plot characterization; infiltration done for 6 plots |
| 2nd Jan-5th Jan 07 | 20 | 10 | - Soil samples collected; plot characterization; infiltration done for 5 plots |
| 8th –12th Jan 07 | 15 | 10 | - Soil samples collected; plot characterization; infiltration done for 5 plots |
| 15th-19th Jan 07 | 21 | 3 | - Soil samples collected; plot characterization; infiltration done for 3 plots. |

Total plots Characterized 		139

Total plots done infiltration 		  35

Plots remaining for characterization 		21

Plots remaining for infiltration 		15

Time frame (incase our program is not interfered with)

To complete characterization  	3-4 W/D

To complete infiltration  		    8W/D