22nd-26th Jan 07 Report

| Date | Activity | Remarks |
| --- | --- | --- |
| 22/1/07 | Measured and took plot measurements in Rera and Kanyadet upper Sub locations | Collected soil samples and plot characterization in 8 plots; did infiltration in 2 plots. Among the 8 plots, one plot had been done infiltration but not taken other measurements. |
| 23/1/07 | Measured and took plot measurements in Gombe, Onyinyore and Uriri sub locations | Collected soil samples and plot characterization in 6 plots, did infiltration in 2 plots. |
| 24/1/07 | Measured and took plot measurements in Ndori and Rera Sub locations | Collected soil samples and plot characterization in 4 plots, did infiltration in 1 plot. |
| 25/1/07 | Measured and took plot measurements in Kanyadet and Ndori sub locations | Collected soil samples and plot characterization in 5 plots of which one plot with serial Id LY010 was replaced with another plot of the same serial Id but different farmer as the former farmer had pulled out. We did 1 infiltration. |
| 26/1/07 | Took plot measurements in Kanyadet sub location | Did 1 infiltration. |

# Summery

Note: This is a cumulative summery report for Lower Yala.

| Week | No of plots Characterized | No of plots done Infiltrations | Comments |
| --- | --- | --- | --- |
| 20th Nkov-24th Nov | 2 | 4 | - Soil samples collected; plot characterization and infiltrations done per plot. - It also acted as a training ground for LY field foremen |
| 27th Nov-1st Dec | 15 | 12 | - Soil samples collected; plot characterization; infiltrations done for 6 plots. |
| 4th Dec-8th Dec. | 13 | 8 | - Soil samples collected; plot characterization; infiltrations done for 4 plots. |
| 11th Dec-15th Dec | 18 | 8 | - Soil samples collected; plot characterization; infiltration done for 4 plots. |
| 18th Dec- 22nd Dec | 35 | 12 | - Soil samples collected; plot characterization; infiltration done for 6 plots |
| 2nd Jan-5th Jan 07 | 20 | 10 | - Soil samples collected; plot characterization; infiltration done for 5 plots |
| 8th –12th Jan 07 | 15 | 10 | - Soil samples collected; plot characterization; infiltration done for 5 plots |
| 15th-19th Jan 07 | 21 | 6 | - Soil samples collected; plot characterization; infiltration done for 3 plots. |
| 22nd-26th Jan 07 | 22 | 14 | - Soil samples collected; plot characterization; infiltration done for 7 plots |

Total plots Characterized 		160

Total plots done infiltration 		  42

Plots remaining for characterization 		0

Plots remaining for infiltration 		8

Time frame (incase our program is not interfered with)

To complete infiltration 4W/D i.e. first week of February 07