2nd – 5th Jan 07 report:

| Date | Activity | Remarks |
| --- | --- | --- |
| 2/1/07 | - Measuring and taking plot measurements in Rera Sublocations - Visited farmers covered in the block but under millennium Villages project in Ramula, Uranga, Lihanda, and Gongo sub locations | - Did infiltration in 1 plot - These farmers admitted that they are preserving their plots or rather farms to MVP while some shows no concerns to planting trees. - Measured 1 plot but didn’t other measurements because we had run out of time. |
| 3/1/07 | Measuring and taking plot measurements in Rera and Chambered Sub locations | Collected soil samples in 7 plots, did infiltration in 1 plot, took GPS readings taken in all plots |
| 4/1/07 | Measuring and taking plot measurements in Wagai east and Wagai west sub location | Collected soil samples in 5 plots, did infiltration in 2 plots and GPS readings taken in all plots |
| 5/1/07 | Measuring and taking plot measurements in Kanyadet and Rera sub locations | Collected soil samples in 7 plots, did infiltration in 1 plot, took GPS readings in all plots. |

# Some of the problems Encountered

- Some farmers mostly in Uriri sub location changed their minds when measuring team arrive at the venue hence making them have plan B and because of distances involved, they may end up not meeting the required number of plots in a day.

- Some 4 farmers in Kanyadet sub location pulled out after being incited by others that their farms will be taken away. They based their reasoning on the logic that no organization or person can give out trees without other hidden agenda.

- Some farmers in Rera sub location with interest in trees invite our field guys to their farms only to discover that the fields are small but they go a head to measure them to avoid embarrassing the farmer.

# Summery

Note: This is a cumulative summery report for Lower Yala.

| Week | No of plots worked on | Infiltrations done | Comments |
| --- | --- | --- | --- |
| 20th Nov-24th Nov | 2 | 4 | - Soil samples collected; plot characterization and infiltrations done per plot. - It also acted as a training ground for LY field foremen |
| 27th Nov-1st Dec | 15 | 12 | - Soil samples collected; plot characterization and infiltrations done for 6 plots. |
| 4th Dec-8th Dec. | 13 | 8 | - Soil samples collected; plot characterization and infiltrations done for 4 plots. |
| 11th Dec-15th Dec | 18 | 8 | - Soil samples collected; plot characterization and infiltration done for 4 plots. |
| 18th Dec- 22nd Dec | 35 | 12 | - Soil samples collected; plot characterization and infiltration done for 6 plots |
| 2nd Jan-5th Jan 07 | 20 | 10 | - Soil samples collected; plot characterization and infiltration done for 5 plots |
| 8th –12th Jan 07 | 15 | 10 | - Soil samples collected; plot characterization and infiltration done for 5 plots |