8th –12th Jan Report 07

| Date | Activity | Remarks |
| --- | --- | --- |
| 8/1/07 | Measuring and taking plot measurements in Gombe and Onyinyore sub location. | Collected soil samples and plot characterization in 7 plots; did infiltration in 2 plots |
| 9/1/07 | Measuring and taking plot measurements in Gombe sub location. Collected soil samples in kambare sub location | Collected soil samples and plot characterization in 2 plots and did 2 infiltrations. Also collected soil samples from 3 plots previously measured and characterization done but soils not collected because of interruption by rains |
| 10/1/07 | Measuring and taking plot measurements in Ndori and Kanyadet sub locations | Collected soil samples and plot characterization in 6 plots and did 1 infiltration. Because of logistics, we could not start running the second infiltration |
| 11/1/07 | Organized field data |  |
| 12/1/07 |  |  |

Note: Because of logistics, we were unable to work in lower Yala on 11th Jan 2007 and 12th Jan 2007. We shall resume there on 15th Jan 2007.

# Summery

Note: This is a cumulative summery report for Lower Yala.

| Week | No of plots Characterized | No of plots done Infiltrations | Comments |
| --- | --- | --- | --- |
| 20th Nov-24th Nov | 2 | 4 | - Soil samples collected; plot characterization and infiltrations done per plot. - It also acted as a training ground for LY field foremen |
| 27th Nov-1st Dec | 15 | 12 | - Soil samples collected; plot characterization and infiltrations done for 6 plots. |
| 4th Dec-8th Dec. | 13 | 8 | - Soil samples collected; plot characterization and infiltrations done for 4 plots. |
| 11th Dec-15th Dec | 18 | 8 | - Soil samples collected; plot characterization and infiltration done for 4 plots. |
| 18th Dec- 22nd Dec | 35 | 12 | - Soil samples collected; plot characterization and infiltration done for 6 plots |
| 2nd Jan-5th Jan 07 | 20 | 10 | - Soil samples collected; plot characterization and infiltration done for 5 plots |
| 8th –12th Jan 07 | 15 | 10 | - Soil samples collected; plot characterization and infiltration done for 5 plots |

Total plots Characterized  		118

Total plots done infiltration  		  32

Time frame (incase our program is not interfered with)

To complete characterization  	7 W/D

To complete infiltration  		10 W/D