7th-12th May 2007

| Date | Activity | Remarks |
| --- | --- | --- |
| 7/5/07 | Planting screening trials in Onyinyore, Gombe and Dienya East sub location | A total of 4 plots of assorted species were planted. 2 plots had a total of 144 seedlings per plot, 1plot had 132 seedlings while the last plot had 141 seedlings |
| 8/5/07 | Planting screening trials in Kanyadet sub location | A total of 4 plots were planted. A total of 144 seedlings were planted per plot |
| 9/5/07 | Planting screening trials in Kanyadet and Rera sub location | A total of 4 plots were planted. 3 plots had a total of 144 seedlings per plot while 1 plot had 92 seedlings. |
| 10/5/07 | Planting screening trials in Rera sub location | A total of 4 plots were planted. 3 plots had a total of 144 seedlings while 1 plot had 86 seedlings of assorted species. |
| 11/5/07 | Planting screening trials in Rera sub location | A total of 3 plots were planted. 1 plot had 61 seedlings; the 2nd plot had 120 seedlings while the third plot had 140 seedlings and gap filled 55 seedlings of assorted spp |
| 12/5/07 | Gap-filling Kanyadet and Rera sub locations | A total of 8 farms were gap filled both in Kanyadet and Rera sub locations. Managed to gap fill 437 seedlings |

This week, we managed to plant 2500 seedlings of assorted species. In addition to this, we managed to gap fill 492 seedlings of assorted species. This gives us a total of 2937

Seedlings planted within the cause of the week.

To date,

- We have managed to plant 19081 seedlings of assorted species equivalent to 139 plots of screening trials in lower Yala.

- Managed to gap filled 1063 seedlings of assorted species.

- We have managed to plant a grand Total of 20,144 seedlings in lower yala.