THE SOCIO ECONOMIC SURVEY REPORT

LOWER YALA BLOCK

13TH – 17TH NOV.

We went to Nyando and did the replacements on Monday. Managed to do interviews in 5 households.

On Tuesday we did sorting and filling as we prepared for work that we began in Yala block on Wednesday

We have been in Yala for the last 3 days where we have managed to interview a total of  17  households.

So far we have not been able to move a little faster because this is shrub land area ,getting access to the households is not easy since the area is highly infested with snakes and so using short cuts  would be very risky yet the house holds are also very scattered.

Again communication is not easy amongst us ,we have not been able to get enough air time so that we talk yet we have one GPS and also one auger and we have to share them.

One of us was also taken ill ( George ) and he had to urgently go for treatment.All in all we are moving on well and trying very much to deliver to our level best.

.

Enumerators.

George Odhiambo

Azinapher Mideva

Salome Aoko