Monthly Report –January 2007 by Walter Adongo

| Month | Week/ Dates | Activities | Challenges |
| --- | --- | --- | --- |
| December January | 31st -06th | Seed sowing (Grevillea robusta, Terminalia brownii and Casuarina equisetifolia) pricking out and watering on going in the two nurseries. | Very wet weather hence slow seed germination and damping off prevalent. Resource unavailability since there was no money |
| January | 7th-13th | Potting and seed sowing continues. Closed the week cloaking the 125,000 tubes for Maseno | Very wet weather hence slow seed germination and damping off prevalent |
| January | 14th-20th | Pricking out continues for the seeds sown in December | Low survival due to weather |
| January | 23rd-27th | Calliandra calothyrsus, Acaccia spp and Albizia coriara seed sowing and pricking out continues Attending the Project Review workshop at Kisumu Hotel. | Low seed germination and rates |
| January- February | 28th - 4th | Pricking out and seedling maintenance continues |  |
| February | 6th – 10th | Seedling maintenance continues To Nakuru and Karatina on Farmers’ of the Future project with Tom Vandenbosch |  |
| February | 13th -17th | Seedling maintenance continues WKIEMP meeting to strategize on the scheduled World Bank monitoring team. Visited 6 nurseries in Lower Nyando with a total of 12,630 assorted tree seedlings. With Roeland Kindt on the TOTDOMEA project | Communication breakdown within project staff despite the concluded workshop; duplication of work and the number of seeds required for long rains. The high hopes of farmers raised previously during the initiation of the project and the lack of follow up on some of the nurseries established by ICRAF. |
| February | 18th -24th | Seedling maintenance continues Visited 8 group tree nurseries in Wagai. They had about 44,000 assorted seedlings | Duplication of work and the disparity on the status of some of the tree nurseries. |
| February/ March | 25th-3rd | Seedling maintenance continues. Pricking of Acacia spp, Carica papaya on going. | Drastic change in weather |
| March | 4th – 10th | Seedling maintenance on going. A total of 45,538 and 57,470 assorted tree seedlings were in Kisumu and Maseno nurseries respectively. Looking for seedlings especially Grevillea robusta for the screening trials as the size of available seedlings is not good enough. | In availability of required seedling hence covering a big mileage to Kericho, Kakamega, Malava and Bondo. The parity in implementation of seedling raising projects; Nile Heritage, Nyandere and Community groups and the Forest department |
| March | 11th – 17th |  |  |
| March | 18th -24th |  |  |
| March | 25th – 31st |  |  |