Progress Report ICRAF (KARI)

By Anja Boye; End-November 2006 (Oct. 30 to Nov. 24th)

- Bio-physical baseline

The bio-physical baseline survey team resumed working in Lower Yala on November 13th, with 5 clusters still to be sampled, e.g. 50 points. In these 5 clusters, 3 infiltration measurements were done for each of the 5 clusters and 8 soil samples were collected per plot, e.g. a total of 80 samples per cluster and a grand total of  400 for the 5 clusters. On November 21st, the team completed their field work in Lower Yala (see brief summary attached).

On November 22nd, Luka, Issac, and Mango joined Wilson Aore from KARI in visiting the block of Lower Nzoia. Sensitization meetings are planned for the week commencing on December 4th. The bio-physical team is ready to start sampling thereafter.

Soil samples for the 11 clusters are ready to be sent to Nairobi and arrangements with Dr. Keith Shepherd have been made for analyses in January 2007 since the spectral lab is closed in December.

- Socio-economic baseline

The socio-economic team completed the Lower block of Nyando on November 13th. The enumerators re-interviewed 150 households and interviewed an additional 6 household to replace the households where the respondent had deceased or did not want to participate. The following list gives the no. of households interviewed at sub-location level:

- Jimo East: 67, Agoro East: 11, Agoro West: 12, Awach: 15, Tabaita: 10, Kaplelaret: 10, Kapsorok: 8, Moro: 7, Rarieda:  6, Ramogi: 6, Kandaria: 4

Caroline Gewa from KARI participated in the survey in Lower Nyando. KARI also sent a student for a few days to participate.

On November 15th, the socio-economic team commenced their work in the Lower block of Yala. Due to shortage of GPS units, the socio-economic team teamed up with the bio-physical team for the first 5 days as to be able to find the entry points into the block. Once the bio-physical team finished their work, the socio-economic team took over the GPS unit.

The first 3 days in Lower Yala the team managed to interview 15 households, however, one enumerator fell ill so we are expecting to progress at a speed of at least 6 interviews per day. During the last 2 weeks of November, the socio-economic team managed to interview 30 households. By Friday November 24th, four clusters had been samples, e.g. more than 40 interviews had been conducted.

The teaming up with 3 of the enumerators trained by KARI depends entirely on when KARI has procured the 8 GPS units. Also, additional soil augers will be required.

The target is to interview 160 households, e.g. 10 households per cluster, and the socio-economic team is expected to have completed Lower Yala by the end of the year. The lower number of expected interviews per day (6 vs. 10) is due to the length of the edited questionnaire and the rough terrain. Therefore, once the team moves into the lower part of the block and KARI sends their enumerators, the progress will be more.

The lower block of Nzoia will be sampled in the month of January and the middle block of Yala in the month of February.

The socio-economic database was up-dated during the month of November to include the modified and new questions in the modified questionnaire. ICRAF started entering the new information in the course of  November, and the exercise in planned to have been completed by December 1st.

A meeting was held on November 24th at ICRAF regarding the socio-economic database. The database has been modified to accommodate the edited and new questions raised in the last World Bank review mission, however, the database is still not fully functional. Eric Ambani is working on it as well as the templates for the other blocks. He is to have finished the work today Nov. 28th so that KARI can be given the templates in the bi-monthly meeting. The interviews conducted for the first 5 clusters will be given to KARI in the bi-monthly meeting. Clusters given to Caroline: 14 (10), 16 (10), 15 (9), 13 (10).

- Survey for tree-screening trials on-farm: A) Lower Nyando and B) Lower Yala

- Lower Nyando

Several meeting were held with the 4 resource people working for the project in Lower Nyando. In the course of November, the resource people have identified 37 plots for the screening trials, with 17 being ready for planting. The target for each person is 40 plots/ trials, and the exercise is to be completed before end year. The speed of some of the resource persons is being evaluated and perhaps changes will be made. The resource persons are paid per farm ready to plant. One resource person, Valentine Awiti, has alone identified 22 plots and will be given the extra task of assisting in some of the other areas where the speed is less. So far, 11 farms have been characterized and 3 infiltration studies performed (e.g. 6 in total since 2 per farm). A total of 50 infiltration studies are to be carried out for the 160 trials.

There is a need to sensitize the farmers who have given areas for the tree screening trials, hence the farmers who have allocated land so far will be invited to a baraza where the project will be discussed. The first baraza will be held on Dec. 1st. Thereafter, as more farmers are engaged in the activity more barazas will be held.

- Lower Yala

In Lower Yala, 160 farmers have been identified for tree-screening trials and towards the end of Nov., the characterization of the respective farms began. However, first a small training was held with the field team, where 4 people were trained in soil sampling and infiltration. So far 2 farms have been characterized and sampled. The plan is to have all 150 farms characterized and sampled before Christmas.

- Tree nursery at ICRAF

The biggest challenge has been to streamline the nursery at the Kisumu office and in setting up an additional nursery at KEFRI in Maseno. In the month of November, production has greatly improved and the nursery now holds 17,500 seedlings, 9,000 Neem seedlings, and 40,000 pots. Productivity for the people potting has increased from 219 to more than 500 per day. Since the space at the Kisumu office has run out, an additional nursery has been set up at KEFRI in Maseno, where ICRAF used to have a large nursery. James Owek, the nursery foreman, has been shifted to Maseno. However, the senior technician Walter Adongo is still in charge of both nurseries. In Kisumu, only a few more thousand seedlings will be raised until mid-December. Thereafter, only maintenance will take place.

In order to be able to pot and prick the remaining 124,900 seedlings required for the long rains, 25 casuals have been hired as from mid-Nov. for 10 working days. As of Nov. 24th, Maseno holds 42,000 pots and 5,000 seedlings, directly sown into tubes, and 22,900 tubes.

The pricking is expected to take 10 working days and will commence in early December.

On November 22nd, Walter and I held another meeting where we went through the budget prepared by Walter, which has been approved by Louis Verchot and the actual expense sheets in relation to the minutes of the meeting held with KARI on October 30th. It was agreed that Walter prepare another budget for KARI, which needs approval before we commence the work of raising seedlings for them. It has been communicated to KARI that if they want seedlings raised in the central nursery as well as in the community / on-farm nurseries, materials and inputs have to bought immediately.

- Identification of degraded areas: Lower Nyando

Work has been progressing for the degraded areas identified in Lower Nyando while the bio-physical team has been on break. To be able to keep track of the work the communities do, a field sheet has been prepared for the community group to fill during their weekly meetings and field days.

Today, Monday Nov 27th, a meeting is being held with the rehabilitation group in Kokoto to assess the amount of food (maize) to be given in the food for work concept. The community is proposing 2.5 bags per week, however, ICRAF wants to assess the number of members participating in the rehabilitation activities to assure correspondence with the amount of food given to the Kalacha group. Today’s report from the field team is that 47 people showed up for the exercise and ICRAF has agreed to pay the 2.5 bag of maize per week – to be given every Friday.

In Kowala, ICRAF has had several meetings with the Kowala Environmental Rehabilitation group.

a) On Nov. 7th ICRAF and KARI visited the Kowala group and KARI promised to look into / follow-up on activities related to livelihood improvement. The community was told to form a CIG, which the community has done. They are waiting for the implementation from KARI. The following was promised to the community by the KARI field officer Samuel Obaga:

- Irrigation kit

- Livestock rearing

- Poultry keeping

- Certified seeds provision

  - On Nov. 24th, ICRAF donated 200 Acacia spp. seedlings to the group, which have been planted in the rehabilitation site.

- Other activities

  - Database management

The two databases, the bio-physical and the socio-economic, have been up-dated. The new information collected in Lower Nyando for the socio-economic baseline survey is currently being entered. A small meeting was held with the M&E team and Caroline Gewa at ICRAF on Nov. 24th. Unfortunately, the database was still not fully functional and it was agreed that the edited database be brought to the bi-monthly meeting on Nov. 28th along with the templates for the other blocks containing the respective sub-locations.

Data for the bio-physical baseline survey in Lower Yala will be entered in December. Additional databases are in the planning phase for the tree-screening trials and rehabilitation of degraded areas.

  - On-farm / community tree nurseries (A) Lower Nyando, (B) Lower Yala

(A) Lower Nyando:

On November 23rd, ICRAF and KARI visited 6 on-farm nurseries in Nyando. The report from the visit is that some groups need more trainings, where all groups need inputs and materials. KARI to take the main lead.

(B) Lower Yala:

On Nov. 3rd, KARI and ICRAF held community mobilization meeting in Wagai on nursery establishment and management – 27 groups participated in the meeting. In the following week, Nov. 6-10th, KARI and ICRAF visited 9 of the 27 groups and 3 groups were chosen for training and capacity building. In the week from Nov. 13-17th, trainings were held for 4 groups in Wagai with ICRAF taking the lead. Unfortunately, the KARI field officer (Eva Gacheru) could not participate because she was attending the UN Climate Change meeting in Nairobi. However, other KARI staff participated. The World Bank Sector Manager, Karen Brooks, visited the site during her visit to the project on Nov. 15th.

Inputs and materials for these nurseries to be purchased by KARI and the urgency has been stressed to the field officer. Further discussion to take place after the bi-monthly meeting tomorrow on the 28th of Nov.

  - Stakeholder meeting in Katuk  organized by the CBO ‘Friends of Katuk’ (Luka represented ICRAF)

On November 21st, the CBO called ‘Friends of Katuk’ called for a Stakeholder meeting at Katuk to coordinate activities taking place in Karuk gully as well as discuss the best way to spend the grant they have received from the Nile Basin Initiative. A team from KARI and ICRAF (Samuel Obaga, Agnes Yoblerik, and Luka Anjeho) participated and it was agreed that the WKIEMP project should not proceed with the planned activities in Kokoto with regards to de-silting the dam and establishment of the nursery, since the CBO has received funding for these activities. The project, however, is still to continue with the rehabilitation of the degraded area.

  - Visits by Donors and other visitors

On November 10th, the regional coordinator for the ICRAF ECA region, Dr. Henning Baur visited ICRAF Kisumu in 3 visitors from Canada. ICRAF took the visitors to Kowala to visit the Kowala Environmental Rehabilitation Group. The visitors were impressed with all the work the group has been doing and was concerned about the progression of the gully. 20 Acacia trees were planted the head of the gully and the team moved on to Kokoto Rehabilitation sites, where we saw the area where the WKIEMP project is planning to plant trees. We also visited the dam and the nursery, as well as Eddy’s farm. Eddy is a farmer ICRAF trained in 2000-2001 in nursery establishment and good farming practice. Eddy has picked up very well and has a large nursery, a pond and many interventions at his farm. Eddy could be very useful to the project as a demonstration farmer, and ICRAF has plans of assisting him further with his nursery.

  - Creation of maps for WKIEMP project

In the course of November, ICRAF has produced several maps for the project:

- A general map showing the 3 river basins and the location of the 9 blocks and the extra block for middle Nzoia

- Individual maps for the respective 10 blocks. Several maps have been made for each block to suit various purposes. Each block now has the following maps: A simple map showing roads, streams and river, and sub locations; a map indicating sampling points for the bio-physical baseline and entry points for the socio-economic baseline; and finally, a map showing topographical features. KARI has had some corrections to these maps and 3 blocks have been re-located: Middle and Upper Yala, and Middle Nzoia. The maps are being made and should be ready by Dec. 1st. Middle Nyando still needs to be ground surveyed by KARI, which is to take place on Nov. 29th with Luka participating from ICRAF.

All maps have been generated by the GIS unit at ICRAF in Nairobi.

  - Creation randomized points for sampling

Markus Walsh has generated the sampling points for each block for the bio-physical baseline survey.

  - Meeting with Centre Director, Dr. Mercy Gichora of KEFRI Maseno on nursery establishment in Maseno

On November 1st a meeting was held with the Centre Director, Dr. Gichora regarding ICRAF’s request to re-possess the nursery space in Maseno. The Centre Director agreed and it was agreed that ICRAF Hq should formalize the agreement with KEFRI Hq. in Nairobi. The following day, a meeting was held in Maseno to assess the office and store space still in the name of ICRAF. It was agreed that ICRAF only keep the seed store, the nursery and the glass house. Two offices were returned to KEFRI as well as 2 stores. The stores were cleared and the few samples transferred to the nursery. ICRAF is still to remove old computers etc. from the nursery building – the ICRAF Kisumu administrator, Nicholas Shitukane, is preparing the inventory list for ICRAF Hq. to act on.

Progress report of the whole biophysical Lower Yala Block

By Joash Mango and Isaac Leramo

The main objective of the biophysical work is to characterize the landform, soil types and vegetation, they by giving the condition and the ecological indicators.

The lower Yala block comprises of 10km2 of which 60% of the area is under agricultural production, 30% is rangeland used as grazing land and 10% is a thicket formation with temporarily to access. The whole block has a total of sixteen cluster comprising of one hundred and sixty plots.

The earliest land conversion in the area took place in 1930’s and the recent conversion took place in 1980’s from wooded grassland to agricultural production land. The forage availability is limited to the rainy season and the immediate post rainy season

Range Condition.

The range condition is generally poor due to the impact caused by overgrazing and removal of vegetation and exposing the soil without any protective cover. This lowered the production of the land under increased soil erosion which left the soils with nutrients deficiencies.

Land forms.

The land forms are made up of foot slopes, uplands, hills valley complexes, wooded grassland and temporary restriction to access.

Vegetation types.

The vegetation types are composed of evergreen to semi deciduous bush land with perennial grass land and minor areas composed of wooded land.

Soil types.

The soil types range from shallow to very shallows, clay loam to loam, stony to gravel clay loam, sandy loam, silty clay, silty clay loam with varying depth and drainages.

Common trees species.

The dominant trees species include the followings; Markhemia lutea, Bridellia micranthus, Acacia polyacantha, Albizia grandibracteata, Teclea nobilis, Cussomia spec, Combretum molle and Ficus sycomorns.

Bushes/shrubs.

Most common shrubs or bushes in the area include the followings; Psidium guajava, Carissa edulis, Rhus vulgaris, Rhus natalensis, Euclea divinorum, Grewia bicolor, Acacia brevilpica, Acanthus pubsence and Lantana camara

Natural grasses.

Natural grasses are the main important grazing resource in the area though their availability varies in quantity and quality. When the quantity is adequate or the quality is low the animals face major nutritional problem. Other sources of animals feed in the area are shrubs and crop residue after harvest.

The most common grass species are as follows; Hyparrhenia variabilis, Hyparrhenia formusa, Digitaria Ciliaris, Chrysoblephana, Panicum maximum, Cynodo dectylon, Cynodon aethiopcus, Bracheria ambigeas, Digitaria gayana and Setaria species.

Some of the weeds in the area due to the succession caused by cultivation in the farm land are as follows; Leonotis neptifolia, Bidens pilosa, Biden biternata, Pavona pateas, Pavona galaensis, Triumfeta rhombodea.

Overgrazing indicator.

Through clearance of bushes, overgrazing and over utilization of land undesirable plant species and unpalatable grass species that produce little animal feed usually encroaches to succession. Some of the overgrazing indicators include Solanum incanum and Ipomes kituensis

Observations.

- Most trees are remnant and currently seen scattered across the block

- The bushes or shrub land are mostly secondary.

- Heavy destruction of woody vegetation is still an on going exercise for timber, charcoal production and fuel wood.

- Grass species found in the area are of low quality and of low grazing value with an exception of few species which are of good to medium grazing value and are also used for thatching e.g. Hyparrhemia spp and Panicam maximum.