Lower Yala Block Activities

2007

10th-21st December 2007

- Finish survival counts/tree measurements

- Plant degraded area (Alwala)

- Sensitization meetings in Dienya East degraded site.

2008

- Entering Data into the Data base (tree survival and other tree measurement parameters for both lower Yala and Lower Nyando)

- Sensitization meetings and implementation process in Upper Nyando block

- Work in the degraded sites

  - Alwala degraded site: - Continue planting tree seedlings and management which includes formation of contour check dams using vegetative locally available materials.

  - Dienya East degraded site:- digging of holes/ preparation for seedlings planting in LR

  - Preparing farmers with screening plots to receive and manage fruit trees that are among the incentives discussed.

  - Follow-up of tree screening trials and rehabilitation sites in lower Yala.